## MERP 2023-2027
MONITORING, EVALUATION AND RESEARCH PLAN 2023-2027
Instructions:
1. This template includes 3 mandatory activities: SN Mid-term Review, Country Gender Equality Profile and Country Portfolio Evaluation. DO NOT REMOVE THEM. 2. Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. 3. Please include all planned research, including the Country Gender Equality Profile (CGEP) that should be ready before development of the Common Country Assessment starts. Other knowledge products (guidance, tools, etc. should not be included in the MERP but in the Knowledge Product Plan developed at the beginning of each year. 4. Please fill out separate rows for each activity
| Fiji Multi Country Office | [11 empty] | Notes
| FIji MCO will undertake a Country Portfolio Evaluation (CPE) to assess the implementation of its Strategic Note 2023-2027, looking at both programmatic and operational effectiveness and efficiency This process will be co-managed by the Independent Evaluation Office (IEO) and the Fiji MCO. The CPE is expected to provide insights for the promotion of organizational learning and accountability, as well as inspire knowledge on what works and what doesn’t work to advance gender equality in the Pacific. and highlight the MCO's contribution to development effectiveness in the region. | [11 empty] | Following the revision of the UN Women Evaluation Policy and the new Policy and Procedure for Decentralized Evaluation, UN Women COs are required to conduct at least one Country Portfolio Evaluation (CPE) every two SN cycles. Therefore, the CPE together with the adequate (approximately $35,000) budgetary requirements should be reflected in the MERP
Monitoring and Research Plan 2023-2027
Monitoring
MCO | SN Mid-term Review |  |  |  |  | Fiji MCO + NRAs Israela Abrahamson | Internal UN Women | 2025 [ongoing data collection] | UN Women | Core | 60000
| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Outcome/ Output/ Flagship Program | Related indicator/KPI (Y/N, Indicator number, how and when | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors | Budget |  | Remarks
[10 empty] | Source | Amount USD
MCO | Country Outcomes Progress Reviews | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | All SN Indicators [inclusive of adopted SP indicators] | Qualitative and quantitative desk reviews of country reports and evaluations. Observations through annual / 6-monthly country missions and internal results reviews for validations. | Fiji MCO + NRAs Israela Abrahamson | Internal UN Women NPP Country Programme Coordinators, Country-based Staff and Programme Leads | 2023-2027 [Q4, Annual[ | UN Women | Staff time | Staff time | Country Monitoring Missions for Outcomes Progress Reviews and contributions to Pacific UNSDCF, CIPs and SP.
MCO | SN Six-Monthly Activity and Annual Results Monitoring (for Corporate reporting in RMS) | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | All SN Indicators [inclusive of adopted SP indicators] | Ongoing qualitative and quantitative programme and project data collections through desk reviews, surveys, interviews and observations, including in-country monitoring visits. | Fiji MCO + NRAs Programme Managers, Project M&E Staff | Internal UN Women NPP Country Programme Coordinators, Country-based Staff, and Programme Leads | 2023-2027 [Q2, Q4, Annual] | UN Women | Staff time | Staff time | Results reporting in June and January
MCO | UNSDCF Indicators monitoring and results reviews | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | UNSDCF indicators under UN Women's responsibility: [SDG 5.1.1, 5.c.1] | Desk reviews of internal results reports | Fiji MCO + NRAs Israela Abrahamson | internal UN Women programmes /projects | 2023-2027 [Q3,Q4, Annual] | UN Women Core | Staff time | Staff time | UN INFO Training Sept 2023
MCO | Gender Theme Group annual workplan monitoring | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | UNSDCF gender indicators under various UN agencies' responibilities | Desk reviews, interviews and observations. | Anne Rehagen | UN agencies | 2023-2027 [Q1-Q4, Annual] | N/A | Staff time | Staff time | UN Women provides secretariat support to the GTG and manages all GTG documentation
MCO | Gender Scorecard monitoring and reporting | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] |  |  | Desk reviews, interviews and observations. | Anne Rehagen | UN agencies | 2023-2027 [Q1-Q4, Annual] | N/A | Staff time | Staff time | This activity is led by the RCO with support from UN Women and the GTG
Fiji GPPL | Monitoring activities for the Access to Justice Project [Fiji] | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.1 | [Adopted SP indcators] 0.1.e, 0.5.c | Qualitative and quantitative project data collections through desk reviews, surveys, interviews and observations, including in-country monitoring visits. | Fiji TBD | Government of Fiji, Fiji Women's Rights Movement | 2024-2025 | PBF | Staff time | Staff time | Project to commence in 2024
Solomon Is GPPL | Monitoring activities for the Enhancing Access to Justice Project [Solomon Is] | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.2 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.1.e, 0.5.c | Qualitative and quantitative project data collections through desk reviews, interviews and observations, including in-country monitoring visits. | Solomon Islands Audrey Manu | Ministry of Women, Ministry of Justice | 2023-2024 | DFAT | Staff time | Staff time | Donor reporting throughout the year depending on project agreed timeline
Samoa GPPL | Monitoring activities for the Women in Leadership in Samoa [WILS] Project | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.2 | [Adopted SP indcators] 0.4.3, 0.1.e, 0.5.c | Qualitative and quantitative project data collections through desk reviews, interviews and observations, including in-country monitoring visits. | Samoa Mele Maualaivao | Ministry of Women, Community and Social Development, Village Councils | ends 2023 | DFAT | Staff time | Staff time | Project ends 2023
Samoa GPPL | Monitoring activities for the Addressing Stigma, Discrimination and Violence for Empowering Women with Disabilities (ASDWD) Project. | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.1 | [Adopted SP indcators] 0.4.3, 0.1.e, 0.5.c | Qualitative and quantitative project data collections through desk reviews,interviews and observations, including in-country monitoring visits. | Samoa Mele Maualaivao | UNDP, Ministry of Women, Community and Social Development, Nuanua O Le Alofa, Disability Advocacy Organisation in Samoa | ends 2023 | UNRPD | Staff time | Staff time | Project ends 2023
Samoa GPPL | Monitoring activities for the SDG Acceleration and Integrated National Financing Frameworks (INFF) Project | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.1 | [Adopted SP indcators] 0.2.1, 0.5.c | Qualitative and quantitative project data collections through desk reviews, interviews and observations, including in-country monitoring visits. | Samoa Mele Maualaivao | Ministry of Women, Ministry of Justice | ends 2023 | Joint SDG Fund | Staff time | Staff time | Project ends 2023
Fiji, Samoa, Solomon Is, Vanuatu WEE | Monitoring activities for the Markets for Change Project | UNSDCF Outcome 3 [Prosperity] | SN Outcomes Fiji FIJ_D_2.1, Solomon Is SLB_D_1.1, Samoa WSM_D_1.1, Vanuatu VUT_D_1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Qualitative and quantitative project data collections through desk reviews, surveys, interviews and observations. | Fiji MCO Preeya Ieli | Local / Provincial Governments, Municipal Councils, Market Vendor Associations, | 2023-2027 | DFAT | Staff time | Staff time | Donor reporting throughout the year depending on project agreed timeline
WEE/ M4C | Markets for Change (M4C) Annual Survey | UNSDCF Outcome 3 [Prosperity] | SN Outcomes Fiji FIJ_D_2.1, Solomon Is SLB_D_1.1, Samoa WSM_D_1.1, Vanuatu VUT_D_1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Survey of market vendors and municipal councils (AKVO) | Fiji, Samoa, Solomon Is, Vanuatu Preeya Ieli | Municipal Councils and Market Vendors | Jan - June 2024 | DFAT Canada | Non-core | 30000 | Questions in draft
WEE/ M4C | Baseline Study for Markers for Change (M4C) Samoa | UNSDCF Outcome 3 [Prosperity] | SN Outcome Samoa WSM_D_1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Qualitative and quantitative surveys, desk reviews, focus group discussions and interviews | Samoa Eric Groves | M4C Stakeholders including local government | 14-18 Oct 2023 | DFAT | Non-core | 20000 | Completed
Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | Monitoring activities for the Pacific Partnership to End VAWG Project | UNSDCF Outcome 2 [People] | SN Outcomes Fiji FIJ_D_3.1 Kiribati KIR_D_1.1 Samoa WSM_D_2.1 Solomon Is SLB_D_2.1 Tonga TON_D_1.1 Vanuatu VUT_D_2.2 | [Adopted SP indcators] 0.1.5, 0.3.2, 0.3.3, 0.4.3, 0.5.4, 0.6.3 0.1.e, 0.3.b, 0.3.c, 0.4.a, 0.4.b, 0.4.c, 0.5.c | Qualitative and quantitative project data collections through surveys, interviews and observations. | Fiji MCO Gabrielle Henderson | Various CSOs and Governments of Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | 2023-2027 | EU, DFAT, MFAT, UN Women | Staff time | Staff time | Donor reporting throughout the year depending on project agreed timeline
EVAW / PacP | Midline quantitative and qualitative data collection for Impact evaluation on Primary Prevention Programme in Kiribati | UNSDCF Outcome 2 [People] | SN Outcome Kiribati KIR_D_1.1 | [Adopted SP indcators] 0.5.4 0.5.c | quasi-experimental mixed methods design, incorporating quantitative baseline and endline surveys with qualitative components over the course of the SPV programme | Kiribati EVAW Prevention Technical Specialist | The Equality Institute and the Ministry for Women, Youth, Sport and Social Affairs (MWYSSA) | [ongoing from previous years] 2023, Q1-Q4 | EU | Non-core | 100000 | ongoing
Fiji Kiribati Solomon Is Vanuatu | Monitoring activities for the Women's Resilience to Disasters Project | UNSDCF Outcome 1 [Planet] | SN Outcome Fiji FIJ_D_4.1 | [Adopted SP indcators] 0.1.5, 0.2.4, 0.4.3 , 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.2.d, 0.4.a, 0.4.c, 0.4.d, 0.5.c, 0.5.d FIJ_4.1.1A, FIJ_4.1.1B, FIJ_4.1.4A, FIJ_4.1.4B | Qualitative and quantitative project data collections through surveys, interviews and observations. | Fiji MCO Naheed Ali | Various CSOs and Governments of Fiji, Kiribati, Solomon Is, Vanuatu | 2023-2027 | DFAT | Staff time | Staff time | Donor reporting throughout the year depending on project agreed timeline
Coordination | UNCT-SWAP Gender Equality Scorecard comprehensive review | Y | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | TBD | Anne Rehagen | Fiji MCO, Samoa MCO, Micronesia MCO | Y, [RCOs. UN agencies] | 2024 April - 2024 June | N/A | TBD | Not yet initiated | This was led and budgeted by RCO in 2020
Research
| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Outcome/ Output/ Flagship Program | Related indicator/KPI (Y/N, Indicator number, how and when | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors | Budget |  | Remarks
[10 empty] | Source | Amount USD
MCO | Mandatory: Country Gender Equality Profile | SN Impacts 1,2,3,4 | All Outcomes and Outputs |  | Yes | Fiji Anne Rehagen | UN Women partners, UN agencies, CSOs, Academic institutions, private sector | January - April 2026 | UN Women | Core | 100000
Evaluation Plan 2023-2027*
Evaluations in which the office leads
| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs2 | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
MCO | Mandatory: Country Programme Evaluation | Y | All | All | Fiji MCO Delphine Serumaga | Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | N | 2025 [Q1-Q2] | UN Women | Core 100,000 | pending |  | Following the revision of the UN Women Evaluation Policy and the new Policy and Procedure for Decentralized Evaluation, UN Women COs are required to conduct at least one Country Portfolio Evaluation (CPE) every two SN cycles. Therefore, the CPE together with the adequate (approximately $35,000) budgetary requirements should be reflected in the MERP
| Fiji Access to Justice Project | Y | UNSDCF Outcome 4 [Peace] GPPL | FIJ SN Outcome 1.1 | Fiji MCO TBD | Fiji | Y [UNDP] | 2025 June - 2025 Sept | PBF | Non-core 30,000 | pending | Consultancy
WEE/ M4C | Markets for Change Phase I End of Term Evaluation & Phase II Mid term Evaluation | y | UNSDCF Outcome 3 [Prosperity] WEE | FIJ SN Outcome 2.1 WSM SN Outcome 1.1 SLB SN Outcome 1.1 VUT SN Outcome 1.1 | Fiji MCO Preeya Ieli | Fiji, Samoa, Solomon Islands and Vanuatu | N | 2024 Feb - | DFAT | Non-core 80,000 | initiated | TOR drafting Q4 2023
WEE/ M4C | Markets for Change Final Evaluation | y | UNSDCF Outcome 3 [Prosperity] WEE | FIJ SN Outcome 2.1 WSM SN Outcome 1.1 SLB SN Outcome 1.1 VUT SN Outcome 1.3 | Fiji MCO Preeya Ieli | Fiji, Samoa, Solomon Islands and Vanuatu | N | 2026 Aug - 2026 Nov | DFAT | TBC | pending | Consultancy
WPSHDRR/ WRD | Women's Resilience to Disasters programme Final Evaluation | y | UNSDCF Outcome 1 [Planet] WPSHADRR | FIJ SN Output 4.1.3, 4.1.4 WRD Flagship | Fiji MCO Naheed Ahmed | Fiji, Kiribati, Solomon Is, Vanuatu | N | 2025 [months TBD] | DFAT | Non-core 200,000 | pending | Consultancy
Evaluations in which the office participates
| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs2 | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
GPPL / SDGF | Project Evaluation: Sustainable Financing for the 2030 Agenda through viable INFF in Cook Islands, Niue and Samoa | Y | UNSDCF Outcome 4 [Peace] GPPL | FIJ SN Output 1.1.1 | Mele Maualaivao | Samoa | Y [UNDP] | 2023-06-01 | MPTF - SDG Fund | Non-core 152,000 | Completed | Completed
GPPL / A2J | Project Evaluation: Access to Justice in Asia and Pacific Project | Y | UNSDCF Outcome 4 [Peace] GPPL | FIJ SN Output 1.1.2 | TBC | Solomon Islands | N | 2023-06-01 | TAR - Sweden SIDA Int. Dev. Coop. Agency | Non-core 300,000 | Completed | ROAP Project
GPPL / ASDWD | Project Evaluation: Addressing Stigma and Discrimination against Women with Disabilities (ASDWD) Project | Y | UNSDCF Outcome 4 [Peace] GPPL | FIJ SN Output 1.1.3 | Mele Maualaivao | Samoa | Y [UNDP] | 2023-06-01 | MPTF | Non-core 40,000 | Completed | Joint project with UNDP

## 2023-2024
MONITORING, EVALUATION AND RESEARCH PLAN 2023-2027
Instructions:
1. This template includes 3 mandatory activities: SN Mid-term Review, Country Gender Equality Profile and Country Portfolio Evaluation. DO NOT REMOVE THEM. 2. Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. 3. Please include all planned research, including the Country Gender Equality Profile (CGEP) that should be ready before development of the Common Country Assessment starts. Other knowledge products (guidance, tools, etc. should not be included in the MERP but in the Knowledge Product Plan developed at the beginning of each year. 4. Please fill out separate rows for each activity
| Fiji Multi Country Office | [11 empty] | Notes
| FIji MCO will undertake a Country Portfolio Evaluation (CPE) to assess the implementation of its Strategic Note 2023-2027, looking at both programmatic and operational effectiveness and efficiency This process will be co-managed by the Independent Evaluation Office (IEO) and the Fiji MCO. The CPE is expected to provide insights for the promotion of organizational learning and accountability, as well as inspire knowledge on what works and what doesn’t work to advance gender equality in the Pacific. and highlight the MCO's contribution to development effectiveness in the region. | [11 empty] | Following the revision of the UN Women Evaluation Policy and the new Policy and Procedure for Decentralized Evaluation, UN Women COs are required to conduct at least one Country Portfolio Evaluation (CPE) every two SN cycles. Therefore, the CPE together with the adequate (approximately $35,000) budgetary requirements should be reflected in the MERP
Monitoring and Research Plan 2023-2027
Monitoring
MCO | SN Mid-term Review |  |  |  |  | Fiji MCO + NRAs Israela Abrahamson | Internal UN Women | 2025 [ongoing data collection] | UN Women | Core | 60000
| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Outcome/ Output/ Flagship Program | Related indicator/KPI (Y/N, Indicator number, how and when | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors | Budget |  | Remarks
[10 empty] | Source | Amount USD
MCO | Country Outcomes Progress Reviews | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | All SN Indicators [inclusive of adopted SP indicators] | Qualitative and quantitative desk reviews of country reports and evaluations. Observations through annual / 6-monthly country missions and internal results reviews for validations. | Fiji MCO + NRAs Israela Abrahamson | Internal UN Women NPP Country Programme Coordinators, Country-based Staff and Programme Leads | 2023-2027 [Q4, Annual[ | UN Women | Staff time | Staff time | Country Monitoring Missions for Outcomes Progress Reviews and contributions to Pacific UNSDCF, CIPs and SP.
MCO | SN Six-Monthly Activity and Annual Results Monitoring and Reporting (for Corporate reporting in RMS) | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | All SN Indicators [inclusive of adopted SP indicators] | Ongoing qualitative and quantitative programme and project data collections through desk reviews, surveys, interviews and observations, including in-country monitoring visits. | Fiji MCO + NRAs Programme Managers, Project M&E Staff | Internal UN Women NPP Country Programme Coordinators, Country-based Staff, and Programme Leads | 2023-2027 [Q2, Q4, Annual] | UN Women | Staff time | Staff time | Results reporting in June and January
MCO | UNSDCF Indicators monitoring and results reviews | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | UNSDCF indicators under UN Women's responsibility: [SDG 5.1.1, 5.c.1] | Desk reviews of internal results reports | Fiji MCO + NRAs Israela Abrahamson | internal UN Women programmes /projects | 2023-2027 [Q3,Q4, Annual] | UN Women Core | Staff time | Staff time | UN INFO Training Sept 2023
MCO | Gender Theme Group annual workplan monitoring | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | UNSDCF gender indicators under various UN agencies' responibilities | Desk reviews, interviews and observations. | Anne Rehagen | UN agencies | 2023-2027 [Q1-Q4, Annual] | N/A | Staff time | Staff time | UN Women provides secretariat support to the GTG and manages all GTG documentation
MCO | UNCT Gender Scorecard Monitoring and Reporting | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN FIJ Outcome 1.2, Output 1.2.1 | SP_D_0.7.a, SP_D_0.7.b | Desk reviews, interviews and observations. | Anne Rehagen | UN agencies | 2023-2027 [Q1-Q4, Annual] | N/A | Staff time | Staff time | Began in 2024; finalisation in 2025. This activity is led by the RCO with support from UN Women and the GTG
| UNCT-SWAP Gender Equality Scorecard comprehensive review | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN FIJ Outcome 1.2, Output 1.2.1 | SP_D_0.7.a, SP_D_0.7.b | Desk reviews, interviews and observations. | Anne Rehagen | UN agencies | 2024 [July-Nov] | N/A | Staff time | Staff time | Began in 2024; finalisation in 2025. This activity is led by the RCO with support from UN Women and the GTG
Fiji GPPL | Monitoring activities for the Access to Justice Project [Fiji] | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.1 | [Adopted SP indcators] 0.1.e, 0.5.c | Qualitative and quantitative project data collections through desk reviews, surveys, interviews and observations, including in-country monitoring visits. | Fiji TBD | Government of Fiji, Fiji Women's Rights Movement | 2024-2025 | PBF | Staff time | Staff time | Project to commence in 2024
Solomon Is GPPL | Monitoring activities for the Enhancing Access to Justice Project [Solomon Is] | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.2 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.1.e, 0.5.c | Qualitative and quantitative project data collections through desk reviews, interviews and observations, including in-country monitoring visits. | Solomon Islands Audrey Manu | Ministry of Women, Ministry of Justice | 2023-2024 | DFAT | Staff time | Staff time | Donor reporting throughout the year depending on project agreed timeline
Samoa GPPL | Monitoring activities for the Women in Leadership in Samoa [WILS] Project | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.2 | [Adopted SP indcators] 0.4.3, 0.1.e, 0.5.c | Qualitative and quantitative project data collections through desk reviews, interviews and observations, including in-country monitoring visits. | Samoa Mele Maualaivao | Ministry of Women, Community and Social Development, Village Councils | ends 2023 | DFAT | Staff time | Staff time | Project ends 2023
Samoa GPPL | Monitoring activities for the Addressing Stigma, Discrimination and Violence for Empowering Women with Disabilities (ASDWD) Project. | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.1 | [Adopted SP indcators] 0.4.3, 0.1.e, 0.5.c | Qualitative and quantitative project data collections through desk reviews,interviews and observations, including in-country monitoring visits. | Samoa Mele Maualaivao | UNDP, Ministry of Women, Community and Social Development, Nuanua O Le Alofa, Disability Advocacy Organisation in Samoa | ends 2023 | UNRPD | Staff time | Staff time | Project ends 2023
Samoa GPPL | Monitoring activities for the SDG Acceleration and Integrated National Financing Frameworks (INFF) Project | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.1 | [Adopted SP indcators] 0.2.1, 0.5.c | Qualitative and quantitative project data collections through desk reviews, interviews and observations, including in-country monitoring visits. | Samoa Mele Maualaivao | Ministry of Women, Ministry of Justice | ends 2023 | Joint SDG Fund | Staff time | Staff time | Project ends 2023
Fiji, Samoa, Solomon Is, Vanuatu WEE | Monitoring activities for the Markets for Change Project Phase I [DAMS 12509] | UNSDCF Outcome 3 [Prosperity] | SN Outcomes Fiji FIJ_D_2.1, Solomon Is SLB_D_1.1, Samoa WSM_D_1.1, Vanuatu VUT_D_1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Qualitative and quantitative project data collections through desk reviews, surveys, interviews and observations. | Fiji MCO Preeya Ieli | Local / Provincial Governments, Municipal Councils, Market Vendor Associations, | April 2018 - Dec 2023 | DFAT Canada MFAT | Staff time | Staff time | Donor reporting throughout the year depending on project agreed timeline
| Monitoring activities for the Markets for Change Project Phase II [DAMS 13948] | UNSDCF Outcome 3 [Prosperity] | SN Outcomes Fiji FIJ_D_2.1, Solomon Is SLB_D_1.1, Samoa WSM_D_1.1, Vanuatu VUT_D_1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Qualitative and quantitative project data collections through desk reviews, surveys, interviews and observations. | Fiji MCO Preeya Ieli | Local / Provincial Governments, Municipal Councils, Market Vendor Associations, | April 2022-June 2026 | DFAT | Staff time | Staff time
WEE/ M4C | Markets for Change (M4C) Annual Survey | UNSDCF Outcome 3 [Prosperity] | SN Outcomes Fiji FIJ_D_2.1, Solomon Is SLB_D_1.1, Samoa WSM_D_1.1, Vanuatu VUT_D_1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Survey of market vendors and municipal councils (AKVO) | Fiji, Samoa, Solomon Is, Vanuatu Preeya Ieli | Municipal Councils and Market Vendors | Jan - June 2024 | DFAT Canada | Non-core | 30000 | Questions in draft
WEE/ M4C | Baseline Study for Markers for Change (M4C) Samoa | UNSDCF Outcome 3 [Prosperity] | SN Outcome Samoa WSM_D_1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Qualitative and quantitative surveys, desk reviews, focus group discussions and interviews | Samoa Eric Groves | M4C Stakeholders including local government | 14-18 Oct 2023 | DFAT | Non-core | 20000 | Completed
Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | Monitoring activities for the Pacific Partnership to End VAWG Project | UNSDCF Outcome 2 [People] | SN Outcomes Fiji FIJ_D_3.1 Kiribati KIR_D_1.1 Samoa WSM_D_2.1 Solomon Is SLB_D_2.1 Tonga TON_D_1.1 Vanuatu VUT_D_2.2 | [Adopted SP indcators] 0.1.5, 0.3.2, 0.3.3, 0.4.3, 0.5.4, 0.6.3 0.1.e, 0.3.b, 0.3.c, 0.4.a, 0.4.b, 0.4.c, 0.5.c | Qualitative and quantitative project data collections through surveys, interviews and observations. | Fiji MCO Gabrielle Henderson | Various CSOs and Governments of Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | 2023-2027 | EU, DFAT, MFAT, UN Women | Staff time | Staff time | Donor reporting throughout the year depending on project agreed timeline
EVAW / PacP | Midline quantitative and qualitative data collection for Impact evaluation on Primary Prevention Programme in Kiribati | UNSDCF Outcome 2 [People] | SN Outcome Kiribati KIR_D_1.1 | [Adopted SP indcators] 0.5.4 0.5.c | quasi-experimental mixed methods design, incorporating quantitative baseline and endline surveys with qualitative components over the course of the SPV programme | Kiribati EVAW Prevention Technical Specialist | The Equality Institute and the Ministry for Women, Youth, Sport and Social Affairs (MWYSSA) | [ongoing from previous years] 2023, Q1-Q4 | EU | Non-core | 100000 | ongoing
Fiji Kiribati Solomon Is Vanuatu | Monitoring activities for the Women's Resilience to Disasters Project | UNSDCF Outcome 1 [Planet] | SN Outcome Fiji FIJ_D_4.1 | [Adopted SP indcators] 0.1.5, 0.2.4, 0.4.3 , 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.2.d, 0.4.a, 0.4.c, 0.4.d, 0.5.c, 0.5.d FIJ_4.1.1A, FIJ_4.1.1B, FIJ_4.1.4A, FIJ_4.1.4B | Qualitative and quantitative project data collections through surveys, interviews and observations. | Fiji MCO Naheed Ali | Various CSOs and Governments of Fiji, Kiribati, Solomon Is, Vanuatu | 2023-2027 | DFAT | Staff time | Staff time | Donor reporting throughout the year depending on project agreed timeline
Coordination | UNCT-SWAP Gender Equality Scorecard comprehensive review | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN FIJ Outcome 1.2, Output 1.2.1 | SP_D_0.7.a, SP_D_0.7.b | Desk reviews, interviews and observations. | Fiji MCO, Samoa MCO, Micronesia MCO Anne Rehagen | Y, [RCOs. UN agencies] | 2024 May- 2024 Nov | N/A | TBD | Not yet initiated | This was led and budgeted by RCO in 2020
Research
| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Outcome/ Output/ Flagship Program | Related indicator/KPI (Y/N, Indicator number, how and when | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors | Budget |  | Remarks
[10 empty] | Source | Amount USD
MCO | Mandatory: Country Gender Equality Profile | SN Impacts 1,2,3,4 | All Outcomes and Outputs |  | Yes | Fiji Anne Rehagen | UN Women partners, UN agencies, CSOs, Academic institutions, private sector | January - April 2026 | UN Women | Core | 100000
Evaluation Plan 2023-2027*
Evaluations in which the office leads
| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs2 | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
MCO | Mandatory: Country Programme Evaluation | Y | All | All | Fiji MCO Delphine Serumaga | Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | N | 2025 [Q1-Q2] | UN Women | Core 100,000 | pending |  | Following the revision of the UN Women Evaluation Policy and the new Policy and Procedure for Decentralized Evaluation, UN Women COs are required to conduct at least one Country Portfolio Evaluation (CPE) every two SN cycles. Therefore, the CPE together with the adequate (approximately $35,000) budgetary requirements should be reflected in the MERP
WEE/ M4C | Markets for Change Phase I End of Term Evaluation & Phase II Mid term Evaluation | y | UNSDCF Outcome 3 [Prosperity] WEE | FIJ SN Outcome 2.1 WSM SN Outcome 1.1 SLB SN Outcome 1.1 VUT SN Outcome 1.1 | Fiji MCO Preeya Ieli | Fiji, Samoa, Solomon Islands and Vanuatu | N | 2024 Feb - | DFAT | Non-core 80,000 | initiated | TOR drafting Q4 2023
WEE/ M4C | Markets for Change Final Evaluation | y | UNSDCF Outcome 3 [Prosperity] WEE | FIJ SN Outcome 2.1 WSM SN Outcome 1.1 SLB SN Outcome 1.1 VUT SN Outcome 1.3 | Fiji MCO Preeya Ieli | Fiji, Samoa, Solomon Islands and Vanuatu | N | 2026 Aug - 2026 Nov | DFAT | TBC | pending | Consultancy
EVAW/PP | Pacific Partnership to End VAW Mid term Review | Y | UNSDCF Outcome 2 [People] EVAW | FIJ SN Outcome 3.1 KIR SN Outcome 1.1 WSM SN Outcome 1.2 SLB SN Outcome 1.2 TON SN Outcome 1.1 VUT SN Outcome 1.2 | Fiji MCO Gabrielle Henderson | Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | N | 2026 [months TBD] | DFAT | TBC | pending | Consultancy
WPSHDRR/ WRD | Women's Resilience to Disasters programme Final Evaluation | y | UNSDCF Outcome 1 [Planet] WPSHADRR | FIJ SN Output 4.1.3, 4.1.4 WRD Flagship | Fiji MCO Naheed Ahmed | Fiji, Kiribati, Solomon Is, Vanuatu | N | 2025 [months TBD] | DFAT | Non-core 200,000 | pending | Consultancy
Evaluations in which the office participates
| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs2 | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
GPPL / SDGF | Project Evaluation: Sustainable Financing for the 2030 Agenda through viable INFF in Cook Islands, Niue and Samoa | Y | UNSDCF Outcome 4 [Peace] GPPL | FIJ SN Output 1.1.1 | Mele Maualaivao | Samoa | Y [UNDP] | 2023-06-01 | MPTF - SDG Fund | Non-core 152,000 | Completed | Completed
GPPL / A2J | Project Evaluation: Access to Justice in Asia and Pacific Project | Y | UNSDCF Outcome 4 [Peace] GPPL | FIJ SN Output 1.1.2 | Kaushal Sharma | Solomon Islands | N | 2023-06-01 | TAR - Sweden SIDA Int. Dev. Coop. Agency | Non-core 300,000 | Completed | ROAP Project
GPPL / ASDWD | Project Evaluation: Addressing Stigma and Discrimination against Women with Disabilities (ASDWD) Project | Y | UNSDCF Outcome 4 [Peace] GPPL | FIJ SN Output 1.1.3 | Mele Maualaivao | Samoa | Y [UNDP] | 2023-06-01 | MPTF | Non-core 40,000 | Completed | Joint project with UNDP
| Mid=Term Review of the Pacific UNSDCF 2023-2027 [2025] | Y | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | TBD | Anne Rehagen Israela Abrahamson | Fiji MCO, Samoa MCO, Micronesia MCO | Y, [RCOs. UN agencies] | 2025 [months TBD] | TBD | TBD | Not yet initiated | RCO led
Reviews
WPSHDRR/ WRD | Midterm Review of the WRD Program | y | Solomon Islands | FIJ Outcome 1.4 Output 4.1.2,4.1.3, 4.1.4 | Fiji MCO Naheed Ahmed | Fiji, Kiribati, Solomon Is, Vanuatu | N | July-2023- Oct 2023 | DFAT | Non-core 100,000 | pending | Consultancy

## 2025
MONITORING, EVALUATION AND RESEARCH PLAN 2025
Instructions:
1. This template includes 3 mandatory activities: SN Mid-term Review, Country Gender Equality Profile and Country Portfolio Evaluation. DO NOT REMOVE THEM. 2. Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. 3. Please include all planned research, including the Country Gender Equality Profile (CGEP) that should be ready before development of the Common Country Assessment starts. Other knowledge products (guidance, tools, etc. should not be included in the MERP but in the Knowledge Product Plan developed at the beginning of each year. 4. Please fill out separate rows for each activity
| Fiji Multi Country Office | [11 empty] | Notes
| FIji MCO will undertake a Country Portfolio Evaluation (CPE) to assess the implementation of its Strategic Note 2023-2027, looking at both programmatic and operational effectiveness and efficiency This process will be co-managed by the Independent Evaluation Office (IEO) and the Fiji MCO. The CPE is expected to provide insights for the promotion of organizational learning and accountability, as well as inspire knowledge on what works and what doesn’t work to advance gender equality in the Pacific. and highlight the MCO's contribution to development effectiveness in the region. | [11 empty] | Following the revision of the UN Women Evaluation Policy and the new Policy and Procedure for Decentralized Evaluation, UN Women COs are required to conduct at least one Country Portfolio Evaluation (CPE) every two SN cycles. Therefore, the CPE together with the adequate (approximately $35,000) budgetary requirements should be reflected in the MERP
Monitoring and Research Plan 2025
Monitoring
MCO | SN Mid-term Review |  |  |  |  | Fiji MCO + NRAs Israela Abrahamson | Internal UN Women | 2025 [ongoing data collection] | UN Women | Core | 60000
| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Outcome/ Output/ Flagship Program | Related indicator/KPI (Y/N, Indicator number, how and when | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month/Quarter and year of start and end) | Donors | Budget |  | Remarks
[10 empty] | Source | Amount USD
MCO | Country Outcomes Progress Reviews | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | All SN Indicators [inclusive of adopted SP indicators] | Qualitative and quantitative desk reviews of country reports and evaluations. Observations through annual / 6-monthly country missions and internal results reviews for validations. | Fiji MCO + NRAs Israela Abrahamson | Internal UN Women NPP Country Programme Coordinators, Country-based Staff and Programme Leads | 2023-2027 [Q1] | UN Women | Staff time | Staff time | Country Monitoring Missions for Outcomes Progress Reviews and contributions to Pacific UNSDCF, CIPs and SP. Also for MCO Results Report
MCO | SN Six-Monthly Activity and Annual Results Monitoring and Reporting (for Corporate reporting in RMS) | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | All SN Indicators [inclusive of adopted SP indicators] | Ongoing qualitative and quantitative programme and project data collections through desk reviews, surveys, interviews and observations, including in-country monitoring visits. | Fiji MCO + NRAs Programme Managers, Project M&E Staff | Internal UN Women NPP Country Programme Coordinators, Country-based Staff, and Programme Leads | 2023-2027 [Q1-Q2, Q3-Q4, Annual] | UN Women | Staff time | Staff time | Results reporting in June and January
MCO | UNSDCF Results Reviews | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | UNSDCF indicators under UN Women's responsibility: [SDG 5.1.1, 5.c.1] | Desk reviews of internal results reports | Fiji MCO + NRAs Israela Abrahamson | internal UN Women programmes /projects | 2023-2027 [Q1-Q4] | UN Women Core | Staff time | Staff time | Update UNSDCF Results (2024 cycle and ongoing 2025]
MCO | Gender Theme Group annual workplan monitoring | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | UNSDCF gender indicators under various UN agencies' responibilities | Desk reviews, interviews and observations. | Anne Rehagen | UN agencies | 2023-2027 [Q1-Q4] | N/A | Staff time | Staff time | UN Women provides secretariat support to the GTG and manages all GTG documentation
MCO | UNCT Gender Scorecard Monitoring and Reporting | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SP Outcome 7 UN Coordination for GE SN FIJ Outcome 1.2, Output 1.2.1 UNSDCF Outcome: 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SP_D_0.7.a, SP_D_0.7.b | Desk reviews, interviews and observations. | Anne Rehagen | UN agencies | 2023-2027 [Q1-Q4] | N/A | Staff time | Staff time
Coordination | UNCT-SWAP Gender Equality Scorecard comprehensive review | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SP Outcome 7 UN Coordination for GE SN FIJ Outcome 1.2, Output 1.2.1 UNSDCF Outcomes: 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SP_D_0.7.a, SP_D_0.7.b | Desk reviews, interviews and observations. | Anne Rehagen | Fiji MCO, Samoa MCO, Micronesia MCO | 2024 April - 2024 June | N/A | TBD | Not yet initiated | This was led and budgeted by RCO in 2020
Fiji GPPL | Monitoring activities for the Strengthening Social Cohesion Pathways, Human Rights and Women's Civic Participation Project [DAMS 14490] | UNSDCF Outcome 4 [Peace] | SN Output Fiji FIJ_D_1.1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.1.e, 0.5.c | Qualitative and quantitative project data collections through desk reviews, surveys, interviews and observations, including in-country monitoring visits. | Fiji TBD | Government of Fiji, Fiji Women's Rights Movement | Oct 2023-Oct 2025 [Q1-Q4] | MPTFO | Non-core | Staff time | Donor reporting
Fiji, Samoa, Solomon Is, Vanuatu WEE | Monitoring activities for the Markets for Change Project Phase II [DAMS 13948] | UNSDCF Outcome 3 [Prosperity] | SN Outcomes Fiji FIJ_D_2.1, Solomon Is SLB_D_1.1, Samoa WSM_D_1.1, Vanuatu VUT_D_1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Qualitative and quantitative project data collections through desk reviews, surveys, interviews and observations. | Fiji MCO Preeya Ieli | Local / Provincial Governments, Municipal Councils, Market Vendor Associations, | April 2022-June 2026 [Q1-Q4] | DFAT | Non-core | Staff time | Donor reporting
| Monitoring activities for the Joint Programme on "Accelerating Progress towards Rural Women's Economic Empowerment" (JP RWEE) [DAMS 14204] | UNSDCF Outcome 3 [Prosperity] | SN Outcomes Fiji FIJ_D_2.1, Solomon Is SLB_D_1.1, Samoa WSM_D_1.1, Vanuatu VUT_D_1.2 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Qualitative and quantitative project data collections through desk reviews, surveys, interviews and observations. | Fiji MCO Preeya Ieli | Local / Provincial Governments, Municipal Councils, Market Vendor Associations, | July 2022-May 2027 [Q1-Q4] | MPTF | Non-core | Staff time | Donor reporting
WEE/ M4C | Markets for Change (M4C) Annual Survey | UNSDCF Outcome 3 [Prosperity] | SN Outcomes Fiji FIJ_D_2.1, Solomon Is SLB_D_1.1, Samoa WSM_D_1.1, Vanuatu VUT_D_1.1 | [Adopted SP indcators] 0.1.5, 0.4.3, 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.4.a, 0.4.d, 0.5.c, 0.5.d, 0.5.e | Survey of market vendors and municipal councils (AKVO) | Fiji, Samoa, Solomon Is, Vanuatu Preeya Ieli | Municipal Councils and Market Vendors | Jan - June 2025 [Q1-Q2] | DFAT Canada | Non-core | 30000 | Questions in draft
| Monitoring activities for the Pacific Partnership to End VAWG Project - Phase I [DAMS 12552] | UNSDCF Outcome 2 [People] | SN Outcomes Fiji FIJ_D_3.1 Kiribati KIR_D_1.1 Samoa WSM_D_2.1 Solomon Is SLB_D_2.1 Tonga TON_D_1.1 Vanuatu VUT_D_2.2 | [Adopted SP indcators] 0.1.5, 0.3.2, 0.3.3, 0.4.3, 0.5.4, 0.6.3 0.1.e, 0.3.b, 0.3.c, 0.4.a, 0.4.b, 0.4.c, 0.5.c | Qualitative and quantitative project data collections through surveys, interviews and observations. | Fiji MCO Abigail Erikson | Various CSOs and Governments of Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | Jan 2018-Dec 2023 [Q1-Q4] | EU, DFAT, MFAT, UN Women | Non-core | Staff time | Donor reporting throughout the year depending on project agreed timeline
Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | Monitoring activities for the Pacific Partnership to End VAWG Project - Phase II [DAMS 14400] | UNSDCF Outcome 2 [People] | SN Outcomes Fiji FIJ_D_3.1 Kiribati KIR_D_1.1 Samoa WSM_D_2.1 Solomon Is SLB_D_2.1 Tonga TON_D_1.1 Vanuatu VUT_D_2.2 | [Adopted SP indcators] 0.1.5, 0.3.2, 0.3.3, 0.4.3, 0.5.4, 0.6.3 0.1.e, 0.3.b, 0.3.c, 0.4.a, 0.4.b, 0.4.c, 0.5.c | Qualitative and quantitative project data collections through surveys, interviews and observations. | Fiji MCO Jurgita Sereikaite | Various CSOs and Governments of Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | July 2023- June 2027 [Q1-Q4] | EU, DFAT, UN Women | Non-core | Staff time | Donor reporting throughout the year depending on project agreed timeline
EVAW / PacP | Midline quantitative and qualitative data collection for Impact evaluation on Primary Prevention Programme in Kiribati | UNSDCF Outcome 2 [People] | SN Outcome Kiribati KIR_D_1.1 | [Adopted SP indcators] 0.5.4 0.5.c | quasi-experimental mixed methods design, incorporating quantitative baseline and endline surveys with qualitative components over the course of the SPV programme | Kiribati EVAW Prevention Technical Specialist | The Equality Institute and the Ministry for Women, Youth, Sport and Social Affairs (MWYSSA) | [ongoing from previous years] 2023, Q1-Q4 | EU | Non-core | 100000 | ongoing
Fiji Kiribati Solomon Is Vanuatu | Monitoring activities for the Women's Resilience to Disasters Project [DAMS 13695] | UNSDCF Outcome 1 [Planet] | SN Outcome Fiji FIJ_D_4.1 | [Adopted SP indcators] 0.1.5, 0.2.4, 0.4.3 , 0.5.4, 0.7.7 0.1.e, 0.1.h, 0.2.d, 0.4.a, 0.4.c, 0.4.d, 0.5.c, 0.5.d FIJ_4.1.1A, FIJ_4.1.1B, FIJ_4.1.4A, FIJ_4.1.4B | Qualitative and quantitative project data collections through surveys, interviews and observations. | Fiji MCO Naheed Ali | Various CSOs and Governments of Fiji, Kiribati, Solomon Is, Vanuatu | June 2021-June 2025 [Q1-Q4] | DFAT Core | Non-core | Staff time | Donor reporting throughout the year depending on project agreed timeline
| Monitoring activities for the Gender in Humanitarian Action programme | UNSDCF Outcome 1 [Planet] | SN Outcome Fiji FIJ_D_4.1 | [Adopted SP indcators] 0.1.5, 0.2.4, 0.4.3, 0.5.4 0.1.e, 0.4.a, 0.4.c, 0.4.d, 0.5.c, 0.5.d | Qualitative and quantitative project data collections through surveys, interviews and observations. | Fiji MCO Kolosa Matebalavu | Governments of Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu, women's CSOs | 2024-2027 [Q1-Q4] | DFAT Core | Non-core | Staff time
| Mandatory: Strategic Note Mid Term Review | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | SN Outcomes [all 4] SN Outputs [all 16] | All SN Indicators [inclusive of adopted SP indicators] | Qualitative and quantitative desk reviews of country reports and evaluations. Country missions and internal results reviews for validations. | Fiji MCO Israela Abrahamson | Various CSOs and Governments of Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | TBC | UN Women | Core | TBC | Optional
Research
| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Outcome/ Output/ Flagship Program | Related indicator/KPI (Y/N, Indicator number, how and when | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors | Budget |  | Remarks
[10 empty] | Source | Amount USD
MCO | Mandatory: Country Gender Equality Profile | SN Impacts 1,2,3,4 | All Outcomes and Outputs |  | Yes | Fiji Anne Rehagen | UN Women partners, UN agencies, CSOs, Academic institutions, private sector | June-Nov 2026 | UN Women | Core | 100000 | 2026 !4 Countries / 1 Regional
| Research on Climate Change and GBV | SN Impact 3 | Outcome 2 | No | Yes | Jurgita Sereikaite | TBD | May-July 2025 | DFAT / EU | Non-core | 256000 | FIJ_D_3.1.1.31 Generate evidence on the link between climate change and the root causes and contributing factors of VAWG to inform primary and secondary prevention policies and programmes, including the exploration of a “climate stress” measure.
Evaluation Plan 2025-2026*
Evaluations in which the office leads
| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs2 | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
MCO | Mandatory: Country Portfolio Evaluation | Y | All | All | Fiji MCO Delphine Serumaga | Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | N | Feb- May 2026 | UN Women | Core 35,000 | pending | 2026 | Following the revision of the UN Women Evaluation Policy and the new Policy and Procedure for Decentralized Evaluation, UN Women COs are required to conduct at least one Country Portfolio Evaluation (CPE) every two SN cycles. Therefore, the CPE together with the adequate (approximately $35,000) budgetary requirements should be reflected in the MERP
WPSHDRR/ WRD | Women's Resilience to Disasters programme Final Evaluation | y | UNSDCF Outcome 1 [Planet] SP Impact 4 WPSHADRR | FIJ SN Output 4.1.3, 4.1.4 WRD Flagship | Fiji MCO Naheed Ahmed | Fiji, Kiribati, Solomon Is, Vanuatu | N | March - June 2025 | DFAT | Non-core 50,000 | pending | possible Cost share with Global
| Rugby Plus impact Evaluation [Fiji and Samoa] | N | UNSDCF 2 (people) | FIJ SN Output 3.2.1 EVAW PEVAW Outcome 2 | Fiji MCO Jurgita Sereikaite | Fiji, Samoa | N | June - Sept 2025 | DFAT | Non-core 95,847 | pending | FIJ_D_3.1.1.26 Design and implement one to two impact evaluations of community-based prevention programmes in faith and/or sport to generate additional evidence on what works in diverse Pacific communities to transform harmful attitudes, beliefs and norms regarding the acceptability of VAWG in the Pacific. UN Women will work with global leaders in prevention of VAWG research to advance feminist research approaches and more intentionally support the documentation of practice-based knowledge to drill into the nuances of what works in the diverse context of the Pacific region.
Evaluations in which the office participates
| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs2 | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
GPPL / ASDWD | Project Evaluation: Addressing Stigma and Discrimination against Women with Disabilities (ASDWD) Project | Y | UNSDCF Outcome 4 [Peace] GPPL | FIJ SN Output 1.1.3 | Mele Maualaivao | Samoa | Y [UNDP] | 2023-06-01 | MPTF | Non-core 40,000 | Completed | Joint project with UNDP
| Mid=Term Evaluation of the Pacific UNSDCF 2023-2027 [2025] | Y | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | TBD | Anne Rehagen Israela Abrahamson | Fiji MCO, Samoa MCO, Micronesia MCO | Y, [RCOs. UN agencies] | 2025 July-Nov | TBD | TBD | Not yet initiated | RCO led

## 2023-2027 Gantt
MERP 2023-2027
| 2023 | [11 empty] | 2024 | [11 empty] | 2025 | [11 empty] | 2026 | [11 empty] | 2027
MONITORING | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Aug | Sept | Oct | Nov | Dec
Country Outcomes Progress Reviews | bar: 2023 Jan to 2023 Mar; 2024 Jan to 2024 Mar; 2025 Jan to 2025 Mar; 2026 Jan to 2026 Mar; 2027 Jan to 2027 Mar
SN Six-Monthly Activity and Annual Results Monitoring (for Corporate reporting in RMS)
UNSDCF Results Reviews
Gender Theme Group annual workplan monitoring
UNCT Gender Scorecard Monitoring and Reporting
UNCT-SWAP Gender Equality Scorecard comprehensive review | bar: 2024 May to 2024 Nov
Monitoring activities for the Enhancing Access to Justice Project [Solomon Is] | bar: 2023 Jan to 2023 Dec
Monitoring activities for the Women in Leadership in Samoa [WILS] Project | bar: 2023 Jan to 2023 Dec
Monitoring activities for the Addressing Stigma, Discrimination and Violence for Empowering Women with Disabilities (ASDWD) Project. | bar: 2023 Jan to 2023 Dec
Monitoring activities for the SDG Acceleration and Integrated National Financing Frameworks (INFF) Project | bar: 2023 Jan to 2023 Dec
Monitoring activities for the Strengthening Social Cohesion Pathways, Human Rights and Women's Civic Participation Project [DAMS 14490] | bar: 2023 Oct to 2025 Sept
Monitoring activities for the Markets for Change Project Phase I [DAMS 12509] | bar: 2023 Jan to 2023 Dec
Monitoring activities for the Markets for Change Project Phase II [DAMS 13948] | bar: 2023 Jan to 2026 June
Monitoring activities for the Joint Programme on "Accelerating Progress towards Rural Women's Economic Empowerment" (JP RWEE) [DAMS 14204] | bar: 2023 Jan to 2027 May
Markets for Change (M4C) Annual Survey | bar: 2025 Jan to 2025 June
Baseline Study for Markers for Change (M4C) Samoa | bar: 2023 Oct
Monitoring activities for the Pacific Partnership to End VAWG Project Phase I [DAMS 12552] | bar: 2023 Jan to 2023 Dec
Monitoring activities for the Pacific Partnership to End VAWG Project Phase II [DAMS 14400]
Midline quantitative and qualitative data collection for Impact evaluation on Primary Prevention Programme in Kiribati | bar: 2023 Jan to 2024 Dec
Monitoring activities for the Gender in Humanitarian Action programme | bar: 2023 Jan to 2025 Dec
Monitoring activities for the Women's Resilience to Disasters Project [DAMS 13695] | bar: 2023 Jan to 2025 June
Strategic Note Mid Term Review
RESEARCH | bar: 2023 Jan to 2025 Dec
Country Gender Equality Profile | bar: 2026 Jan to 2026 Apr
Cimate Change and GBV | bar: 2025 May to 2025 July
EVALUATION - UN Women leads | bar: 2023 Jan to 2025 Dec
Markets for Change Phase I End of Term Evaluation & Phase II Mid term Evaluation | bar: 2024 June to 2024 Oct
Women's Resilience to Disasters programme Final Evaluation | bar: 2025 Mar to 2025 June
Rugby Plus (Fiji and Samoa) impact Evaluation | bar: 2025 June to 2025 Sept
Country Portfolio Evaluation | bar: 2026 Mar to 2026 July
EVALUATION - UN Women participates | bar: 2023 Jan to 2025 Dec
Project Evaluation: Sustainable Financing for the 2030 Agenda through viable INFF in Cook Islands, Niue and Samoa | bar: 2023 Jan to 2023 June
Project Evaluation: Access to Justice in Asia and Pacific Project | bar: 2023 Jan to 2023 June
Project Evaluation: Addressing Stigma and Discrimination against Women with Disabilities (ASDWD) Project | bar: 2023 Jan to 2023 June
Mid-Term Evalaution of the Pacific UNSDCF 2023-2027 [2025] | bar: 2025 July to 2025 Nov

## Reviews
REVIEWS
Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs2 | SN Impact, Outcome, Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
Midterm Review of the Fiji MCO Strategic Note | Y | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | FIJ Impact 1,2,3,4 | Fiji MCO Israela Abrahamson | Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | N | June-Oct 2025 |  | Core 80,000 | Pending | Consultancy
Midterm Review of the WRD Program | y | UNSDCF Outcome 1 [Planet] | FIJ Outcome 1.4 Output 4.1.2,4.1.3, 4.1.4 | Fiji MCO Naheed Ahmed | Fiji, Kiribati, Solomon Is, Vanuatu | N | July-2023- Oct 2023 | DFAT | Non-core 50,000 | completed | Consultancy
Pacific Partnership to End VAW Mid term Review | Y | UNSDCF Outcome 2 [People] EVAW | FIJ SN Outcome 3.1 KIR SN Outcome 1.1 WSM SN Outcome 1.2 SLB SN Outcome 1.2 TON SN Outcome 1.1 VUT SN Outcome 1.2 | Fiji MCO Gabrielle Henderson | Fiji, Kiribati, Samoa, Solomon Is, Tonga, Vanuatu | N | 2026 [months TBD] | DFAT | TBC | pending | Consultancy
Mid-Term Review of the Pacific UNSDCF 2023-2027 [2025] | Y | UNSDCF Outcomes 1 [Planet], 2 [People], 3 [Prosperity], 4 [Peace] | TBD | Anne Rehagen Israela Abrahamson | Fiji MCO, Samoa MCO, Micronesia MCO | Y, [RCOs. UN agencies] | 2025 [months TBD] | TBC | TBC | Not yet initiated | RCO led