MONITORING, EVALUATION AND RESEARCH PLAN 2014-2017

Monitoring and Research Plan 2014

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount USD |
| MONITORING |  |  |  |  |
| Product and disseminate office trimestral report | Implementation Partners | Trimestral : March, June, September and December 2014 |  | Memory |
| Product and disseminate office annual report | Implementation Partners | December 2014 |  | 5000 |
| Product and disseminate donors’ report | Implementation Partners s | April, December 2014 |  | Memory |
| Undertake monitoring missions on the field | Implementation Partners | Trimestral : March, June, September and December 2014 |  | 12000 |
| Organize middle and final office Mali review (office retreat) | Implementation Partners | June and December 2014 |  | 25000 |
| Establish and manage monitoring and evaluation system | Implementation Partners | January-December 2014 |  | 16000 |
| RESEARCH |  |  |  |  |
| Realize study CAP on violence’s against women and girls in conflict situation | INSTAT, Major General State Armed | January-March 2014 | 00084608 | 72000 |
| Document and disseminate good practices and success cases | Implementation Partners | June-December2014 | 00084608 | 5000 |
| Conduct a specific study of impacts of free caesarean measures Mali | Office of the Auditor General Budget Monitoring Group (National Council of Civil Society) | March-May 2014 | 00075521 | 14000 |

Evaluation Plan 2014-2017

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Realize the final evaluation of the Strategic Plan 2014-2017 | Y | Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Mali AWP Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Mali CO | WCARO | N | MPFFE, NGOs partners | July-August 2017 | 30 000 |  |  |
| Conduct an assessment to internal mid-term and final external evaluation of the Programme "Support to women / girls affected by conflict and participation of women in the process of consolidation of peace" |  | Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Mali AWP Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Mali CO | WCARO | N | MPFFE, NGOs partners Netherland Cooperation in Mali | March 2014 June-July 2015 | 15 000 00084608 30 000 00084608 |  |  |
| Realize Project final evaluation “Support for Rural Women’s Economic Empowerment in the Context of Food Insecurity and Climate Change in Mali “ | N | Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Mali AWP Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Mali CO | WCARO | Y | MPFFE, NGOs partners Sweden, FAO | June 2015 | 5 000 00085796 |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Final Project Evaluation "Belgian Fund for Food Security" | N | Operational effectiveness and efficiency results output cluster 2, Output 2.3 | Operational effectiveness and efficiency results output cluster 2, Output 2.3 | Mali CO | WCARO | Y | MPFFE, NGOs partners Belgium , | 2016 | Memory (FBSA) |  |  |

Please fill out a separate row for each evaluation.