MONITORING, EVALUATION AND RESEARCH PLAN 2020

UN Women Haïti Country Office

- Monitoring and Research Plan (MERP) 2020

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Cross‐cutting |  |  |  |  |
| RBM and program monitoring training for new staff and implementing partners | Internal exercise | Monthly | Core Staff time | 1,00 USD |
| Timely Month-end closures and according to corporate standards, including liquidation of partners' advances | Internal exercise with LACRO | Monthly | Core Staff time | 1,00 USD |
| Formulation and validation of a high quality 2021 UN Women Haiti Country Office Annual Work Plan - Timely and high-quality reporting (quarterly & annual) in RMS and submission of donor reports | Internal exercise | Monthly | Core | 17,899 USD |
| Quarterly progress program and operations report | M&E, Internal exercise in RMS | Quarterly | Core Staff time | 1.00 USD |
| Indicators Tracking Tool to monitor AWP implementation | M&E, Internal exercise with LACRO | Annually | Core Staff time | 1.00 USD |
| Review of data collection for SN 2018-2021-DRF/OEEF and AWP 2020 indicators | M&E, Haiti Country Office | June 2020 | Core Staff time | 1.00 USD |
| Update DAMS report matrix to ensure narrative and financial reports are submitted to donors on time | M&E | Quarterly | Core Staff time | 1.00 USD |
| Update Profil’s project on DAMS | M&E | Quarterly | Core Staff time | 1.00 USD |
| Update Profil’s proposal on LEADS | M&E | Quarterly | Core Staff time | 1.00 USD |
| Indicators Tracking Tool to monitor UNDAF AWP implementation | M&E, Internal exercise | Quaterly | Core Staff time | 1.00 USD |
| Regular AWP-UNDAP monitoring and reporting: quarterly and annual | M&E, Internal exercise | 2020 Quarterly reports: Q1 - Q4; Annual report in december 2020 | Core Staff time | 1.00 USD |
| Review of data collection for UNDAF-AWP indicators | M&E, Internal exercise | June 2020 | Core Staff time | 1.00 USD |
| Program |  |  |  |  |
| SP Outcome 2: Women lead, participate in and benefit equally from governance systems |  |  |  |  |
| Periodic monitoring of the "Women's political participation and leadership program" | Program Management Team, Ministry of Women Affairs and Women's Rights (MCFDF in French), Ministry of Interior and Local Authorities (MICT in French), Ministry of Justice and Public Security (MJSP in French), Civil Society Organizations (CSOs), Women’s organizations | Quarterly | Core Staff time | 1.00 USD |
| SP Outcome 3: Haïtian Women have income security, decent work and economic autonomy |  |  |  |  |
| Periodic monitoring of the "Women Economic Empowerment program" | Program Management Team, Ministry of Public Works, Telecommunication and Energy (MTPTC), Ministry of Environment (MdE in French), Ministry of Trade and Industry (MCI in French), Ministry of Agriculture and Natural Resources (MARNDR in French), Green Climate Funds (GCF) Government of Norwegian | Quarterly | Core Staff time | 1.00 USD |
| SP Outcome 4: All women and girls live a life free from all forms of violence |  |  |  |  |
| Periodic monitoring of the "Spotlight program" | Program Management Team, Ministry of Women Affairs and Women's Rights (MCFDF in French), Ministry of Interior and Local Authorities (MICT in French), Ministry of Justice and Public Security (MJSP in French), Civil Society Organizations (CSOs), Women’s organizations | Quarterly | Core Staff time | 1.00 USD |
| RESEARCH |  |  |  |  |
| Research in which the office participates |  |  |  |  |
| Study on the Spotlight prevention strategy | External exercise MCFDF, CSOs, Women organizations, NGOs | 2020 | Non-core Spotlight Pending This will be done by RCO and Spotlight Secretariat with UNW’s technical support | 1.00 USD |

- Evaluation Plan 2020

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/Relevant flagship program | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by Haïti Country Office |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation of the “Reducing violence against women during electoral processes” program | Y | UNDAF Outcome 3 UNW Impact 2 SP Outcome 2 SN Outcome 2.1 | SN Output 1.1.1 | Haiti Country Office | LAC/Haiti | N | March October 2020 | 20,000.00 USD Non-Core Canada | Pending | n/a |
| Internal Mid-term review of WEE, FADEKA Project | N | UNW Impact 2 SP Outcome 3 SN Outcome 2.1 | SN Outputs 2.1.2, 2.1.3 | Haiti Country Office | LAC/Haiti | N | August October 2020 | 15,000.00 USD Non-core Norway | Pending | n/a |
| Midterm review of AWP 2020 | N | UNW Impact 1, 2, 3 and 4 SP Outcomes 2, 3, 4 and 5 SN Outcome 1.1, 1.2, 2.1, 3.1 | SN Outputs 1.1.1, 1.2.1, 1.2.2, 1.2.3, 2.1.2, 2.1.3, 3.1.1, 3.1.2, 3.1.3, 3.1.4, 3.1.5, 3.1.6. 3.1.7, 3.1.8, 3.1.9, 3.1.10, 3.1.11 | Haiti Country Office | LAC/Haiti | N | July 2020 | 1,00 USD | Pending | Non-Core ou core à identifier |
| Haiti's Strategic Note SN 2018-2021 mid-term review | Y | UNW Impact 1, 2, 3 and 4 SP Outcomes 2, 3, 4 and 5 SN Outcome 1.1, 1.2, 2.1, 3.1 | SN Outputs 1.1.1, 1.2.1, 1.2.2, 1.2.3, 2.1.2, 2.1.3, 3.1.1, 3.1.2, 3.1.3, 3.1.4, 3.1.5, 3.1.6. 3.1.7, 3.1.8, 3.1.9, 3.1.10, 3.1.11 | Haiti Country Office | LAC/Haiti | N | September 2020 | 1,00 USD | Pending | Non-Core ou core à identifier |
| EU project Baseline | Y | UNW Impact 1, SP Outcomes 2, SN Outcome 1.2 | SN Outputs 1.2.3, | Haiti Country Office | LAC/Haiti | N | April 2020 | 4.440.00 USD Non-core UE | Pending | n/a |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of UNTFHS Program | N | UNDAF Outcome 4 IMPACT 4 SP Outcome 5 SN Outcome 4.1 | Output 4.1.1 4.1.2 | UNDP | Haiti | Y UNDP UNESCO UNWOMEN | Janvier March 2020 | 1,00 USD Non-core UNTFHS | Ongoing | This will be done by UNDP with UNW’s technical support |
| Final evaluation of Peace Building Fund Program | N | UNDAF Outcome 4 IMPACT 4 SP Outcome 5 SN Outcome 4.2 | Output 4.2.1 4.2.2 4.2.3 4.2.4 | UNDP | Haiti | Y UNDP IOM UNWOMEN | January 2020 | 1,00 USD Non-core PBF | Ongoing | This will be done by UNDP with UNW’s technical support |
| Spotlight Midterm evaluation | Y | UNW Impact 3 SP Outcomes 4 SN Outcome 3.1 | SN Outputs 3.1.1, 3.1.2, 3.1.3, 3.1.4, 3.1.5, 3.1.6. 3.1.7, 3.1.8, 3.1.9, 3.1.10, 3.1.11. | Haiti Country Office | LAC/Haiti | N | February 2020 | 1,00 USD Non-core Spotlight | Pending | This will be done by RCO and Spotlight Secretariat with UNW’s technical support |

## Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Partnership evaluation in the field of Women Political Participation | Relevance of the subject Knowledge gap Demands for accountability from stakeholders | High | Formulation of new Strategic partnership for CO in support of Strategic Note 2018-2021, learn and to generate accountability |
| Final Evaluation of the “Reducing violence against women during electoral processes” program | Relevance of the subject Significant investment: more 1M | High | Support the formulation of new SN, learn and to generate accountability |
| Midterm review of AWP 2019 | Relevance of the subject Knowledge gap Alignment with UN Women strategic note mid-term review Demands for accountability from stakeholders | TBD | Identification and understanding of key success factors and bottlenecks Generate recommendations for performance improvement |
| Haiti's Strategic Note SN 2018-2021 mid-term review | Relevance of the subject Knowledge gap Alignment with UN Women strategic note mid-term review Demands for accountability from stakeholders | TBD | Identification and understanding of key success factors and bottlenecks Generate recommendations for performance improvement |
| Spotlight Midterm evaluation | Relevance of the subject Knowledge gap Alignment with UN Women strategic note mid-term review Demands for accountability from stakeholders | TBD | Identification and understanding of key success factors and bottlenecks Generate recommendations for performance improvement |

Monitoring Plan 2020

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| All | Reports: UN Women Haïti Country Office Quarterly and Annual Report; Project Donor Reports (See Donor Report Matrix, which includes project details, reporting requirements and due dates) | All Program Manager | UN Women Haïti Country Office | January – December 2020 | Core Staff time | 1.00 USD |
| All | Baseline study and M&E toolbox for each program under Impacts Areas 1, 2, 3 & 4 | Program Manager | UN Women Haïti Country Office Partners listed under Impacts Areas 1, 2, 3 & 4 | January – December 2020 | Non-core | … USD |
| SN Impact area 2 | Quarterly monitoring of activities of the program "Reducing violence against women during electoral processes" | Project Manager | UN Women Haïti Country Office: internal staff | March 2020 June 2020 September 2020 December 2020 | Core Staff time | 1.00 USD |
| SN Impact area 2 | Annual report of the program "Reducing violence against women during electoral processes" | Project Manager | UN Women Haïti Country Office Provisional Electoral Council (CEP in French), NGO/ CSO | September 2020 | Core Staff time | 1.00 USD |
| SN Impact area 3 | Quarterly monitoring of activities of the program "WEE Program" | Project Manager | UN Women Haïti Country Office: internal staff | March 2020 June 2020 September 2020 Décember 2020 | Core Staff time | 1.00 USD |

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| SN Impact area 3 | Annual report of the program "WEE Program" | Project Manager | UN Women Haïti Country Office: internal staff Ministry of Women Affairs and Women's Rights (MCFDF in French), Implementing partners, Women’s organizations | Décember 2020 | Core Staff time | 1.00 USD |
| SN Impact area 4 | Quarterly monitoring of activities of the program "Spotlight Program" | Project Manager | UN Women Haïti Country Office: internal staff | March 2020 June 2020 Septembre 2020 Décembre 2020 | Core Staff time | 1.00 USD |
| SN Impact area 4 | Annual report of the program "Spotlight Program" | Project Manager | UN Women Haïti Country Office: internal staff Ministry of Women Affairs and Women's Rights (MCFDF in French), Implementing partners, CSO’s, Women’s organizations | Décembre 2020 | Core Staff time | 1.00 USD |

- Knowledge management

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Systematization of the Project "Reducing Violence Against Women in Electoral Context" | UN Women | TBC | Core Staff time | 1.00 USD |
| KM strategy | UN Women | TBC | Core Staff time | 1.00 USD |
| Development and dissemination of knowledge products on thematic areas and issues | UN Women | TBC | Core Staff time | 1.00 USD |

- Innovation

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Innovation strategy | UN Women | TBC | Core Staff time | 1.00 USD |

Outcomes contributing to the SDGs as per the Strategic Plan