MONITORING, EVALUATION AND RESEARCH PLAN

Vietnam Country Office (2012-2013) [revised May 2013]

The UN Women Viet Nam Office continues to strengthen and sharpen its monitoring and evaluation activities to ensure the effectiveness of the UN Women technical and financial support to national gender priorities.

In the Delivering as One Approach, UN Women chairs the Gender Joint Programme Group which is an internal mechanism of the United Nations to ensure the effective implementation and monitoring of the gender-related outcome of the One Plan 2012-2016. Gender JPG ensures the coordination of the implementation of specific One Plan Outputs 2.4.3 and 2.4.4 on gender, including joint programming, with particular emphasis on maximizing synergies, coordinating and where possible jointly undertaking implementation, monitoring and evaluation activities.

As chair of the Gender JPG, UN Women is responsible for monitoring, reviewing and reporting on progress made in the implementation of the joint Annual Work Plan of the Gender JPG while the management and financial accountability, including monitoring and reporting, for specific projects/programmes remains the responsibility of individual UN system agencies and their National Implementing Partners. It is noted that the monitoring and reporting system for the One Plan will not undermine this basic accountability.

Since 2011, UN Women has been a member of the UNCT Monitoring and Evaluation (M & E) Working Group of the UNCT which is formed by all ME focal points from UN agencies. The ME focal point of UN Women also serves as Gender Focal Point of the MEWG. Through participation in the MEWG and chairing the Gender JPG, UN Women aims to integrate a gender equality perspective to the monitoring and evaluation of the whole plan. It provides UN Women an opportunity to advocate for more joint and peer monitoring and evaluations in the UNCT system on different dimensions of gender equality and women’s human rights, as is consistent with the UN Women SP, as well as with the Paris Declaration and Ha Noi Declaration on ODA principles.

The performance monitoring activities will be implemented through:

- Maximum use of exiting tools such as work plans, tracking delivery rates through ATLAS, regular meetings with partners on project implementation, and field monitoring reports as well as  progress report from the implementing partners to assess programme process (achievements of result and delivery rate);

- Actively participating in the preparation of mid-term evaluation of the One Plan 2012-2016 to be conducted in 2013  led by UNCT MEWG.

- Allocating budget for regular monitoring of project activities as UN rules, at least 5% of the project budget;

- Ensuring the development of a joint results framework for the Gender JPG in collaboration with participation UN agencies;

- Leading at least one joint monitoring mission every year for UN Gender JPG focusing on UN Women or other UN agencies that contributed to the achievement of a specific gender outcome and outputs of the One Plan 2012-2016;

- Ensuring the time bound indicators for project/programme are developed together with partners during programme formulation. Reviewing these indicators regularly and corrective action taken to address low performance or other problems (this will be documented through meetings with partners or internal programme staff meeting);

- Analyzing the expenditure regularly by both finance and programme staff and action taken to address the significant over/under expenditure;

- Meeting periodically with partners, beneficiaries and key stakeholders to discuss progress and corrective action taken if necessary. This will be done through monitoring system, regular meeting at partners’ office to discuss on project activities;

- JPG mechanism: organizing midyear programme review and annual review with project partners and other key stakeholders working on gender equality and gender mainstreaming;

- Visiting the project site and documenting findings in the mission reports by both UN Women and its partners to ensure the national ownership of the follow up actions.

- Progress of AWP implementation regularly discussed during the staff and management meetings; and

- Participating the joint-missions organized by other UN agencies to track gender progress in project implementation conducted by other UN agencies of UNCT.

- Conducting evaluability assessments for two Detailed Project Outlines of two five year programmes under the One Plan framework: Strengthen capacity for implementation, monitoring and evaluation of the National Strategy and the National Programme on Gender Equality and Strengthening women’s capacity in disaster risk reduction to cope with climate change. The purpose of the evaluability assessment is to identify if the UN Women interventions are in a condition to be evaluated and whether the evaluation planned for 2016 for these programme is feasible and likely to provide useful information.

There will be the following two types of evaluations under the monitoring and evaluation plan

UN Women Project/Programme evaluations to assess the efficiency and effectiveness of an intervention or set of interventions in achieving the intended results. They also assess the relevance and sustainability of outputs as contributions to medium-term and longer-term outcomes. A project/ programme evaluation can be invaluable for managing for results, and serves to reinforce the accountability of project/ programme managers. Additionally, project/programme evaluations provide a basis for the evaluation of outcomes and programmes, and for distilling lessons from experience for learning and sharing knowledge. The finding and recommendations from UN Women’s evaluations will be shared through the JPG mechanism to ensure dissemination of the lesson leant within the UNCT, Government and CSO.

In addition to the above, UN Women will participate in joint evaluations with UN partners in the context of the One Plan 2012-2016 and/ or ONE UN programmes. The reviews may be conducted internally with external support, and will follow rapid assessment techniques.

# Annex 1: 2012-2013 MONITORING, EVALUATION AND RESEARCH (MER) PLAN

Note: As per the Guidance “How to develop UN WOMEN Monitoring, Evaluation and Research (MER) Plans”, MER Plans are developed at country, sub-regional and regional level. The development of MER Plan needs to be closely linked with the development of Annual Work Plans.

NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities.

| Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome |  | Relevant Country/ SRO AWP Output |  |  |  |  |  | Office to manage the MER activity |  |  | Region, Sub Region or Country |  |  | Joint MER activity (Y/ N, indicate partners) |  |  |  |  |  | Key Stakeholders |  |  |  | Planned Dates (start-completion) |  |  |  |  |  |  |  | Budget (US$) for MER activity/ Sources of Funding |  |  |  |  | Status (pending - initiated – ongoing - completed) |  |  | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2012 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Annual JPG meeting | Y | 2.4 OP Outcome |  |  |  |  | MRF 1 |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  |  |  |  | Y |  |  | Government, UN agencies donors, bilateral and CSOs |  |  |  |  |  | Feb 2012 |  |  |  |  |  |  | USD $ 6,000 USD from core |  |  |  | Completed |  | Gender as the cross cutting issue of the OP |
| Joint mission with other UN agencies to UN Women project site | Y | 2.4 OP Outcome |  |  |  |  | MFR 1 |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  |  |  |  | UN Women and UNFPA |  |  | Project implementing partners |  |  |  |  |  | December 2012 |  |  |  |  |  |  | USD 3,000 from OPF and contribution from other UN agencies |  |  |  | Completed |  |  |
| Field missions/report | Y | OP Outcomes 1.2, 1.3, 2.4 and 3.1 |  |  |  |  | AWP Outputs 1.1, 2.1, 2.2, 3.1 and 4.1 |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  |  |  |  | Y |  |  | Government Partners, mass organistions and CSOs |  |  |  |  |  | From March to December 2013 |  |  |  |  |  |  | USD $ 35,000 |  |  |  | completed |  | Gender specific programme |
| Partner visits (minutes) | Y | OP Outcomes 1.2, 1.3, 2.4 and 3.1 |  |  |  |  | AWP Outputs 1.1, 2.1, 2.2, 3.1 and 4.1 |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  |  |  |  | Y |  |  | Government Partners mass organistions and CSOs |  |  |  |  |  | From March to December 2012 |  |  |  |  |  |  | No-cost |  |  |  | Completed |  |  |
| JPG working groups’ meetings (report) | Y | OP Outcome 2.4 |  |  |  |  | AWP Outputs 1.1, 2.1, 2.2, 3.1, 3.2 and 4.1 |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  |  |  |  | Y |  |  | UN agencies and Government partners mass organistions and CSOs |  |  |  |  |  | From January to December 2013 |  |  |  |  |  |  | No –cost |  |  |  | Completed |  |  |
| AWP Baseline monitoring | Y | OP Outcomes 1.2, 1.3, 2.4 and 3.1 |  |  |  |  | AWP Outputs 1.1, 2.1, 2.2, 3.1, 3.2 and 4.1 |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  |  |  |  | N |  |  | Government Partners, mass organistions and CSOs |  |  |  |  |  | From March to December 2012 |  |  |  |  |  |  | No-cost |  |  |  | Completed |  |  |
| Regular meetings of UNCT ME Working group | Y | All OP outcomes |  |  |  |  | AWP Outputs 1.1, 2.1, 2.2, 3.1 and 4.1 |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  |  |  |  | Y (Joint working of all UN agencies led by UN RCO and UNFPA) |  |  |  |  |  |  |  |  | No-Cost |  |  |  |  |  |  | Completed |  |  |  |  |  |
| Participatory review sessions (at project level, twice per year) | Y | OP Outcomes 1.2, 1.3, 2.4 and 3.1 |  |  |  |  | AWP Outputs 1.1, 2.1, 2.2, 3.1 and 4.1 |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  |  |  |  | Y |  |  | Government Partners mass organistions and CSOs |  |  |  |  |  | July and January 2013 |  |  |  |  |  |  | Cost included in the LOAs and managed by the partners |  |  |  | On-going |  |  |  |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors, etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| UNTF Project in Vietnam Evaluation of the project “Promoting Multi-stakeholder Community-based Approach to Address the Twin Pandemics of Trafficking in Women and Girls and HIV/AIDS” implemented by Institute for Reproductive Family Health (RaFH), Vietnam Women’s Union, Lang Son Women’s Union, and Lao Cai Women’s Union | Y | UN Women SP DRF Goal 3 |  |  |  |  | East and South East Asia AWP |  |  |  |  | Evaluation is to be conducted by external evaluator under guidance of CO, ESEA SRO and UNTF HQ | SRO |  |  |  |  |  |  |  | N |  |  | External Evaluator |  |  |  |  |  | Q4 2011 – Q1 2012. |  |  |  | US$ 16,800 UNTF Grantee |  |  |  |  |  |  | Completed in May 2012 | *As per UNTF Policy, since cycle 13 the Grantees are requester to sent a side of 10% of total grant for Monitoring and external independent evaluative |  |
| UN-Government JPGE | Y | OP (2006-2011) Outcome 1.9 |  |  |  |  | AWP Output 4.1 |  |  |  |  | UNFPA as the State Management Agency for JPGE – UN Women as the participating agency |  |  |  |  |  |  |  |  | Y |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | No cost from UN Women (35,000 USD managed directly by UNFPA as the UN Management Agency for the JPGE) |  |  |  | Completed and shared with the stakeholder in March 2012 |  |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of UN Women’s approach on engaging men and boys in gender equality and violence against women | Y | OP Outcome 2.4 |  |  |  |  |  | AWP outputs 3.2 |  | Viet Nam |  |  |  |  | Viet Nam |  |  |  |  | N |  |  |  |  | Ho Chi Minh Youth Union |  |  |  | May - September 2012 |  |  |  |  |  |  | USD $ 15,000 |  |  | 31 December 2012 |  |  |  |  |
| Masculinity study (joint study UNFPA and UN Women) | Y | OP Outcome 2.4 |  |  |  |  | AWP output 3.1 |  | Viet Nam Country Office |  |  |  |  |  |  |  |  |  |  |  | Y (Joint study with UNFPA Viet Nam) |  |  | N |  |  |  |  | August 2011 to May 2012 |  |  |  |  |  |  |  | 15,000 USD |  |  |  | Completed |  |  |
| Triangulation report of HIV Intimate Partner Transmission (IPT) (joint study between UN AIDS and UN Women) | Y | OP Outcome 2.4 |  |  |  |  | AWP Output 4.1 |  | Viet Nam Country office |  |  |  |  |  | Viet Nam |  |  |  |  |  | Y (Joint study with UN AIDS Viet Nam) |  |  | N |  |  |  |  | September 2011 to May 2012 |  |  |  |  |  |  |  | 30,000 from PAF funded by UN AIDS |  |  |  | Completed |  |  |
| Study on linkages between HIV and domestic violence (joint study between UN Women and UN AIDS) | Y | OP Outcome 2.4 |  |  |  |  | AWP Output 4.1 |  | Viet Nam Country office |  |  |  |  |  | Viet Nam |  |  |  |  |  | Y (Joint study with UN AIDS Viet Nam) |  |  | N |  |  |  |  | September 2011 to May 2012 |  |  |  |  |  |  |  | 30,000 USD from PAF (funded by UN AIDS) |  |  |  | Completed |  |  |
| Costing study on the impact of DV to households | Y | OP Outcome 2.4 |  |  |  |  | AWP Output 3.1 |  | Viet Nam Country Office |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam Academy of Social Science – Institute of Gender and Family Study |  |  | Viet Nam Academy of Social Science – Institute of Gender and Family Study |  |  |  |  | October 2011 to October 2012 |  |  |  |  |  |  |  | 110.000 USD from core and AusAid (SRO), in which 70,000 USD will be done in 2012) |  |  |  | Completed |  |  |
| Capacity assessment on the implementation of the National Strategy and the National programme on gender equality | Y | OP Outcome 2.4 |  |  |  |  | AWP 4.1 |  | Viet Nam Country Office |  |  |  |  |  | Viet Nam |  |  |  |  |  |  |  |  | Gender Equality Department, Ministry of Labour, Invalids and Social Affairs |  |  |  |  | October 2012 to December 2013 |  |  |  |  |  |  |  | 15,000 USD from core |  |  |  | Completed |  |  |
| Situation analysis of women migrant workers | Y | OP Outcome 1.2 |  |  |  |  | AWP Output 2.1 |  | Viet Nam Country Office |  |  |  |  |  | Viet Nam |  |  |  |  |  | Department of Oversea Labour, Ministry of Labour, Invalids and Social Affairs. UN Women have consulted technically with ILO, IOM on the study |  |  | Department of Oversea Labour, Ministry of Labour, Invalids and Social Affairs |  |  |  |  | January to May 2012 |  |  |  |  |  |  |  | 15,000 USD from the regional programme |  |  |  | Completed |  |  |
| Knowledge, Attitude and Practice (KAP) on Disaster Risk Reduction in Phu Yen province | Y | OP Outcome 3.1 |  |  |  |  | AWP Output 1.1 |  | Viet Nam Country office |  |  |  |  |  | Viet Nam Country office |  |  |  |  |  | Viet Nam Women’s Union, UNDP |  |  | Viet Nam Women’s Union |  |  |  |  | June 2012 |  |  |  |  |  |  |  | 6,000 USD |  |  |  | Completed | This will be done two time per year at the project site to measure the changes |  |
| Macro Economic Study | Y | OP Outcome 2.1 |  |  |  |  | AWP Output 2.1 |  | Viet Nam Country office |  |  |  |  |  | Viet Nam Country office |  |  |  |  |  |  |  |  | Hanoi Economics University |  |  |  |  | Jan 2011 to May 2012 |  |  |  |  |  |  |  | USD 10,000 USD from core for the launching of the report |  |  |  | Completed |  |  |
| Retirement age paper from CEDAW perspectives | Y | OP Outcome 3.1 |  |  |  |  | AWP Output 4.1 |  | Viet Nam Country office |  |  |  |  |  | Viet Nam Country office |  |  |  |  |  | UNDP, UNFPA and ILO |  |  |  |  |  |  |  | December 2011 to March 2012 |  |  |  |  |  |  |  | No cost for 2012 as all payment completed in 2011 |  |  |  | Completed | (this is UN joint position paper and led by UN Women) |  |
| POLICY BRIEF: “Legal Framework on Land Rights for Women in Compliance with Viet Nam Commitments to Human Rights/Women’s Rights” | Y | OP Outcome 3.1 |  |  |  | AWP Output 4.1 |  |  |  |  | Viet Nam Country office |  |  | Viet Nam Country office |  |  |  |  | UNDP, UN Women |  |  |  |  |  |  |  |  |  |  |  | August 2012 – Oct. 2013 |  |  |  | USD 10,000 (fund from CEDAW program) |  |  |  |  |  | Completed | (this is UN joint position paper and led by UN Women) |  |
| Research on “Assessment of the realities that women face when dealing with the justice system, focusing on the following categories of women: victims of gender-based violence, women in conflict with the law and women as actors and professionals in the justice system in Vietnam | Y | OP Outcome 3.1 |  |  |  | AWP Output 4.1 |  |  |  |  | Viet Nam Country office |  |  | Viet Nam Country office |  |  |  |  | UNODC, UN WOMEN, UNFPA |  |  |  |  |  |  |  |  |  |  |  | Nov. – Dec. 2012 |  |  |  | USD -5,000 (Fund from IB) |  |  |  |  |  | On-going | (this is UN joint position paper and led by UNODC ) |  |
| Policy brief on gender mainstreaming in the disaster risk reduction and climate change adaption policies | Y | OP Outcome 1.3 |  |  |  | AWP Output 4.1 |  |  |  |  | Viet Nam Country office |  |  | Viet Nam Country office |  |  |  |  | UNDP, Oxfam International in Viet Nam |  |  |  |  | Viet Nam Women’s Union |  |  |  |  |  |  | January 2012 to March 2012 |  |  |  | 700 USD for printing the policy brief for the International Women’s Day from the One Plan Fund. |  |  |  |  |  | Completed |  |  |
| 2013 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome |  | Relevant Country/ SRO AWP Output |  |  |  |  |  | Office to manage the MER activity |  |  | Region, Sub Region or Country |  |  |  |  | Joint MER activity (Y/ N, indicate partners) |  |  |  | Key Stakeholders |  |  |  |  | Planned Dates (start-completion) |  |  |  |  | Budget (US$) for MER activity/ Sources of Funding |  |  |  |  |  |  |  | Status (pending - initiated – ongoing - completed) |  | Remarks |  |
| Midterm JPG Review meeting | Y | 2.4 One Plan (OP – UNDAF) Outcome |  | MRF 1 |  |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  |  |  | Y |  |  |  | Government, UN agencies bilaterals and CSOs |  |  |  |  | June 2013 |  |  |  |  | USD $ 6,000 USD from core |  |  |  |  |  |  |  | On –going |  | Gender as the cross cutting issue of the OP |  |
| Annual JPG meeting | Y | 2.4 OP Outcome |  |  | MFR 1 |  |  |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  | Y |  |  |  | Government, UN agencies bilaterals and CSOs |  |  |  |  | December 2013 |  |  |  |  | USD $ 6,000 USD from core |  |  |  |  |  |  |  | On -going |  | Gender as the cross cutting issue of the OP |  |
| Field missions/report | Y | OP Outcomes 1.2, 1.3, 2.4 and 3.1 | AWP Outputs 1.1, 2.1, 2.2, 3.1 and 4.1 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam | Y |  |  |  |  |  | Government Partners mass organistions and CSOs |  |  |  |  | From March to December 2013 |  |  |  |  | USD $ 35,000 from the Regional programme fund (CEDAW and migration), Core and the One Plan Fund |  |  |  |  |  | On-going |  |  |  | Gender specific programme |  |
| Partner visits (minutes) | Y | OP Outcomes 1.2, 1.3, 2.4 and 3.1 | AWP Outputs 1.1, 2.1, 2.2, 3.1 and 4.1 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam | Y |  |  |  |  |  | Government Partners mass organistions and CSOs |  |  |  |  | From March to December 2013 |  |  |  |  | No-cost |  |  |  |  |  | On-going |  |  |  |  |  |
| JPG working groups’ meetings (report) | Y | OP Outcome 2.4 | AWP Outputs 1.1, 2.1, 2.2, 3.1, 3.2 and 4.1 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam | Y |  |  |  |  |  | UN agencies and Government partners |  |  |  |  | From January to December 2013 |  |  |  |  | No –cost |  |  |  |  |  | On-going |  |  |  |  |  |
| UN Women’s quarterly report | Y | OP Outcomes 1.2, 1.3, 2.4 and 3.1 | AWP Outputs 1.1, 2.1, 2.2, 3.1, 3.2 and 4.1 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam | N |  |  |  |  |  | Government Partners mass organistions and CSOs |  |  |  |  | From March to December 2013 |  |  |  |  | No-cost |  |  |  |  |  | On-going |  |  |  |  |  |
| AWP JPG One Plan Data based | Y | OP Outcomes 2.4 | AWP Output 2.4.3 and 2.4.4 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam | UNFPA |  |  |  |  |  |  |  |  |  |  | January 2012- Dec 2013 |  |  |  |  | No-cost |  |  |  |  |  | On-going |  |  |  |  |  |
| Joint mission with other UN agencies to UN Women project site | Y | 2.4 OP Outcome | MFR 1 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam | UNFPA, ILO, UNDP, UNODC, IMO |  |  |  |  |  |  |  |  |  |  | July and August 2013? |  |  |  |  | USD 2,000 from core and contribution from other UN agencies |  |  |  |  |  |  |  |  |  |  |  |
| Regular meetings of UNCT ME Working group | Y | All OP outcomes | AWP Outputs 1.1, 2.1, 2.2, 3.1 and 4.1 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam | Y (Joint working of all UN agencies led by UN RCO) |  |  |  |  |  |  |  |  |  |  | January to December 2013 |  |  |  |  | No-Cost |  |  |  |  |  | On –going |  |  |  |  |  |
| FGE baseline survey | Y | OP Outcomes 2.1 | AWP Outputs 2.1 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam | Y (LIGHT) |  |  |  |  |  | NGOs |  |  |  |  | May – June 2013 |  |  |  |  | TBA |  |  |  |  |  | On going |  |  |  |  |  |
| Participatory review sessions (at project level, twice per year) | Y | OP Outcomes 1.2, 1.3, 2.4 and 3.1 | AWP Outputs 1.1, 2.1, 2.2, 3.1 and 4.1 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam | Y |  |  |  |  |  | Government Partners mass organistions and CSOs |  |  |  |  | July and January 2013 |  |  |  |  | Cost included in the LOAs and managed by the partners, from core and OPF |  |  |  |  |  | On-going |  |  |  |  |  |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Example: Evaluation of the E-Village Project (project) | Example: Y | Example: Goal 2, Outcome 2.3 | Example: Jordan AWP Output 2.1 |  |  |  |  |  | Example: Jordan CO |  |  |  |  |  | Example: Jordan |  | Example: N |  |  |  |  |  | Example: Ministry of Planning, Ministry of ICT, JOHUD |  |  |  |  | Example: May July 2011 |  |  |  |  | Example: US$60,000, core funds |  |  |  |  | Example: Ongoing |  |  |  |  |  |
| Evaluability asessement of the five year programme on strengthening women’s capacity in disaster risk reduction to cope with climate change | Y | OP Outcome 3.1 | Viet Nam AWP 1.1 |  |  |  |  |  | Viet Nam CO |  |  |  |  |  | Viet Nam | N |  |  |  |  |  | Viet Nam Women's Union |  |  |  |  |  | July-December 2013 |  |  |  |  |  | 15,000 |  |  |  | Initiated |  |  |  |  |  |
| Evaluability assessment of five year programme: Strengthen capacity for implementation, monitoring and evaluation of the National Strategy and the National Programme on Gender Equality | Y | OP Outcomes 2.4, 1.2 and 3.1 | Viet Nam AWP 2.1, 4.1 and 4.2 |  |  |  |  |  | Viet Nam CO |  |  |  |  |  | Viet Nam | N |  |  |  |  |  | MOLISA |  |  |  |  |  | August – October |  |  |  |  |  | 10,000 |  |  |  | Initiated |  |  |  |  |  |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors etc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Support provided to three NGOs women’s rights networks to better coordinate and promote gender equality in Viet Nam | Y | One Plan 2012-2016 outcome 2.4.3 | Annual Work Plan 2012, outcome 4 |  |  |  |  |  | Viet Nam |  |  |  |  |  | Viet Nam |  | N |  |  |  |  |  | Gencomnet, DOVIPNET and NEW , |  |  |  |  | September – December 2013 |  |  |  |  | Cost included in the PCA and managed by the partners, from core fund |  |  |  |  | On-going |  |  |  | Support provided to three NGOs women’s rights networks to better coordinate and promote gender equality in Viet Nam |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Research on “Assessment of the realities that women face when dealing with the justice system, focusing on the following categories of women: victims of gender-based violence, women in conflict with the law and women as actors and professionals in the justice system in Vietnam | Y | OP Outcome 3.1 |  | AWP Output 4.1 |  |  |  |  |  | Viet Nam Country office |  |  | Viet Nam Country office |  |  | UNODC, UN WOMEN, UNFPA |  |  |  |  |  |  |  |  |  | Nov 2012 – June 2013 |  |  |  |  |  |  |  | USD -5,000 (Fund from IB) |  |  |  |  | On-going |  |  | (this is UN joint position paper and led by UNODC ) |  |
| Research on how women access to land right from CEDAW perspectives | Y | OP Outcome 3.1 |  | AWP Output 4.1 |  |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  | Y |  |  |  |  |  | UNDP Viet Nam |  |  |  | July – December 2013 |  |  |  |  |  |  |  | 10,000 USD from the CEDAW regional programme (phase II) |  |  |  |  | Initiated |  |  |  |  |
| Three surveys: Knowledge, Attitude and Practice (KAP) on Disaster Risk Reduction in Binh Dinh, Hue and Quang Binh provinces | Y | OP Outcome 1.3 |  | AWP Output 1.1 |  |  |  |  |  | Viet Nam Country office |  |  | Viet Nam Country office |  |  | Viet Nam Women’s Union, UNDP |  |  |  |  |  | Viet Nam Women’s Union |  |  |  | June 2012 and July 2013 and December 2013 |  |  |  |  |  |  |  | 12,000 USD |  |  |  |  | On-going |  |  | This will be done two time per year at the project site to measure the changes |  |
| Research on the situation of monitoring the applications of recruiting agencies towards protecting women migrant workers in Viet Nam | Y | OP Outcomes 2.1 |  | AWP Outputs 2.1 |  |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  | Y (Government) |  |  |  |  |  | Department of Overseas Labour, MOLISA |  |  |  | June –August 2013 |  |  |  |  |  |  |  | USD 5,500 |  |  |  |  | Initiated |  |  |  |  |
| Multi-Country Study on the Policing and Prosecution of Sexual Violence in Asia | N | Outcomes 2.4 and 3.1 |  | AWP Output 3.1 |  |  |  |  |  | Viet Nam |  |  | Viet Nam |  |  | Y (joint UN and Gov), with the coordinaiton and leading from Gender and Goverence JPGs |  |  |  |  |  | Ministry of Justice, Ministry of Public Security, and Institute for Gender and Family Studies/Vietnam Academy of Social Science |  |  |  | June – September 2013 |  |  |  |  |  |  |  | Possible contribution needed from UN Women (estimated 10,000 USD) |  |  |  |  | Tentative |  |  |  |  |

# Annex 2: Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Evaluability assessment of the five year programme on strengthening women’s capacity in disaster risk reduction to cope with climate change | - Scope of the project - Specific target group - Time of project implementation - Partners is committed. | - The potential evaluability could be high as the project is an expansion of a pilot project that was successfully running for two years. - Clear indicators - Small scope of the project | The purpose of the evaluability assessment is to identify if the UN Women interventions are in a condition to be evaluated and whether the evaluation planned for 2016 for these programme is feasible and likely to provide useful information. |
| Evaluability assessment of five year programme: Strengthen capacity for implementation, monitoring and evaluation of the National Strategy and the National Programme on Gender Equality |  |  |  |

This evaluation is the same evaluation as on the regional MER plan. The grantee will conduct the evaluation with support from the SRO and the CO.