## Sheet1
TEMPLATE – MONITORING, EVALUATION AND RESEARCH PLAN 2022-2025
Name of Office: East and Souther Africa Regional Office
Monitoring and Research Plan 2022-2025
Activity | UN Women SP Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget |  | Remarks
[9 empty] | Source | Amount
Monitoring
Review quarterly, annual and donor reports and provide timely feedback (within 5 days of receiving the report) | All | All |  |  | Strategic support unit, Barbara Bamanya | Country offices and RO thematic leaders | Annual report – January-February each year Quarterly reporting – April, July, October Donor reporting – per donor agreements |  | Core |  | Staff time as this is a routine activity
Conduct sub-regional reporting and RBM training for M/COs in collaboration with HQ | All | All |  |  | Strategic support unit, Barbara Bamanya | HQ and country offices |  |  | Core | 80000
Undertake quality review of donor reports for Tier classification | All | All |  |  | Strategic support unit, Barbara Bamanya | HQ and country offices | Every two years |  | Core | 40000 | Consultant will be hired to undertake an independent assessment
Monitor and track progress against the annual work-plans | All | All |  |  | Strategic support unit, All thematic leads | Country offices and RO thematic leaders |  |  | Core |  | Staff time as this is a routine activity
Undertake quarterly monitoring verification visits | All | All |  |  | Strategic support unit, All thematic leads | Country offices and RO thematic leaders |  |  | Core
Check collected data in country offices and compare with performance indicators to identify data gaps as well as data quality issues and make recommendations accordingly | All | All |  |  | Strategic support unit, Barbara Bamanya | Country offices |  |  | Core |  | Staff time as this is a routine activity
Coordinate the annual report preparation and ensure quality in line with UN women guidelines | All | All |  |  | Strategic support unit, Barbara Bamanya | Country offices and RO thematic leaders | Annual report – January-February each year |  | Core |  | Staff time as this is a routine activity
ESARO SN mid-term review | All | All |  |  | Strategic support unit, SPCU | Country offices and RO thematic leaders | 4th quarter 2023 |  | Core | 50000
Research
Support to women’s movement, organizations and networks to generate and contribute to knowledge products and tools | All | All | Number of women’s movement, organizations and networks supported to generate and contribute to knowledge products and tools |  | Thematic units | Women’s movement, organizations and networks | Jan 2022-Dec 2025 |  | Core |  | Staff time as this is a routine activity
Develop National Action Plans on Women, Peace and Security with monitoring indicators |  | Outcome 1: Regional bodies in ESA hold member states accountable for implementation of GEWE commitments | Number of adopted National Action Plans on Women, Peace and Security with monitoring indicators | Identify NAPS in ESAR that have been adopted and that have monitoring indicators Governments/countries that have constituted their NAPS | WPS | Regional bodies | Jan 2022-Dec 2026
Hold multi-stakeholder dialogues and learning/ knowledge sharing processes to promote engagement of governments,civil society actors, RECs and private sector on GEWE related issues. | All | All | Number of multi-stakeholder dialogues and learning/ knowledge sharing processes to promote engagement of governments,civil society actors, RECs and private sector on GEWE related issues. | Y | Thematic units | HQ and country offices | Jan 2022-Dec 2027 |  | Core
Technical support to country offices to ensure use of gender statistics, analysis, and policy-relevant research with ESARO support (UNFPA, UNICEF) | All | All | Number of countries demonstrating use of gender statistics, analysis, and policy-relevant research with ESARO support (UNFPA, UNICEF) | Y | Gender Statistics Unit and Thematic Leads | Country offices and RO thematic units | Jan 2022-Dec 2028 |  | Core |  | Staff time as this is a routine activity
Mapping/Listing of evidence-based models for social norms and behaviour change | All | All | Number of evidence and/or practice based standardized approaches or models for social norms and individual behavior change that are available for partners | Y | Thematic units | Country offices and RO thematic leads | Jan 2022-Dec 2029 |  | Core
Develop, publish and review national gender equality profiles and ensure utilisation towards informing national priorities |  |  | Number of countries in ESA with national gender equality profiles developed and published and informing national priorities | Y | KM | M/COs | Jan 2022-Dec 2030 |  | Core |  | Staff time
Generate and disseminate demand-driven thematic gender data and research knowledge products with support from ESARO | All | All | Number of demand-driven thematic gender data and research knowledge products generated and disseminated with support from ESARO | Y | KM and thematic leads | UN, CSOs, M/COs, development agencies, Member States | Jan 2022-Dec 2031
Technical support on gender, data, statistics and research products to inform national polices/strategies and planning. | All | All | Number of ESARO-supported gender, data, statistics and research products that are used to inform national polices/strategies and planning. | Y | KM and thrematic leads | M/COs | Jan 2022-Dec 2032 |  | Core
Develop normative frameworks, standards, guidance notes and protocols to regulate and inform the production of gender data, statistics and research on GEWE | All | All | Normative frameworks, standards, guidance notes and protocols are developed - by all stakeholders to regulate and inform the production of gender data, statistics and research on GEWE | Y | Gender Statistics Unit and Thematic Leads | Country offices, NSOs | Jan 2022-Dec 2033 |  | Core |  | Staff time as this is a routine activity
Develop and operationalise a regional knowledge management and research strategy for ESARO | All | All | Regional knowledge management and research strategy developed and operationalized. | Y | KM | Country offices and RO thematic units | 2022-01-01 |  | Core |  | Staff time as this is a routine activity
Develop and disseminate interagency GEWE knowledge products (flagship publications) | All | All | Number of interagency GEWE knowledge products (flagship) developed and disseminated with ESARO support/leadership | Y | KM and other thematic leads | UN agencies and other CSOs | Jan 2022-Dec 2025 |  | Core
Evaluation Plan 2022-2025
Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs2 | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks
Evaluations in which the office leads
Regional evaluation in final year of the RO Strategic Note in order to inform the new Strategic Note | Y | All | All | IES, Regional Evaluation Specialist | ESAR | Y | 2025 |  | 50,000 Core
Thematic regional | N | TBD based on evaluation topic | TBD based on evaluation topic | IES, Regional Evaluation Specialist | ESAR | Y | 2022-2025 |  |  |  | This will depend on projects/programmes implemented/resources mobilized.
Evaluations in which the office participates