## 2014 MER Plan India MCO
Annex 6: MONITORING, EVALUATION AND RESEARCH PLAN 2014
INDIA MULTI COUNTRY OFFICE
Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome | Relevant Country/ SRO AWP Output | Office to manage the MER activity | Region, Sub Region or Country | Joint MER activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-completion) | Budget (US$) for MER activity/ Sources of Funding | Status (pending - initiated – ongoing - completed) | Remarks
2014
1) MONITORING activities undertaken by the Multi Country Office e.g. Partner visits, Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc.
Impact 1: Women lead and participate in decision making at all levels
Quarterly progress reports and annual progress reports for the training of EWRs from India and Bhutan | N | Outcome 1.1 Women from excluded communities have increased political representation and voice at levels of the government | Output 1.1.1 Women from excluded communities are trained to participate at all levels of government in India, Bhutan and Maldives between 2014 – 2017 | India MCO | India | N | NIRD | Jan-Dec
Baseline and six monthly narrative progress reports for project on " Making women's voices and votes count- An ICT based intervention in India" | N |  |  | Inida MCO | India | Y | It for Change, KMVS, ANANDI | Jan-Dec |  | Ongoing | FGE Project
Impact 2: Women from excluded communities in MCO countries realise their right to sustainable livelihoods, decent work and social protection.
Quarterly progress reports and annual progress reports for research study on " Tribal Women's Right to Land Ownerhsip" and "project on women’s collectives or membership-based organisations (MBOs) formed" | N | Outcome 2.1 National and state policies, strategies and flagship programmes become gender responsive and women have increased access to and control over income and resources. | Output 2.1.1 Research, training and support provided to engender flagship government programmes on rural employment, livelihoods, social protection and financial inclusion | India MCO | India | N | SEWA Bharat, Home Net India and PRADAN | Jan-Dec |  | Pradan ( Ongoing)
Quarterly progress reports and annual progress reports for "Research study on remittances sent by women migrant domestic workers" | N |  |  | India MCO | India | N | Western Union Foundation , Centre for Development Studies | Jan-Dec
Quarterly progress reports and annual progress reports for "project on women farmers and informal sector workers with access to sustainable livelihood and decent work" | N |  | Output 2.1.2 Women from excluded communities, especially those working in agricultural and informal sectors, have increased access to income generation opportunities, social protection and decent work conditions | India MCO | India | N | NRLM, MKSP, ANANDI | Jan-Dec
Baselines and six monthly narrative progress reports for the projects on : 1. Economic empowerment of women in low income goups and the realization of their economic rights and gender equality ( SriLanka); 2. Dignity Campaign- Action for Liberation of Dalit Manual Scavenger women in India; 3. Facilitating women in four endemic poverty states of India to access, actualize and sustain provisions on women empowerment | N |  |  | India MCO | India | Y | CENWOR, Jan Sahas, PRADAN | Jan-Dec |  | Ongoing | FGE Projects
Impact 3: Women and girls in four South Asian countries live a life free from violence.
Quaterly, Annual progress reports and Donor reports for the projects on ending violence against women (trafficking, widows, safe Cities, Trust fund, SG Unite) |  | Outcome 3.1 State response to violence against women (i.e. EVAW laws, policies and strategies) are informed by voices of women and survivors of violence | Output 3.1.1 EVAW service providers have increased capacity for effective coordination and implementation of multi sectoral plans on VAW | India MCO | India | N | CECODECON, JJS, CBATN, SANLAAP, FXB India Suraksha, AID India, | Jan-Dec
| N |  | Output 3.1.2 Girls, women, boys and men in Bhutan and India have increased awareness and display positive attitudes on the prevention of gender-based violence [in Bhutan with UNDP, UNFPA, UNICEF, WHO, P4P, in India UNTF projects, Safe Cities program) | India MCO | India | N | Jagori, ICRW, KHPT, Fair Wear, Breakthrough | Jan-Dec
Monitoring of the Trust Fund Projects in India and Bangladesh | N |  | Output 3.1.2 Girls, women, boys and men in Bhutan and India have increased awareness and display positive attitudes on the prevention of gender-based violence [in Bhutan with UNDP, UNFPA, UNICEF, WHO, P4P, in India UNTF breakthrough projects, safe cities) | India MCO | India and Bangladesh | Y | Fair Wear Foundation, Breakthrough and Karnataka Health Promotion Trust | Jan-Dec
Impact 4: Peace building and humanitarian action are shaped by women leadership and participation in four countries in South Asia.
Quaterly, Annual progress reports and Donor reports for the projects on "Capacity building of peacekeeping institutions and partners to integrate gender perspectives into policies and measures for humanitarian action" and "pre-deployment trainings provided to UN military observers" |  | Outcome 4.1 Peace building process and humanitarian action is gender responsive | Output: 4.1.1 Gender responsive pre-deployment training, particularly related to sexual violence in armed conflicts, provided to UN military observers | India MCO | India | N |  | Jan-Dec
Impact 5: Macroeconomics framework and national development plans and budgets fully reflect accountability for GE commitments and priorities
Quaterly, Annual progress reports and Donor reports for projects on "Macroeconomic Framework and National Development Plans and Budgets reflect GE outcomes), capacity building of practitioners on gendered aspects of Census and statistics and data systems and statistics generated on GE in partnership with the GOI" | N | Outcome 5.1 Macroeconomic policies, national and sub-national plans adopt and implement specific commitments to advance GE/WE | Output 5.1.2 National and sub-national planning, budgeting and accountability mechanisms made gender responsive | India MCO | India | N | Fiscal Policy Institute | Jan-Dec
| N |  | Output 5.1.3 Strengthened capacities and alliance of gender equality advocates and national women’s machinery in four countries to influence global and regional mechanism to promote gender equality and women’s empowerment | India MCO | India | N | NEN, | Jan-Dec
OEE output cluster 2: To institutionalize a strong culture of results-based management, reporting, knowledge management and evaluation
14 Monitoring visits to be conducted for 7 projects under 5 Impact areas | N |  | Output 2.1 Performance Monitoring Framework (PMF) effectively implemented by the MCO office by 2017 | India MCO | India | N |  | Jan-Dec | 20000
2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc.
Impact 2: Women from excluded communities in MCO countries realise their right to sustainable livelihoods, decent work and social protection.
Final Evaluation of UN Women projects on "Empowering Rural, Informal and Home Based women workers through Capacity Development" | N | Outcome 2.1 National and state policies, strategies and flagship programmes become gender responsive and women have increased access to and control over income and resources. | Output 2.1.2 Women from excluded communities, especially those working in agricultural and informal sectors, have increased access to income generation opportunities, social protection and decent work conditions | India MCO | India | N | SEWA Bharat | Apr-Jun | 10000
Impact 3: Women and girls in four South Asian countries live a life free from violence.
Final Evaluation of the "Anti Human Trafficking Programme" | Y | Outcome 3.1 State response to violence against women (i.e. EVAW laws, policies and strategies) are informed by voices of women and survivors of violence | Output 3.1.1 EVAW service providers have increased capacity for effective coordination and implementation of multi sectoral plans on VAW | India MCO | India | N | Ernst & Young | July-Sep | 30000
Final Evaluation of the project on "Empowerment of Widows and their Coalitions programme" | N |  |  | India MCO | India | N | WHR, WERC | Jan-Mar | 15000
Impact 5: Macroeconomics framework and national development plans and budgets fully reflect accountability for GE commitments and priorities
Final Evaluation of the Ford funded Programme on "Partnership with civil society and the Comptroller and Auditor General (CAG) of India to promote gender responsive planning, budgeting and auditing in select States" | Y | Outcome 5.1 Macroeconomic policies, national and sub-national plans adopt and implement specific commitments to advance GE/WE | Output 5.1.1 Research and data on women’s role in the macro economy provided to make policies and plans gender responsive | India MCO | India | N | Swadhikar, Social Watch, NEN, Fiscal Policy Institute and Independent Researchers | Apr-Jun | 10000
2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors etc.
Impact 2: Women from excluded communities in MCO countries realise their right to sustainable livelihoods, decent work and social protection.
Mid Term Review of the project on- Dignity Campaign- Action for Liberation of Dalit Manual Scavenger women in India; | N | Outcome 2.1 National and state policies, strategies and flagship programmes become gender responsive and women have increased access to and control over income and resources. | Output 2.1.1 Research, training and support provided to engender flagship government programmes on rural employment, livelihoods, social protection and financial inclusion | India MCO | India | Y | Jan Sahas | TBC | TBC
Impact 3: Women and girls in four South Asian countries live a life free from violence.
Final Evaluation of the Trust Fund Project in India and Bangladesh | N | Outcome 3.1 State response to violence against women (i.e. EVAW laws, policies and strategies) are informed by voices of women and survivors of violence | Output 3.1.2 Girls, women, boys and men in Bhutan and India have increased awareness and display positive attitudes on the prevention of gender-based violence [in Bhutan with UNDP, UNFPA, UNICEF, WHO, P4P, in India UNTF breakthrough projects, safe cities) | India MCO | India and Bangladesh | Y | Fair Wear Foundation, Breakthrough and Karnataka Health Promotion Trust | July-Oct | TBC
3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans
Impact 2: Women from excluded communities in MCO countries realise their right to sustainable livelihoods, decent work and social protection.
Research and Documentation on Best practices on Gender and NREGA | N | Outcome 2.1 National and state policies, strategies and flagship programmes become gender responsive and women have increased access to and control over income and resources. | Output 2.1.1 Research, training and support provided to engender flagship government programmes on rural employment, livelihoods, social protection and financial inclusion | India MCO | India | N | TBC | TBC | 50000
Research on Status of Women's Economic Empowerment in India. women's right to livelihood, decent work and social protection | N |  |  | India MCO | India | N | TBC | TBC
Research study on " Tribal Women's Right to Land Ownerhsip" | N |  |  | India MCO | India | N | PRADAN | TBC | 3000 (FGE) | Ongoing
Research study on remittances sent by women migrant domestic workers | N |  |  | India MCO | India | N | Western Union Foundation , Centre for Development Studies | TBC | 40000
Rapid impact assessment of gender sensitizations carried out by the gender advocates | N |  | Output 2.1.2 Women from excluded communities, especially those working in agricultural and informal sectors, have increased access to income generation opportunities, social protection and decent work conditions | India MCO | Maldives | N | TBC | TBC | TBC
Impact 3: Women and girls in four South Asian countries live a life free from violence.
Research on Models of One Stop Crisis centres | N | Outcome 3.1 State response to violence against women (i.e. EVAW laws, policies and strategies) are informed by voices of women and survivors of violence | Output 3.1.1 EVAW service providers have increased capacity for effective coordination and implementation of multi sectoral plans on VAW | India MCO | India | N | TBC | Apr-Sep | 15000
Research on Standard Operating Procedures on mainstreaming prevention of Trafficking in Large scale national programmes NRLM | N |  |  | India MCO | India | N | TBC | Jan-Sep | 50000
Impact 5: Macroeconomics framework and national development plans and budgets fully reflect accountability for GE commitments and priorities
Research study on interlinkages between Gender, Trade and Green Growth in India, Bangladesh, Bhutan and Nepal | N | Outcome 5.1 Macroeconomic policies, national and sub-national plans adopt and implement specific commitments to advance GE/WE | Output 5.1.1 Research and data on women’s role in the macro economy provided to make policies and plans gender responsive | India MCO | India | N | TBC | Jan-Dec | 286,070 (Non Core)
Research study on gender and fiscal policy | N |  |  | India MCO | India | N | TBC | Jan-Dec | 50000
Research study on Time Use to assess women's underpaid and unpaid work in select countries | N |  |  | India MCO | India | N | TBC | Jan-Dec | TBC
Expenditure reviews of select programmes/schemes . | N |  | Output 5.1.2 National and sub-national planning, budgeting and accountability mechanisms made gender responsive. | India MCO | India | N | TBC | Jan-Dec | 80,000 (Non-Core)

## Sheet1
5