UN Women Senegal

MONITORING, EVALUATION AND RESEARCH PLAN 2014-2017

Monitoring and Research Plan 2014

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Produce and disseminate the quarterly report of the Senegal Programme | Implementing partners | Quarterly: March, June, September, December 2014 |  | 0 |
| Produce and disseminate the annual report of the Senegal Programme | Implementing partners | December 2014 | Core Budget under OEEF 4 | 5 000 UDS |
| Produce and disseminate donor reports | Implementing partners | December 2014 (GELD, F4GE) | Non-core (GELD, F4GE) | 20 000 USD |
| Monitoring missions to the field | Implementing partners | Quarterly : March, June, September, December 2014 |  |  |
| Organize final evaluation and planning retreat for the Senegal Programme | Implementing partners | December 2014 | Core Budget under OEEF 3 | 6 000 USD |
| Establish and manage a strategy for monitoring and evaluation | Implementing partners | 01/14-12/14 | Core Budget under OEEF 3 | 5 000 USD |
| RESEARCH |  |  |  |  |
| Collection of data on women’s contribution to the parliament after one year of parity law implementation | Women parliamentarians | 01/14-12/14 | Core Budget under DRF 1 | 2 000 USD |
| Production of booklets on Senegal’s international commitments on gender issues in local languages | Women parliamentarians | 01/14-12/14 | Non-core (OSIWA) | 3 300 USD |
| Elaboration of a report on GSB and gender-sensitive policies | Women parliamentarians | 01/14-12/14 | Non-core (F4GE) under DRF 5 | 3 000 USD |
| Research and data collection is conducted at national level on VAWG in collaboration with UNFPA | Prime Minister cabinet; Ministry of Women’s affairs; Ministry of Health, Ministry of Justice, Ministry of Interior Affairs | 01/14-12/14 | Core Budget under DRF 3 | 20 000 USD |
| Conduct a study on practices of donors regarding the financing of GE measures | UN Women, bilateral and multilateral partners | 01/14-06/14 | Non-core (F4GE) Under DRF 5 | 15 500 USD |
| Finalization of a guide on GRB | Women parliamentarians | 01/14-06/14 | Non-core (F4GE) | 2 000 USD |
| Advocacy paper on Universal Health Care in Senegal | CICODEV | 01/14-12/14 | Core | 3 780 USD |

Evaluation Plan 2014-2017

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of the project « d’appui à la promotion des droits des femmes et des filles (PAPDFF) » [Support to the promotion of women’s and girl’s rights] with the Ministry of Justice | Y | Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Senegal AWP Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Senegal Programme | WCARO | N | Ministry of Justice, Ministry of Women’s Affairs | December 2014 | 5000 USD | Pending |  |
| Final evaluation of Project « renforcement des capacités des femmes parlementaires pour une application effective des engagements sur l’égalité des sexes au Sénégal »[Capacity building for women parliamentarians for an effective implementation of Senegal’s committments to gender equality ] Final evaluation of the project « Plaidoyer et renforcement des capacités pour la mise en œuvre effective de la loi sur la parité au Sénégal »(Advocacy and capacity development for the effective implementation of the parity law in Senegal) with COSEF | Y | Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Senegal AWP Operational effectiveness and efficiency results output cluster 2, Output 2.3. | Senegal Programme | WCARO | Y | Association of Women Parliamentarians; Ministry of Women’s Affairs COSEF, Ministry of Women’s Affairs | December 2014 | 3 321 USD 3 321 USD | Pending |  |

NB : Merci de noter que le taux utilisé est le taux en cours du mois de  JUIN : 602,182 $

- Projet  PAPDFF : 6.000.000 FCFA

- Les Projets : Femmes Parlementaires et le COSEF rassemblés font  4.000.000 FCFA

Les montants des projets étant en FCFA seront convertis en DOLLARS

Les bons montants actuels sont en surligné couleur Verte

Please fill out a separate row for each evaluation.