MONITORING, EVALUATION AND RESEARCH PLAN

El Salvador CO 2020

Monitoring and Research Plan

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Completion of Monitoring Module of Results Management System | Project coordinator-program specialist | Quarterly | n/a | n/a |
| Submission of inputs for quarterly and Annual Report | Project coordinator-program specialist | Quarterly Annually | n/a | n/a |
| Financial Reports | Project coordinator-program specialist | Monthly / Quarterly / Annually | n/a | n/a |
| Annual Programme Report (APR) | Project coordinator-program specialist | Annually (Quarterly?) | n/a | n/a |
| Donor final report | Project coordinator-program specialist | Three to Six months after the end of the project | n/a | n/a |
| RESEARCH |  |  |  |  |
| Geographic Atlas | Regional Coordination, national coordinators, Regional WEE Specialist | Q1-Q2, Q3, Q4 2020 | Non-core | 60,000 |
| Knowledge products and tools to improve women's position in value chains | Regional Coordination, national coordinators, Regional WEE Specialist | Q1-Q2, Q3, Q4 2020 | Non-core | 80,000 |
| Collection and dissemination of innovative technologies and methodologies used in national and international contexts to enhance women's owned enterprises access to productive resources | Regional Coordination, national coordinators, Regional WEE Specialist | Q1-Q2, Q3, Q4 2020 | Non-core | 60,000 |
| Costo directo e indirecto de la violencia | El Salvador CO | Q1, Q2 2020 | Core | 20,000 |
| Technical support to ISDEMU and Civil Society to strengthen the capacities for analysis and generation of information on femicidal violence and femicides, and for its dissemination. Spotlight pillar 5 (5.2.1 | El Salvador CO | Q1-Q2, Q3, Q4 2020 | Non -Core | 50,000 Usd |
| Reinforcement of the capacities of women’s organizations for monitoring and tracking compliance with recommendations for international mechanisms for the protection of human rights.( A. 6.2.1. pillar 6 spotlight ) Mecanismo de monitoreo OSOC. | ORMUSA, CEMUJER, MSM | Q1-Q4 2020 | Non core | 110,000.0 |
| Development of research on the resolutions and sentences for cases in the justice system; creation of reports on the application of laws, awareness raising and proposed changes.( A. 6.1.3. pillar 6 spotlight) | El Salvador | Q1-Q2, Q3, Q4 2020 | Non -Core | 70,000 usd |
| Development of a monitoring and evaluation system for the implementation of the Criminal Prosecution Policy in regards to violence against women | ISDEMU, Escuela de Capacitación Fiscal. | Q1-Q4 2020 | Non core | 35,000 usd |

Evaluation Plan

| Evaluation name | Manda tory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation Regional Programme on Women Economic Empowerment in Honduras, Guatemala y El Salvador (Italian Cooperation) | Y | SP Outcome 3 Output 9 | SNs/AWPs Outcome 3 | Panamá | Americas and the Caribbean | Y (Italian Cooperation) | SIECA, COMMCA (Secretaria Técnica), BCIE | 4Q 2021 | 60,000 (non-core) | Pending |  |
| Mid term Evaluation of SPOTLIGHT INITIATIVE | Y | SP Outcome 4 | SNs/AWPs Outcome 4 | El Salvador | Americas and the Caribbean |  |  | Q2, Q3 2020 | 60,000 non core | pending |  |
| Final Evaluation of the PBF | Y | SP Outcome 1 | SNs/AWPs Outcome 1 | El Salvador | Americas and the Caribbean | Yes, UNDP | Ministry of transport, | Q 1, Q2 2021 | 40,000 non core | pending |  |
| Final Evaluation of the SN | Y | NA | OEEF | El Salvador | LAC | n | ISDEMU, CSO, government counterparts | Q1 2020 | 25,000 | Tor drafted |  |
| Evaluation in which the | Office | participates |  |  |  |  |  |  |  |  |  |
| Final Evaluation of Fomilenio Project | N | SP Outcome 4 | SNs/AWPs Outcome 4 |  | Americas and the Caribbean | no | Ministry of Educatio, Simeón Cañas University (UCA), FOMILENIO | Q1 | TBC | pending |  |
| Evaluation of the Special and Comprehensive Law for a Life Free of Violence against Women, that contributes, among other aspects, to the revision, drafting, advocacy and reform proposal of the Penal Code, to ensure alignment with international human rights standards for women (MESECVI/Belem do Pará andCEDAW). | Y | SP Outcome 4 | SNs/AWPs Outcome 4 | El Salvador | El Salvador | N | ISDEMU, Asamblea Legislativa | Q1,Q2 2020 | 67,500 | STARTED |  |
| Evaluation of training processes linked to violence against women and femicidal violence developed by training schools in the justice and security sector, to identify knowledge gaps, the application of these trainings, and incorporate quality improvements in the training plans and processes. | Y | SP Outcome 4 | SNs/AWPs Outcome 4 | El Salvador | El Salvador | n | ISDEMU, / Escuelas del sector de Justicia | Q1-Q4 2020 | 30,000 USD | pending |  |

## Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Mid term evaluation of the Spotlight Initiative | Relevance of the Subject, Mandatory for the donor | High | Resource Mobilization |
| Final Evaluation o f the Strategic Note 2016-2020 | Relevance of the work | High | Lessons learned |
| Final Evaluation Regional Programme on Women Economic Empowerment in Honduras, Guatemala y El Salvador (Italian Cooperation) | Relevance of the subject Significant investment Mandatory for the donor | High | Strategic planning and programming, learning and accountability |