# Annex 1: 2012-2013 MONITORING, EVALUATION AND RESEARCH (MER) PLAN

Note: As per the Guidance “How to develop UN WOMEN Monitoring, Evaluation and Research (MER) Plans”, MER Plans are developedat country, sub-regional and regional level. The development of MER Plan needs to beclosely linked with the development of Annual Work Plans.

| Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome | Relevant Country/ SRO AWP Output | Office to manage the MER activity | Region, Sub Region or Country | Joint MER activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-completion) |  | Budget (US$) for MER activity/ Sources of Funding | Status (pending - initiated – ongoing - completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2012 |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |  |
| Systematization of the work of UN Women and UNDP in 6 regions of the country (missions will be used as well for monitoring purposes) | N | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | Colombia CO | Colombia | N | UN Women’s SC organizations and local governments and institutions | January/September 2013 |  | USD 50,000 “Truth Justice and Reparation programme” (T,J,R P) funds | start in 2013 |  |
| Monitoring of the use that is given to knowledge products and tools made available by UN Women, and the impact that UN Women’s trainings and workshops have. | N | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | Colombia CO | Colombia | N | UN Women’s SC organizations and local governments and institutions | January. December |  | USD 10,000 (T,J,R P) funds | not carried out |  |
| Finalized the Base line on the access of women victims to the rights to truth , justice and reparations in Colombia | N | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | Colombia AWP Output: 4.1.1, 4.1.2, 4.2.1 | Colombia CO | Colombia | N | UN Women’s SC organizations, local and national governments and institutions | January- March |  | Total activity: USD 213,000 (T,J,R P) funds distributed as following: 2011: USD 200,000 2012: USD 13,000 | completed | Activity running from 2011 |
| UN Women Annual Report | Y | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | Colombia CO | Colombia | N | UN Women’s SC organizations and local governments and institutions | August-November |  | USD 5,000 (T,J,R P) funds | completed |  |
| Final Official Report on Truth, Justice and Reparation made by the Center for Memory in Colombia (former National Commission for Reparation and Reconciliation) | N | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | Colombia AWP | Colombia | Colombia | N | Center for Memory in Colombia (former National Commission for Reparation and Reconciliation) | June –December and the report will be completed by mid 2013 |  | USD 50,000 (T,J,R P) funds | completed |  |
| Annual report on sociopolitical violence against women in the framework of the armed conflict | N | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | DRF 4.2.3 | Colombia | Colombia | N | “Mesa de trabajo Mujer y conflicto armado” | January-April |  | USD 20,000 in 2012 (T,J,R P) funds | completed | Activity running from 2011 |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |  |
| Mid-term Evaluation of the Programme “Truth, Justice and Reparation for women victims in Colombia” | Y | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | ColombiaCO | Colombia | Y | UN Women, Swedish Embassy | December 2011 - February 2012 |  | USD30,800 | Completed |  |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors, etc. |  |  |  |  |  |  |  |  |  |  |  |  |
| FinalEvaluation of the MDG-F Programme on Gender Based Violence | Y | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | Colombia AWP | HQ MDG-F | Colombia | Office of the Resident Coordinator in Colombia, UN Women,AECID |  | January 2012- March 2012 |  | USD16,000 | Completed |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |  |
| Report on historical perspective and contributions to peace building from women ex-combatants | N | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | DRF 4.1.1. | Colombia | Colombia | N | “COLECTIVO MUJERES COMBATIENTES” |  | January- April | USD 2,000 in 2012 (T,J,R P) funds | completed | Activity running from 2011 |
| Publication about women’s political participation and leadership at the local level after 2011 elections ( Acts as a baseline) | N | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, | Colombia | Colombia | N | Political Commission of the International Cooperation Gender Group Table |  | February -March | USD 5,500 (T,J,R P) funds | Completed in 2013. |  |
| Gender Equality ranking between men and women in political parties and movements in Colombia | N | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, | Colombia | Colombia | N | Political Commission of the International Cooperation Gender Group Table |  | February- July | USD 5,500 (T,J,R P) funds | completed |  |

| 2013 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |
| Systematization of the work of UN Women and UNDP in 6 regions of the country (missions will be used as well for monitoring purposes) | N | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | DRF 4.1.2.a | Colombia CO | Colombia | N | UN Women’s SC organizations and local governments and institutions | January. December | USD 10,000 (T,J,R P) | on going |  |
| Monitoring of the use that is given to knowledge products and tools made available by UN Women, and the impact that UN Women’s trainings and workshops have | N | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | Colombia CO | Colombia | N | UN Women’s SC organizations and local governments and institutions | January. December | Core. | starting |  |
| UN Women Monthly Report | Y | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | Colombia CO | Colombia | N | UN Women’s SC organizations and local governments and institutions | Monthly | Core. | On goin. |  |
| UN Women tracking tools | Y | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | Colombia CO | Colombia | N | UN Women’s SC organizations and local governments and institutions | August-November | Core. | pending |  |
| UN Women Annual Report | Y | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | Colombia CO | Colombia | N | UN Women’s SC organizations and local governments and institutions | August-November | USD 1,000 to be raised | pending |  |
| Final systematization of the MDG-F Program on Peace Building in Pasto. | N | UNCT Priorities / UNDAF 2008-2012: Outcome 2 UN WOMEN SP Goal 3 | Colombia AWP | HQ MDG-F / Resident Coordinator | Colombia | Office of the Resident Coordinator in Colombia, UN Women, AECID |  | May2013 / July 2013 | USD10,352 | On going |  |
| Systematization of the Diploma in Business Management with indigenous women, in Nariño. | N | UNCT Priorities / UNDAF 2008-2012: Outcome 2 UN WOMEN SP Goal 3 | Colombia AWP | HQ MDG-F | Colombia | Office of the Resident Coordinator in Colombia, UN Women,AECID |  | May 2013 / July 2013 | USD10,352 | On going |  |
| Systematization of four cases of historical memory in the framework of the MDG-F Programme on Peace Building in Nariño. | N | UNCT Priorities / UNDAF 2008-2012: Outcome 2 UN WOMEN SP Goal 3 | Colombia AWP | HQ MDG-F | Colombia | Office of the Resident Coordinator in Colombia, UN Women,AECID |  | May 2013 / July 2013 | USD10,352 | On going |  |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |
| None |  |  |  |  |  |  |  |  |  |  |  |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors etc. |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation of the MDG-F Programme on Peace Building in Pasto. | Y | UNCT Priorities / UNDAF 2008-2012: Outcome 2 UN WOMEN SP Goal 3 | Colombia AWP | HQ MDG-F / Resident Coordinator | Colombia | Office of the Resident Coordinator in Colombia, UN Women,AECID |  | April 2013 / June 2013 | USD5,000 | On going |  |
| Final Evaluation of the Program “Truth, justice and reparation for women victims in Colombia” | Y | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | Swedish Embassy (ASDI) | Colombia | N | Colombian Government State’s Institutions and CS | January-April | TBD by Swedish Cooperation | Pending |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |
| Final systematization of the MDG-F Program on Peace Building in Pasto. | N | UNCT Priorities / UNDAF 2008-2012: Outcome 2 UN WOMEN SP Goal 3 | Colombia AWP | HQ MDG-F / Resident Coordinator | Colombia | Office of the Resident Coordinator in Colombia, UN Women, AECID |  | May2013 / July 2013 | USD10,352 | On going |  |
| Publication about women’s political participation and leadership at the local level after 2011 elections ( Acts as a baseline) | N | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, | Colombia | Colombia | N | Political Commission of the International Cooperation Gender Group Table | February -March | USD 5,500 (T,J,R P) funds | Completed in february 2013 |  |
| “Ranking of Equality of Men and Women in Colombian Political Parties and Movements”, | N | UNCT Priorities / UNDAF 2008-2012: Outcome 4 UN WOMEN SP Goal 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, | Colombia | Colombia | N | Political Commission of the International Cooperation Gender Group Table | March | USD 1,000 (T,J,R P) funds | Completed in march 2013 |  |
| Toolkit for reconstruction of the contemporary history of armed conflict in Colombia, with gender perspective. | N | UNCT Priorities / UNDAF 2008-2012: Outcome 1,2, 3, 4 UN WOMEN SP Goal 1, 3 and 4 | Colombia AWP Output: 1.1.1, 1.1.2, 1.1.3, 1.2.1, 1.3.1, 3.1.1, 3.2.1, 3.3.1, 4.1.1, 4.1.2, 4.2.1 | Swedish Embassy (ASDI) | Colombia | N | Colombian Government State’s Institutions and CS | January-April | USD30,000 (T,J,R P) funds | On going |  |
| # Case study of women, peace and security | N | UNCT Priorities / UNDAF 2008-2012: Outcome 2 UN WOMEN SP Goal 4 | Colombia AWP | RO | Colombia | RO |  | May 2013 / July 2013 | - | On going |  |

# Annex 2: Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Mid-Term Evaluation of the Programme “Truth, justice and reparation for women victims in Colombia” | Mandatory due to UN Women evaluation Policy and required by the donor | Yes - Existence of the mid-term evaluation - Existence of the M&E system, and sufficient information about the programme | To gain lessons learned and provide feedback to the programmatic action lines of the Colombian Office. In addition, to adjust the strategy for a possible programme extension |