MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2018

SOUTH SUDAN COUNTRY OFFICE

Monitoring Plan

| SN Impact/Outcome/Output Cluster | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| Women lead and participate in decision-making at all levels |  |  |  |  |  |  |
| 1.4.1. National and selected state legislative assemblies have the technical capacity to formulate, review and implement legal and policy frameworks within Peace Agreement to advance women’s rights and political participation. | Conduct review meetings with selected state legislative assemblies to determine their level of engagement in the legislative reforms related to ARCSS | Programme Specialists Programme Officers | Transitional National Legislative Assembly, Women Parliamentary Caucus, Ministry of Gender, National Transformational Leadership Institute | Quarterly | Non-core | 20,000 |
| Women, especially the poorest and most excluded, are economically empowered and benefit from development |  |  |  |  |  |  |
| 2.1.1. Policy makers have improved skills and ability to apply international best practices in laws, policies, programmes and regulations on women's economic empowerment | Conduct review meetings and field visits with partners and beneficiaries in the programmatic intervention areas | Programme Specialists Programme Officers | Ministry of Finance, Commerce, Trade and Industry, Investment and Economic Planning, Chamber of Commerce, Ministry of Gender, SSWEA, focal points of implementing partners | Monthly | Non-core | 34,000 |
| 2.3.1. Women entrepreneurs have strengthened skills and opportunities (including credit) to improve their livelihoods and resilience | Carry out focus group discussions with beneficiaries of loan, verification of SACCO records and discussion with women engaged in cross-border | Programme Specialists Programme Officers | Focal persons of implementing partners, Ministry of Gender, SSWEA, South Sudan Chamber of Commerce and the Cooperative Bank | Quarterly | Non-core | 29,000 |
| 2.5.1. Local infrastructure developed to improve access to markets, reduce labour, and save time for women farmers. | Embark on site visits and conduct focus group discussions with women cooperative members | Programme Specialists Programme Officers | Focal persons of implementing, Ministry of Agriculture, Cooperative and Rural Development, WFP, FAO | Q1 and Q3 | Non-core | 15,000 |
| Women and girls live a life free from violence |  |  |  |  |  |  |
| 3.2.1: Law enforcement at the local levels, and customary court authorities in local communities (payam level), have increased their technical skills to implement laws, policies and strategies to prevent and respond to violence against women and girls by the end of 2018 | Tracking on legal aid services documentations; status of implementation of the customary law officials action plans, gender/women’s right strategy for the national police service and male champions engagement | Programme Specialists Programme Officers | National Police Service, Customary Law Officials and Focal persons of Implementing partners | Quarterly | Non-core | 20,000 |
| Women and girls contribute to and have greater influence in building sustainable peace and resilience, and benefit equally from the prevention of natural disasters and conflicts and from humanitarian action |  |  |  |  |  |  |
| 4.1.1 Multi-sectoral humanitarian/crisis response planning and programming informed by gender analysis. | Follow-up on humanitarian cluster workplans and engagement of women in humanitarian response; | Programme Specialists Programme Officers | Ministry of Humanitarian Affairs, Ministry of Gender, Inter-cluster working group, humanitarian Clusters and Focal persons of Implementing partners | Quarterly | Core | 10,000 |
| 4.1.2. Increased capacity and effective engagement of women & gender machineries in humanitarian planning, response frameworks and programming. | Midterm review of plans of gender machineries and other key stakeholders | Programme Specialists Programme Officers | Ministry of Humanitarian Affairs, Ministry of Gender, Inter-cluster working group, humanitarian Clusters and Focal persons of Implementing partners | Monthly | Core | 5,000 |
| 4.1.3: National, UN & aid coordination mechanisms strengthened to identify, address and monitor the needs of women and girls by the end of 2018 | Conduct a follow-up on the application of the gender-responsive monitoring tools | Programme Specialists Programme Officers | Ministry of Humanitarian Affairs and Disaster Management, Ministry of Gender, Child and Social Welfare, OCHA and Focal persons of Implementing partners | Q2 and Q4 | Core | 5,000 |
| 4.2.1: I Increased leadership and engagement by displaced women in relief efforts & decision making (in conflict affected communities) | Track and document women’s active engagement in leadership structures and in project management committees in all project locations | Project Specialists Project Officers | Ministry of Humanitarian Affairs and Disaster Management, Ministry of Gender, Child and Social Welfare, OCHA, NTLI and Focal persons of Implementing partners | Quarterly | Non-core | 8,000 |
| 4.2.2: Increased access to effective services & protection mechanisms through social spaces in temporary shelters and in host communities in 2018 | Track and document the services accessed by the beneficiaries in the project areas | Project Specialists Project Officers | Ministry of Humanitarian Affairs and Disaster Management, Ministry of Gender, Child and Social Welfare and HCT, and Focal persons of Implementing partners | Monthly | Non-core | 10,000 |
| 4.2.3: New sources of income and economic opportunities created through targeted cash for work & development of capacities and skills by the end of 2016 | Conduct focus groups discussions and interviews with women and girls engaged livelihoods activities, ICT and adult literacy programmes | Project Specialists Project Officers | Ministry of Humanitarian Affairs and Disaster Management, Ministry of Gender, Child and Social Welfare, Ministry of Education, Science and Technology, Ministry of Agriculture, Forestry, Cooperatives and Rural Development, University of Juba, OCHA, UNESCO, AMIRAN Kenya and Focal persons of Implementing partners | Monthly | Non-core | 50,000 |
| 4.3.1: Women participate in peacebuilding & recovery planning | Meetings with women groups, organizations and networks to determine the level of engagement at the national grassroots levels | Project Specialists Project Officers | Ministry of Gender, Child and Social Welfare, National Legislative Assembly, National Constitutional Review Commission, Disarmament, Demobilisation and Reintegration (DDR) Commission and Security Sector, and Civil Society and UNDP | Monthly | Non-core | 6000 |
| 4.3.2: Post-conflict institutions and processes (including security, justice, reconciliation & governance) are gender-responsive. | Conduct review meetings with newly established institutions to determine gender mainstreaming status | Project Specialists Project Officers | Ministry of Gender, Child and Social Welfare, National Legislative Assembly, National Constitutional Review Commission, Disarmament Demobilisation and Reintegration (DDR) Commission, Security Sector, and Civil Society, including women led organizations and UNDP | Q2 and Q4 | Non-core | 30,000 |

Research Plan

| Activity | Partners and stakeholders |  | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |  |
| 2.1.1.4. Provide technical support to the Ministry of Gender to develop a legal framework for the Women Enterprise Development Fund. | Ministry of Finance; Commerce, Trade and Industry, Investment and Economic Planning; Ministry of Gender Child and Social Welfare, Chamber of Commerce, South Sudan Women Entrepreneurs Association | Q1 |  | Non-core | 40,000 |
| 2.3.1.2. Develop a database of women owned enterprises and cooperatives in South Sudan. | Ministry of Finance; Commerce, Trade and Industry, Investment and Economic Planning, South Sudan Women Entrepreneurs Association (SSWEA); South Sudan Chambers of Commerce; Cooperatives Bank of South Sudan | Q2 |  | Non-core | 20,000 |
| 3.2.1.5. Undertake study to assess women and girls access to transitional justice in communities affected by conflict (those hosting IDPs and with a focus on women/girls living with disabilities, living with HIV/AIDS, SGBV survivors and young mothers). | South Sudan National Police services, Traditional Court Officials, Focal persons of Implementing partners | Q1 and Q2 |  | Non-core | 50,000 |
| 4.1.1.3. Lead the conduct of assessment of gender gaps in humanitarian response in IDP sites and spontaneous settlements, including hard to reach areas where humanitarian assistance is by air-drops by 2018 | Ministry of Gender, Child and Social Welfare, Ministry of Humanitarian Affairs and Disaster Management; OCHA, Humanitarian Cluster focal persons, Geopoll, Focal persons of Implementing partners | Q1 |  | Non-core | 20,000 |
| 4.2.3.6: Conduct a study on gender and land rights in Pageri, Awerial, Jubek, Mundri, Yambio, Wulu and Turalei to inform advocacy on women's access to land in project locations | Ministry of Humanitarian Affairs and Disaster Management, Ministry of Gender, Child and Social Welfare, OCHA, University of Juba, UNESCO, Ministry of Education and Focal persons of Implementing partners | Q1 and Q2 |  | Non-core | 75,000 |

Evaluation Plan

| Evaluation name | Mandatory (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| 7. Quarterly progress review meeting of the AWP-tracking of delivery on the various OEEF, key deliverable, RRIs and DRF outputs and outcomes | Y | UN Women’s Outcomes 1.4, 2.1, 2.3, 2.5, 3.2, 4.1, 4.2 and 4.3 | All | South Sudan CO | South Sudan | N | South Sudan CO | quarterly | $10,000 |  |  |
| Midterm review of the UN Women AWP report uploaded into the online UN Women GATE System | Y | UN Women’s Outcomes 1.4, 2.1, 2.3, 2.5, 3.2, 4.1, 4.2 and 4.3 | All | South Sudan | South Sudan | N | South Sudan CO | June 2018 | US$ 15,000 |  |  |
| End of Project Evaluation of the Humanitarian Assistance Programme funded by Japan | Y | Impact 4 | All | South Sudan CO | South Sudan and RO | Y | South Sudan CO | March 2018 | US $ 35,000 |  |  |