China Project Office

MONITORING, EVALUATION AND RESEARCH PLAN 2020

Monitoring and Research Plan 2020

| Activity | Partners and stakeholders | Responsible Staff | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Source | Amount |
| To conduct project site visits for the 8th batch and 9th batch CGF project monitoring to ensure the compliance to UN Women rules and regulations. 1) Project site visits conducted by project staff during key project activities (at least 2 for each project in 2020); 2) Monthly (online) meetings with RP; | - The Snowland Great Rivers Environmental Protection Association of Qinghai Province (SGR)， - China Association for NGO Cooperation - Shaanxi Research Association for Women and Family - Shanghai Mana Data Foundation - Jiangsu Association of Artificial Intelligence - Gansu Xingbang Social Work Serving Center - Dehong le chuang women's and children's development center - Xining Institute of Mental Health Education | Mr. Ma Leijun Ms. Gao Tao (backup) | Jan 2020-Dec 2021 Three times for each project in 2020 | Non-Core | $45,000 |
| Project site visits conducted during key project activities and monthly skype/telephone meetings with partners to monitor the progress of the the GBV-China programme and compliance to UN Women rules and regulations - At least three project-launch activities, one in each of the three pilot sites, in March 2020; - At least three training activities, one in each of the three pilot sites, in April/May 2020 | - Government Partners - Non-Government Partners - Pilot Sites, including but not limited to: - Beijing - Chengdu; - Dalian | Mr. Li Shuo Ms. Ai Yajuan (backup) | Jan 2020 – Dec 2020 Monitoring activities for first half of 2020 will take place in March and April. Details on monitoring activities for second half of 2020 will be determined in consultation with project partners. Skype/telephone meeting will take place on a monthly basis. | Non-Core | $15,000 |
| Monitor the progress of Gender and Climate Change Programme and compliance to UN Women rules and regulations, through: 1) Project site visits conducted by project staff during key project activities (at least 3 in 2020); 2) Monthly (online/offline) meetings with RP; 3) Site visit with the Donor (tentatively planned as in the middle of the year) | Government partners (tbc), field site beneficiaries |  | June 2018 – January 2021 | Non-core | $15,000 |
| Monitor the progress of Women’s Economic Empowerment Programme and compliance to UN Women rules and regulations, through: 1) Project site visits or online monitoring conducted by project staff during key project activities (at least 3 in 2020); 2) Bi-monthly (online) meetings with donor and RP | - China Global Philanthropy Insititute - Government, universities and NGO partners | Ms. Lin Jialei Ms. Liu Di (Bakcup) | Oct. 2017 – Dec 2020 | Non-core | $8,000 |
| Monitor the progress of WeEmpowerAsia programme and compliance to UN Women rules and regulations, through: 1) Project site visits or online monitoring conducted by project staff during key project activities (at least 5 for each project in 2020) | - China Textile Information Centre - Government, universities and NGO partners (tbc) | Ms. Lin Jialei Ms. Li Tingting (Backup) | November 2019- Mar 2022 | Non-core | $16,500 |
| Monitor the progress of COVID-19 Recovery Project and compliance to UN Women rules and regulations, through: 1) Project site visits or online monitoring conducted by project staff during key project activities (at least 2 for each project in 2020) 2) Regular Steering committee meeting (quarterly tbc) | - Government partners and local women’s federations(tbc) - Pilot Sites, including: - Wuhan - Tianjin | Ms. Liu Di Ms. Ai Yajuan (Backup) | June 2020-Jun 2022 | Non-core | $2,580 |
| Undertake CGF stock-take review-UN Women China Office | Finalize and launch the Stock-take review of the CGF and CGF strategy for resource mobilization |  | June-Dec. 2020 | Core and Non-Core | Core: USD 30,000 Non-Core: USD 60,000 |
| Undertake research by CGF partners in the following areas: Gender and new technology Gender and philanthropy And gender and belt and road | - Research on gender and environmental Protection by CGF partner-The Snowland Great Rivers Environmental Protection Association of Qinghai Province (SGR)， - Research on Gender and Philanthropy by CGF-Partner Shaanxi Research Association for Women and Family - Research on Gender and New Technology and COVID-19 impact on gender by CGF-partner Shanghai Mana Data Foundation, and Jiangsu Association of Artificial Intelligence - Research on girl’s education rights and Impact of COVID-19 on girls’ education by CGF partner-Gansu Xingbang Social Work Serving Center - Research on the life of the women trafficked from other countries to Dehong, Yunnan Province by CGF partner -Dehong Women and Children's Development Center | Mr. MA Leijun Ms. Gao Tao (Back up) | Jan-Dec 2020 All research studies will be conducted in the second half of 2020. | Please specify | $40,000 |
| A consultant will undertake research under Women’s economic empowerment programme on the cost of unpaid care work for women from a socio-economic and policy perspective– link to Outcome 2.1, Output 2, Activity 8 | TBD | Ms. Lin Jialei | Jan-Dec 2020 | Non-core | $25,000 |
| Undertake rapid impact assessment of COIVD-19 outbreak impacts on women-owned SMEs and targeted business with a large % of women workers, to identify targeted recover measure and strategy under COVID-19 recovery project | TBD | Ms. Liu Di | June-August 2020 | Non-core | $30,000 |
| Undertake research under GBV Programme on school-based primary intervention – link to Outcome 3.1, Output 3.1.1, Activity 3.1.1.1 and 3.1.1.4 | TBD |  | Mar – Dec 2020 | Non- core | $30,000 |
| Review and analyse GEWE principles, standards and actions in China's investment, development and humanitarian aid, including South-South Cooperation in the recent past years | TBD |  | Mar – Dec 2020 | Core | $50,000 |

Evaluation Plan 2020

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partner) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation on the Women’s Economic Empowerment | Y | Women have income security, decent work, and economic autonomy | Women in China have increased access to equal employment and leadership opportunities | UN Women China | ROAP/ China |  | Government, universities, and NGO partners, private sector stakeholders | June-Dec. 2020 | USD 50,000 Non-Core | Completed |  |

Please fill out a separate row for each evaluation.