# MEXICO COUNTRY OFFICE

# 2012-2013 MONITORING, EVALUATION AND RESEARCH (MER) PLAN

| Title & Type of MER activity | Mandatory (Y/ N) | Relevant UNDAF Outcome/ UN Women SP Goal and Outcome | Relevant Country AWP Output | Office to manage the MER activity | Region, Sub Region or Country | Joint MER activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-completion) | Budget (US$) for MER activity/ Sources of Funding | Status (pending – initiated – ongoing – completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2012 |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |
| Periodic monitoring of 2012 closing projects in Mexico (two weeks/monthly) | Y | MRF Goal 2 Output 2.1 | MRF Output 2.1. | Mexico-CO | MEXICO | N | - | March-December | Core funds (See SRO MER Plan) | Finalized (pending closure in Atlas) | 1 project closes in June 2012 The SRO hired an external consultant to periodically monitor all 2012 closing projects of the sub-region, including those for Mexico. Funds included only in the SRO MER Plan. |
| Revision of the MEXICO Strategy and AWP 2012-2013 (refinement of indicators/establishing of pending baselines and targets) | Y | MRF Goal 2 Output 2.1 | MRF Output 2.1. | Mexico-CO | MEXICO | N | - | May-June 12 | Core funds USD 1,000 | Finalized |  |
| Mid-term review of the MEXICO Strategy and AWP 2012-2013 | Y | MRF Goal 2 Output 2.1 | MRF Output 2.1. | Mexico-CO | MEXICO | N | - | Nov 2012- Enero 2013 | Core funds USD approx. 1,000 | Finalized |  |
| Monitoring of the Mexico Strategy and AWP 2012-2013 activities (core and non-core) | Y | MRF Goal 2 Output 2.3 | MRF Output 2.1 and 2.3 | Mexico-CO | Mexico | N | - | June-December | NA | Finalized |  |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |
| Phase III of the Specific Agreement UN Women- CDI: Strengthening the Institutional Capacity of CDI to Build Public Policies for Indigenous Peoples with a Gender Perspective 2011- 2012 | Y | Mexico UNDAF (2008-2012) Outcomes 2.6, 4.3 and 5.2. DRF GOAL 3 and 5 Outcomes 3.3 and 5.3 | DRF Outputs 3.2.1 and 5.3. 1 | Mexico CO | Mexico | N | National Commission for the Development of Indigenous Peoples (CDI), indigenous women’s organizations, academic sector, COs | June- August | Non-Core funds (Mexican Govt) USD 65,000 | Finalized MR ongoing |  |
| Evaluation of the programme: Design and implementation of Gender Equity Policies in the Ministry of Education | N | Mexico UNDAF 2008-2012 Outcome 2.6 and 4.3 DRF Goal 3 Outcome 3.2 |  | Mexico-CO | Mexico | Y (Ministry of Education) | National Institute of Public Health (INSP) | May-November | Non-core funds (Mexican Govt) USD 122,627.73 | Finalized |  |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors, etc. |  |  |  |  |  |  |  |  |  |  |  |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |
| Evidence production on how mass media professionals project women and gender issues during the 2012 electoral campaigns | Y | Mexico UNDAF (2008-2012) Outcome 5.3 (Output 5.3.3) DRF Goal 1, Outcome 1.1 | DRF Output 1.1.2 | Mexico-CO | Mexico (national and 3 States) | Y (IDEA-INTERNATIONAL, UNDP) | NWM, SUMA FGE-Project, Federal Electoral Institute, Political Parties, State Govts. | April-July | Non-core funds (Mexican Govt) TBD at first of July | Ongoing | 1 monitoring exercise at national level and 3 at State level |
| Key analyses of the results of the Mexico Time Use Survey and National Households Satellite Account regarding women’s paid and unpaid work | Y | Mexico UNDAF 2008-2012 Outcome 1.1 and 2.6 DRF Goal 2 Outcome 2.1. | México AWP Output 2.1.2 | Mexico-CO | Mexico | N | NWM, National Statistics Office, OCDE and ILO) Colmex | Nov2011-Dec 2013 | Core funds USD 70,000 | Ongoing |  |
| Research/ studies to detect strengths and weaknesses on violence against women´s administrative records and suggestions for improvements. | Y | Mexico UNDAF 2008-2012 Outcome 4.3 DRF Goal 3 Outcome 3.1 | Mexico AWP Output 3.1.1 | Mexico-CO | Mexico | N | NWM, Parliamentarian Femicide Commission, local women’s institutions, justice chain institutions, National Statistics Office, academic sector and stakeholders at State level | June- November | Non Core funds (Mexican Govt) USD 265,000 | Finalized |  |
| Research/ studies on feminicide violence at state level | Y | Mexico UNDAF 2008-2012 Outcome 4.3 DRF Goal 3 Outcome 3.1 | Mexico AWP Output 3.1.2 | Mexico-CO | Mexico (31 States and the Federal District) | Y (Congress’ feminicide Commission) | Academic sector (COLMEX), NWM, National Statistics Office (INEGI) and stakeholders at local level, justice sector | January-September | Core funds USD 100,000 | Ongoing | This activity includes south-south cooperation with CA countries to replicate Mexican femicide studies methodology 2012 study in Mexico finalized, CA studies to be finalized in 2013 |
| Knowledge production on good practices and lessons learned on gender effective planning and budgeting process at national level | Y | UNDAF UNDAF 2008-2012 Outcome 2.6 DRF GOAL 5, OUTCOME 5.1 | Mexico AWP Output 5.1.3 | Mexico-CO | Mexico | Y (NWM) | NWM, State Govts., State Congresses, Local Women’s institutions | June- November | Non Core funds (Mexican Government) USD 12,000 | Finalized |  |
| 2013 |  |  |  |  |  |  |  |  |  |  |  |
| 1) MONITORING activities undertaken by the Country/ Sub-regional/ Regional Office e.g. Partner visits, (Repeat) Baselines, Reviews, UN Women Annual Report, Annual Programme and UNDAF Review Process etc. |  |  |  |  |  |  |  |  |  |  |  |
| Periodic monitoring of 2013 closing projects in Mexico (two weeks/monthly) | Y | MRF Goal 2 Output 2.1 | MRF Output 2.1. | MEXICO-CO | MEXICO | N | - | January-December | Core funds TBD | Ongoing | Depending on projects/programmes |
| Monitoring of the Mexico AWP and Strategy 2012-2013 activities (core and non-core) | y | MRF Goal 2 Output 2.3 | MRF Output 2.1 and 2.3 | Mexico-CO | Mexico | N | - | January-December | Core funds 3500 US$ | Ongoing | Refined internal monitoring instruments have been elaborated and are in use, and the LAC-RO monitoring instruments have been incorporated to these. |
| 2a) EVALUATIONS managed by the Country/ Sub-regional/ Regional Office e.g. outcome, thematic, programme evaluations etc. |  |  |  |  |  |  |  |  |  |  |  |
| 2b) Other EVALUATIONS in which Country/ Sub-regional/ Regional Office is involved but NOT managing, e.g. evaluations managed by HQ Evaluation Office, Trust Fund on VAW, UNDEF, donors etc. |  |  |  |  |  |  |  |  |  |  |  |
| Mid-term and Final evaluation of the SUMA FGE-project: “Strengthening Women's Political Participation and Promoting an Economic Empowerment Agenda” | Y | Mexico UNDAF (2008-2012) Outcome 5.3 (Output 5.3.3) DRF Goal 1 Outcome 1.1 | DRF Output 1.1.1 | HQ | Mexico (federal and 12 States) | Y (FGE) | Implementing partners (CSOs), NWMs, Federal Electoral Institute, Federal Electoral Justice Tribunal, Political Parties, State Governments, State Parliaments, among others | September 2012 | FGE Funds TBD as of the first of July | Mid-term review ongoing Final evaluation planned for September-December2013 | Request for postponing final evaluation to first quarter of 2014 has been sent to HQ by FGE M&E Specialist |
| 3) RESEARCH Activities undertaken by the Country/ Sub-regional/ Regional Office with regard to the monitoring and evaluation needs of the Annual Work Plans |  |  |  |  |  |  |  |  |  |  |  |
| Research/ studies on feminicide violence at state level | Y | Mexico UNDAF 2008-2012 Outcome 4.3 DRF Goal 3 Outcome 3.1 | Mexico AWP Output 3.1.2 | Mexico-CO | Mexico (31 States and the Federal District) | Y (Congress’ feminicide Commission) | Academic sector (COLMEX), NWM, National Statistics Office (INEGI) and stakeholders at local level, justice sector | January-September | Core funds TBD | Ongoing | This activity includes south-south cooperation with CA countries to replicate Mexican feminicide studies methodology |
| Research on Human Development and Violence against Women | N | DRF Goal 3 Outcome 3.1 | México | Mexico | Mexico | Y (UNDP) | UNDP | TBD | Core funds TBC | Pending |  |
| Research/ studies to detect strengths and weaknesses on violence against women´s administrative records and suggestions for improvements. | Y | Mexico UNDAF 2008-2012 Outcome 4.3 DRF Goal 3 Outcome 3.1 | Mexico AWP Output 3.1.1 | Mexico-CO | Mexico | N | NWM, Parliamentarian Femicide Commission, local women’s institutions, justice chain institutions, National Statistics Office, academic sector and stakeholders at State level | June- November | Non-core funds (Mexican Govt) Approx. USD 265,000 | Pending | The project was renewed for 2013 and will start in June. |
| Knowledge production on good practices and lessons learned on gender effective planning and budgeting process at national level | Y | UNDAF UNDAF 2008-2012 Outcome 2.6 DRF GOAL 5, OUTCOME 5.1 | Mexico AWP Output 5.1.3 | Mexico-CO | Mexico | Y (NWM) | NWM, State Govts., State Congresses, Local Women’s institutions | June- November | Non-core funds (Mexican Government) TBD | Pending | The project was renewed for 2013 and will start in June-July. |
| Knowledge production on good practices and lessons learned on political participation |  | Mexico UNDAF (2008-2012) Outcome 5.3 (Output 5.3.3) DRF Goal 1 Outcome 1.1 | Mexico AWP Output 1.1.1 | Mexico-CO | Mexico | Y (NWM) | SUMA FGE-project, NWM, State Govts., State Congresses, Local Women’s institutions | June- November | Non-core funds (Mexican Government) TBD | Pending | The project was renewed for 2013 and will start in June-July. |
| Mapping document to detect the state of implementation of the CEDAW General Recommendation No. 26 (composed by two complementary knowledge products elaborated by Colmex and IMUMI) | Y | Mexico UNDAF 2008-2012 Outcome 1.1 and 2.6 DRF Goal 2 Outcome 2.1 | DRF Output 2.1.1. | Mexico-CO | Mexico | N | Implementing Partners: Colmex & IMUMI | February-November | Core funds USD 200,000 | Ongoing (to be finalized in Nov-2013) | The purpose of these two knowledge products is to advance progress in the formulation, monitoring and evaluation of public policies regarding the protection of migrant women worker’s rights through generation of knowledge on socio-demographic characteristics, conditions and rights of this group of women. |

# Annex 2: Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Phase III of the Specific Agreement UN Women- CDI: Strengthening the Institutional Capacity of CDI to Build Public Policies for Indigenous Peoples with a Gender Perspective 2011- 2012 (project evaluation) | Assess the results (outcomes, outputs and activities) of the Project from a gender and ethnic perspective and through analysis and dialogue among the strategic partners involved: the government, UN Women, the academic sector, CSOs, and particularly indigenous women’s organizations. It is important to evaluate the results of the VAW and Sexual and Reproductive Health Attention Model implemented by the CAMIs, since it is the only public initiative that addresses VAW in indigenous contexts. | High: necessary conditions in place to assess key aspects of the project. | - Disseminate the evaluation findings with national counterparts, in order to influence policy makers to design and implement public policies, legal frameworks and budgets from an ethnic and gender perspective, specifically with regard to EVAW in indigenous contexts and indigenous women’s leaderships. - Improve future programming with the new authorities of the CDI and indigenous women’s organizations, academia and key partners, including UNS, based on the lessons learned, innovative strategies and best practices identified in the evaluation. - Provide elements for the definition of a standardized VAW and Sexual and Reproductive Health Attention Model implemented by the CAMIs (indigenous women houses), in order to advance its institutionalization as national programme with increasing financial resources. |
| Evaluation of the programme: Design and implementation of Gender Equity Policies in the Ministry of Education (Institutional Programme evaluation) | It is one of the first evaluations in the LAC region regarding VAW prevention and GE in the educational sector. Systematize and contextualize the progress of the programme and its contribution to advance gender mainstreaming in the national educational policy. | High: necessary conditions in place to assess key aspects of the programme. | - Disseminate the evaluation findings among stakeholders, in order to improve the design, implementation and follow-up of the overall programme. - Reorient the objectives of the programme accordingly with the assessment of the current social context in the country. - Provide evidence to improve the design and implementation of the Gender Violence Guidance, Attention and Prevention Module. - Provide key recommendations to advance the institutionalization of the programme in the Ministry of Education. |
| Evaluation of the UN Women-Country Strategy and AWP (analysis of lessons learned and best practices) (Ex-post evaluation) | Evaluate the compliance and impact of the first overall Country Strategy 2012-2013. Identify areas of opportunity and improvement, as well as the lessons learned and good practices, to be provided as inputs for future exercises and South-South cooperation. | High: necessary conditions in place to assess key aspects of the first Country Strategy’s results | - Improve UN Women-CO decision-making at country level and future programming based on the evidence, lessons learned, best practices and innovative strategies identified throughout the execution of the first Country Strategy. |