MONITORING, EVALUATION AND RESEARCH PLAN

El Salvador CO 2022-2026

Monitoring and Research Plan

| Activity |  | Partners and stakeholders |  |  | Planned Dates (Month and year of start and end) |  | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |  |  |
| Monitoring Gender mainstreaming in the implementation of the UNSDCF and UNCT SWAP |  | Project coordinator-program specialist |  |  | Quarterly |  | staff time | n/a |
| Submission of inputs for quarterly and Annual Report |  | Project coordinator-program specialist |  |  | Quarterly / Annually |  | staff time | n/a |
| Financial Reports |  | Project coordinator-program specialist |  |  | Monthly / Quarterly / Annually |  | staff time | n/a |
| Submission of corporate quarterly and annual progress report in RMS,. |  | Project coordinator-program specialist |  |  | Annually |  | staff time | n/a |
| Preparation of donor report |  | Project coordinator-program specialist |  |  | Three to Six months after the end of the project |  | staff time | n/a |
| Conduct regular reviews of the work, plan e.g. Weekly staff meetings, operations meetings and quarterly reviews and to ensure implementation of follow up actions |  | UN Women |  |  | quarterly |  | Staff time | n/a |
| RESEARCH |  |  |  |  |  |  |  |  |
| Actualization of Country Gender Equality Profile (CGEP) |  | Program specialist |  |  | Q2 2024 |  | staff time | tbd |
| Update of the UN Common Country Analysis |  | UN Women |  |  | 2023/2024 |  | staff time | tbd |
| Development of Knowledge Management products on Governance, leadership and Political participation of women |  | Un women with key actors |  |  | anually |  | staff time | tbd |
| Development of knowledge Management products on Elimination of violence against women |  | UN Women with Key actors |  |  | anually |  | Staff time | tbd |
| Development of knowledge Management Products on Women, Peace and Security |  | UN Women with key actors |  |  | anually |  | Staff time | tbd |
| development of knowledge Management Products on Climate ChangeUN Women with Key actors | anually |  | Staff time | tbd |  |

Evaluation Plan

| Evaluation name | Manda tory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| final Evaluation of SPOTLIGHT INITIATIVE | Y | SP Outcome 4 | SNs/AWPs Outcome 4 | El Salvador | Americas and the Caribbean |  |  | Q2, Q3 2022 | 40,000 non core | pending |  |
| Mid term evaluation | y | NA | Oeef and drf | El salvador |  |  | ISDEMU, CSO, government | Q 3 2024 | 5,000 | pending |  |
| Final Evaluation of the SN | Y | NA | OEEF | El Salvador | LAC | n | ISDEMU, CSO, government counterparts | -Q3 2025 | 25,000 | pending |  |
| Evaluation in which the Office participates |  |  |  |  |  |  |  |  |  |  |  |
| Final evaluation of UNSDCF | Y | UNSDCF Outcome | DRF | Office of the Resident COordinator ELS |  | Y UNCT | Government counterparts | Q1 2026 |  | pending |  |
| Final Evaluation of MELyt | Y | UNSDCF pillar 2, SP Outcome 2, SDG 1s2s5 and 8 |  | Panama | ELS, HOnduras and Guatemala | N | Multicountry Goverment | 2025 | tbd | pendinng |  |

## Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Final evaluation of the Spotlight Initiative | Relevance of the Subject, Mandatory for the donor | High | Resource Mobilization |
| Final Evaluation o f the Strategic Note 2021-2026 | Relevance of the work | High | Lessons learned |