TEMPLATE – MONITORING, EVALUATION AND RESEARCH PLAN 2022-2025

Name of office

NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities.

- Monitoring and Research Plan 2022-2025

| Activity | UNSDCF Outcome/UN Women SP Outcome | SN Output/Relevant flagship program | Related indicator/KPI (Y/N, Indicator number, how and when) | Data Collection (Y/N, what data, how) | Office and Person in charge | Partners and stakeholders | Planned Dates (Month and year of start and end) | Donors Involved | Budget |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |  |  |  |  |
| Monthly monitoring of status of AWP | UNSDCF Outcome 2.1 and 3.1 | Serbia BWP |  | N | Serbia PP Project Officers | Coordination Body for Gender Equality, Ministry of Finance, Ministry of European Integration, Ministry of Interior, Provincial Secretariat for Demography, Social Welfare and Gender Equality, Provincial Secretariat for Finance, State Audit Institution, Ministry of Justice, selected NGOs, LSGs | Monthly | N/A | N/A | N/A |
| Annual Review of implementation of BWP | UNSDCF Outcome 2.1 and 3.1 | Serbia BWP |  | N | Serbia PP Project Officers | Coordination Body for Gender Equality, Ministry of Finance, Ministry of European Integration, Ministry of Interior, Provincial Secretariat for Demography, Social Welfare and Gender Equality, Provincial Secretariat for Finance, State Audit Institution, Ministry of Justice, selected NGOs, LSGs | Annually | N/A | N/A | N/A |
| Monitoring of delivery as per AWP and Project Plans | UNSDCF Outcome 2.1 and 3.1 | Serbia BWP |  | N | Serbia PP Project Officers | Coordination Body for Gender Equality, Ministry of Finance, Ministry of European Integration, Ministry of Interior, Provincial Secretariat for Demography, Social Welfare and Gender Equality, Provincial Secretariat for Finance, State Audit Institution, Ministry of Justice, selected NGOs, LSGs | Monthly | N/A | N/A | N/A |
| Regular update in the online RBM system | UNDSCF Outcome 2.1 and 3.1 | All |  |  | Serbia PP Project Officers and Coordination Associate |  | Quarterly | N/A | N/A | N/A |
| Preparation and submission of annual narrative and financial report for the project Support to Priority Actions for Gender Equality | UNDSCF Outcome 2.1 | 1.1.1. |  |  | Serbia PP Project Officers Aleksandra Miletic, Jelena Sekulic Nedeljkovic and Nevena Marceta | Coordination Body for Gender Equality, Ministry of European Integration, selected NGOs | Annually | European Union |  |  |
| Preparation and submission of final narrative and financial report for the UN Joint Project on Integrated response to violence against women and girls in Serbia III | UNDSCF Outcome 2.1 | 3.1.1 |  |  | Serbia PP Project Officer Andrijana Covic | Coordination Body for Gender Equality, Ministry of Interior, Ministry of Justice, Ministry of Labor, Employment, Veteran and Social Affairs, Ministry of Health, Ministry of Education, Science and Technological Development, Ministry of Youth and Sports, Commissioner for Protection of Equality, Provincial Secretariat for Social Protection, Demography and Gender Equality, civil society organizations and media. |  | SIDA |  |  |
| Preparation and submission of inputs for annual narrative and financial report for the Serbia component of the Regional EVAW Project Implementing Norms Changing Minds | UNDSCF Outcome 2.1 | 3.1.2 |  |  | Serbia PP Technical Project Analyst Natalija Ostojic | Coordination Body for Gender Equality, selected NGOs |  | European Union |  |  |
| Preparation and submission of inputs for final narrative and financial report for the project Improved Safety of Women in Serbia | UNDSCF Outcome 2.1 | 3.1.3 |  |  | Project Officer Ljiljana Loncar | Ministry of Interior (formal partner), Ministry of Justice, Local Self-Governments, Women Parliamentary Network, media houses and associations, Women CSOs | End of 2023 | Government of Norway | N/A | N/A |
| Preparation and submission of inputs for annual narrative and financial report for the Serbia component of the Regional Gender Responsive Budgeting Project | UNDSCF Outcome 3.1 | 1.1.1 |  |  | Serbia PP GRB Programme Coordinator Olja Jankovic Lekovic | Ministry of Finance, Provincial Secretariat of Finance, State Audit Institution, LSGs, direct budget users |  | SIDA |  |  |
| Conduct monitoring missions to RP and partners | UNDSCF Outcome 2.1 and 3.1 | All |  |  | Project Officers | Provincial Secretariat for Demography, Social Welfare and Gender Equality, municipalities, UNTF to EVAW grantees, Coordination Body for Gender Equality and selected government institutions selected NGOs | Quarterly |  |  |  |
| Monitoring the work of SOS mobile application | EVAW | EVAW |  |  | Natalija Ostojic | SOS Network of Vojvodina | 01/22-06/22 | EC | Non-core | $5,000 |
| Monitoring of Consultants and Contactors as per contracts and deliverables timelines | UNDSCF Outcome 2.1 and 3.1 | All outputs |  |  | Project Officers and other staff as applicable |  | Monthly |  |  |  |
| Monitoring of delivery rates | UNDSCF Outcome 2.1 and 3.1 | All outputs |  |  | Project Officers and Operations Officer |  | Monthly |  |  |  |
| Preparation of the Annual Progress Report against the Gender Scorecard Action Plan and Re-Assessment of Indicators |  |  |  |  | Serbia GTG, IAT and UN Women Serbia Coordination Associate Zorana Kataranovski as Coordinator |  | Annually |  |  |  |
| Preparation of the Gender Thematic Group Reports for the UNCT Annual Report |  |  |  |  | Serbia GTG and UN Women Serbia Coordination Associate Zorana Kataranovski |  | Annually |  |  |  |
| RESEARCH |  |  |  |  |  |  |  |  |  |  |
| The implementation of the Law on Free Legal Aid with regards to VAWG survivors and their access to free legal aid | EVAW | EVAW |  |  | Natalija Ostojic | Association Fenomena | 09/21 – 05/22 | EC | Non-core | $9,000 |
| National survey on VAGW in public spaces | UNDSCF Outcome 3.1. | Output 3.1.4. |  |  | Vladimir Vukićević | Coordination Body for Gender Equality, Ministry of Labor, Employment, Veteran and Social Affairs, selected local self-governments, selected NGOs | 12/21 - 05/22 | FCDO | Non-core | £23,500 |
| Guide to implementing Women safety audit tool - for local governments and women's organizations | UNDSCF Outcome 3.1. | Output 3.1.4. |  |  | Vladimir Vukićević | Local self-government units | June 2023 | FCDO | Non-core | £ 3,013.29 |
| Shadow Report to CEDAW | UNDSCF Outcome 3.1 | Output 3.1.2 |  |  | Natalija Ostojic | SOS Network Vojvodina |  | EC | Non-Core |  |
| Study on Women Entrepreneurs | UNSDCF Outcome 3.1 | 1.1.1 | SRB_D_1.1.1F |  | Aleksandra Miletic | SeCONS | October 2021- October 2022 | EC | Non-Core | 35000$ |
| Guidelines and Recommendations for ethical and non discriminative reporting about violence against women and girls (VAWG) in online sphere | UNDSCF Outcome 3.1 | Output 3.1.3 |  |  | Ljiljana Lončar | Belgrade Center for Human Rights | April- October 2022 | Norwegian Embassy | Non- Core | 9.000$ |
| Situational Analysis on the rights of persons with disabilities |  |  |  |  | Natalija Ostojic | Government, DPOs, UN agencies | 15 December 2022 – 15 April 2023 | PRPD MPTF | Non-core | 25,000$ |

- Evaluation Plan 2022-2025

| Evaluation name | Mandatory (Y/N) | UNSDCF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/ Relevant flagship program | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluation of the Improved Safety of Women in Serbia Project | Y | UNDSCF Outcome 2.1 |  | Serbia PP, Project Officer Ljiljana Loncar | Serbia | N | second half of 2023 | Norwegian Embassy | 50,000.00 USD | Not initiated |  |  |
| Final evaluation of “Ending violence against women in the Western Balkans and Turkey: Implementing norms, changing minds” Phase II. Project ends in July 2023 | Not for EC | EVAW | EVAW | ECA RO Yolanda Iriarte | ECA + Albania, BiH, North Macedonia, Montenegro, Kosovo, Serbia and Turkey | CSOs, women’s rights organizations (beneficiaries); others – Ministries of Social Affairs and Labours Policies, National Machineries for the Advancement of Women; Ombudsperson offices, EVAW referral system/mechanisms, Justice Sector Stakeholders. | 01/23-07/23 | EC | Max $80,000 | Not initiated |  |  |
| Evaluation of the Safeguarding women and girls in Serbia Project (Project ending October 2023) | Y | EVAW | EVAW | Serbia PP, Project Officer Vladimir Vukicevic | Serbia |  | second half of 2023 | Foreign & Commonwealth Off | 10000$ | Not initiated |  |  |
| Evaluation of the project “Integrated response to violence against women and girls in Vojvodina III” implemented by PSSPDGE | N | EVAW | EVAW | Serbia PP, Project officer Andrijana Covic | Serbia | PSSPDGE | December 2022 | UNDP | 4,000$ | Not initiated |  |  |
| Evaluation of the project Support to Priority Actions in Serbia (GEF II). Project ends in February 2024 | Y | UNDSCF Outcome 2.1 |  | Serbia PP, Project Officers Jelena Sekulic Nedeljkovic, Aleksandra Miletic, Nevena Marceta | Serbia | N | June 2023-February 2024 | EU | 30,000 USD | Not initiated |  |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| ECA Evaluation of UN Women's contribution to Capacity Development of partners | Y | N/A | N/A | ECA RO Ayca Atabey | ECA/All countries in the region | Country Office staff, government counterparts - institutions and independent bodies, selected CSOs, women's organizations, entrepreneurs, academia | July – December 2022 | N/A | N/A | Ongoing |  |  |
| Final Evaluation of the UNJP “Integrated response to violence against women and girls in Serbia III” | Y | EVAW | EVAW | UNDP | Serbia | UNDP, UNFPA, UNICEF, national partners | March-May 2023 | SIDA | 10,000$ | Not initiated |  |  |

Please fill out a separate row for each evaluation.

Outcomes contributing to the SDGs as per the Strategic Plan