## Sheet1
EVALUATION PLAN 2025 - 2030 for SIERRA LEONE COUNTRY OFFICE
Instructions:
1. 1. This template includes 1 mandatory evaluation (Country Portfolio Evaluation) which is required at least every second Strategic Note cycle, but recommended for every cycle. ONLY REMOVE IT IF YOU COMPLETED A CPE IN THE PREVIOUS STRATEGIC NOTE CYCLE and do not plan to complete a CPE in the current cycle. Also, note that one CPE per Strategic Note cycle is required if monitoring and audit information points to a significant shift in the programming context or a significant increase in the level of risk. (e.g., contextual risks such as political or civil country risk, risk related to programme/project delivery or donor relationship management risk). 2. Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real life activities. 3. Please fill out separate rows for each activity
Guidance: 1. Coverage norms: To ensure appropriate evaluation coverage, IES recommends between two to four country thematic evaluations, component evaluations, or project evaluations, over the Strategic Note cycle. 2. Criteria for prioritizing evaluations: The eight parameters for prioritizing evaluations are: 1) relevance of the subject; 2) risk associated with the intervention; 3) significant investment (more than 1/3 of the country portfolio); 4) demands for accountability from stakeholders; 5) potential for replication and scaling-up; 6) potential for joint of UNSDCF evaluation; 7) feasibility for implementing evaluation; 8) knowledge gap. 3. Regional Evaluation Specialists engagement: RES should be consulted when selecting evaluations and drafting these plans to get feedback, before the quality assurance process.
Evaluation name | Mandatory (Y/N) (Please indicate whether the planned evaluation is required as part of corporate guidance or donor requirements). | Purpose of evaluation (Please explain whether and how the planned evaluation will contribute to learning, accountability, and decision-making). | UN Women SP Thematic areas | SDG | Relevant flagship program or signature initiatives (SIs) | Office and Person in charge | Region/ country | Joint activity (Y/N, indicate partners) | Type (Please indicate whether the planned evaluation is a midline, final/summative, or quantitative impact evaluation). | Planned Dates (start-end) | Donors Involved | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks (please also note if this is a new evaluation, not included in the original Strategic Note evaluation plan)
Evaluations in which the office leads
Strategic Note Evaluation / Country Programme Evaluation (CPE) | Y (Corporate Guidance) | SL CO CPE is planned to assess the performance of the Strategic Note 2025 - 2030 (Country Office's portfolio) using OECD DAC criteria | All | All | All | Sierra Leone CO - Abdul Conteh & Baindu Patricia Massaquoi | West Africa Region, Sierra Leone | NO | Final/summative Evalaution | September - December 2030 | All relevant Donors | $50,000, core funds | Pending | Assessing the CO Programme Document
Midterm Evaluation of the country programme document (SN 2025 - 2030) | N | The Midterm Evaluation aims to comprehensively assess the performance of the SN, identify key achievements and gaps, and provide actionable recommendations to enhance the effectiveness and impact of the programme | All | All | All | Sierra Leone CO - Abdul Conteh & Baindu Patricia Massaquoi | West Africa Region, Sierra Leone | NO | Midline Evaluation | September - December 2027 | All relevant Donors | $40,000, core funds | Pending | Assesing the midterm impact, relevance and efficiency of CO programme
Final Evaluation of the ELSIE Peace Operation programme for RSLAF | Y (Donor guidance) | Final Evaluation for Women in Peace Operation Programme to assess the performance of the programme, track results, challenges and lessions learnt using OECD DAC criteria | UN Women SP Impact 4 | SDG 5 | SP Impact 4 (WPS/HA | Sierra Leone CO – Abdul Conteh & Mariama Jusu Koiyia | West Africa Region, Sierra Leone | NO | Final Evalaution | March - June 2027 | ELSIE | $30,000, ELSIE | Pending | This Evaluation will be co led by the Elsie MPTF and UN Women CO
Final Evaluation of the ELSIE Peace Operation programme for Sierra Leone Police | Y (Donor guidance) | Final Evaluation for Women in Peace Operation Programme to assess the performance of the programme, track results, challenges and lessions learnt using OECD DAC criteria | UN Women SP Impact 4 | SDG 5 | SP Impact 4 (WPS/HA | Sierra Leone CO – Abdul Conteh & Mariama Jusu Koiyia | West Africa Region, Sierra Leone | NO | Final Evalaution | TBD | ELSIE | TBD | Pending | This Evaluation will be co led by the Elsie MPTF and UN Women CO
Final Evaluation for PBF/IRF-504: Localizing for change: Positioning women’s Civil Society Organizations for effective implementation of the WPS agenda | Y (Donor guidance) | The main purpose of the final project evaluation is to assess the results of the project interventions and to the extent the PBF support been effective in contributing to women’s leadership and participation in peace and security in Sierra Leone. | UN Women SP Impact 4 | SDG 5, 6 and 16 | SP Impact 4 (WPS/HA | Sierra Leone CO – Abdul Conteh & Mariama Jusu Koiyia | West Africa Region, Sierra Leone | YES, (UNDP, World Vision) | Final Evalaution | March - June 2025 | PBF Secretariat | $50,000, PBF Fund | Pending | The Final evaluation will be lead by SL UN Women with support from the PBF Secretariat
Final Evaluation of Gender Mainstreaming in Local Councils Project - Phase II | Y (Donor guidance) | The Final Evaluation is to assess the performance of the project using the OECD/DAC criteria inline with UN Women Evaluation policy and UNEG ethics and standards | UN Women SP Impact 4 | SDG 5, 6 and 16 | SP Impact 1 (WLEAD) | Sierra Leone CO – Abdul Conteh & Mariama Gbao | West Africa Region, Sierra Leone | YES, (UNDP) | Final Evalaution | Octomber - December 2028 | Iceland | $50,000, Iceland | Pending | The Final evaluation will be lead by SL UN Women with support from Iceland
Evaluations in which the office participates
Final Evaluation of the Spotlight Initiative in Sierra Leone | Y (Donor guidance) | The Final evaluation is to assess the performance of the project using the OECD/DAC criteria inline with UN Women Evaluation policy and UNEG ethics and standards | UN Women SP Impact 3 | SDG 5, 10 and 11 | SP Impact 3 (EVAWG) | Sierra Leone CO – Abdul Conteh & Ella Syl-Macfoy | West Africa Region, Sierra Leone | YES, (UNCT, UNICEF, UNDP, UNFPA) | Final Evalaution | Oct - Dec 2028 | EU | $40,000, EU | Pending | This Evaluation will beco led by the Spotlight Secretariat and CO
Final Evaluation National Unity and Cohension Project - PBF | Y (Donor guidance) | The Final Evaluation is to assess the performance of the project using the OECD/DAC criteria inline with UN Women Evaluation policy and UNEG ethics and standards | UN Women SP Impact 4 | SDG 5 | SP Impact 4 (WPS/HA | Sierra Leone CO – Abdul Conteh & Mariama Jusu Koiyia | West Africa Region, Sierra Leone | YES, (UNDP, UNICEF) | Final Evalaution | Oct - Dec 2027 | PBF | $40,000, PBF | Pending | The Final evaluation will be co-lead by SL UN Women and PBF Secretariat
UNSDCF 2024-2030 Evaluation | Y (Donor guidance) | To evaluate the UNSDCF as per UNSDG guidelines | All | SDG 5 | All IMPACT AREAS | Sierra Leone CO - Abdul Conteh & Baindu Patricia Massaquoi | West Africa Region, Sierra Leone | YES (UNCT) | Final Evaluation | Oct - Dec 2030 | All relevant Donors | $ 5,000, Core | Pending | The CO will ensure the inclusion of gender sensitive methodologies in the UNSCDF evaluation as per the previous UNSCDF evaluation