MONITORING, EVALUATION AND RESEARCH PLAN (MERP) 2018

Monitoring 2018

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| 2018 AWP | Routine monitoring of programme portfolio; core and non-core projects (programmatic activities & delivery) | Programme Manager and/or thematic responsible | Internal staff, implementing partners/responsible parties | 1/2018-12/2018 | n/a | n/a |
| CO 2017 Annual Report | Update RMS | Programme Analyst | Focal point per Output in RMS | 01/2018 | n/a | n/a |
| Quarterly monitoring of activities | Update RMS | Programme Analyst | Focal point per Output in RMS | 3/2018 6/2018 9/2018 12/2018 | n/a | n/a |
| Donor reporting | Prepare and present narrative and financial reports to donor and update the information in DAMS | Programme Analyst | Internal Staff: Programme staff assigned to the projects and Programme and Finance Associate Donors: Itaipú Binational and EU | 05/06/2018 (Final Narrative & Provisional Reports) – DAMS ID: 11615 - Itaipú 21/08/2018 (Interim Narrative and Financial Reports) DAMS ID: 12171 – EU | n/a | n/a |

Research Plan 2018

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Publication of the Economic empowerment of women in vulnerability situations through gender mainstreaming in projects and flagship programs of the Secretariat of Social Action (SAS) | UN Women | 3/2018-10/2018 | Core | $2,000 |
| Systematization of the pilot planning experience with gender indicators with the Ministry of Public Works | UN Women | 6/2018-11/2018 | Core | $4,000 |
| Research on the representation of women´s political participation in the media in the electoral process toward the 2018 national elections. | UN Women | 01/2018-07/2018 | Non-core | 7.500 |
| Research on political violence against women in Paraguay. | UN Women | 01/2018-07/2018 | Non-core | 7.500 |
| Research on the electoral results of women in 2018, compared to the previous elections. | UN Women | 01/2018-07/2018 | Non-core | 7.500 |
| Qualitative study on persistent forms and new forms of violence against women and girls. | UN Women | 01/2018-03/2018 | Non-core | 5.000 |
| Publication of the Equal Pay Day update | UN Women | 01/2019-05/2019 | Core | 3.500 |
| Roadmap of the Interinstitutional Committee to implement the Comprehensive Law on VAW. | UN Women | 04/2019-11/2019 | Core | 7.700 |

Evaluation Plan 2018

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stake holders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Country portfolio evaluation | Y | UNDAF Impact 1 and 2 UNDAF Outcomes: 1.1. 1.3. 2.1. SP Goals 1, 2, 3, 6 | PY Strategic Note 2015-2019 | Paraguay CO | LAC Paraguay | N, *Ministry of Women *Secretariat of Planning *Secretariat of Social Action *Ministry of Labor *Gender Secretariat of the Supreme Court of Justice *National Statistics Office *Congressional Commissions on Gender Equality *SDGs Implementation National Commission | *Ministry of Women *Secretariat of Planning | March to September 2018 | $20.000 | Pending |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| Gender-responsive evaluation of the III National Plan for Equal Opportunities between Women and Men (2008-2017), implemented by the Ministry of Women. |  |  |  |  |  |  |  |  |  |  |  |