COLOMBIA COUNTRY OFFICE

MONITORING, EVALUATION AND RESEARCH PLAN 2017-2021

Monitoring 2017-2021

| SN Impact/Outcome | Activity | Responsible staff member | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Source | Amount |
| MONITORING |  |  |  |  |  |  |
| All SN (Impact area 1, 2, 3, 4, and OEEF) | UNDAF 2015-19 mid-term review and periodic reports. Reports on the UNSDCF (UNINFO; Government; etc.) | UNW M&E focal point | RCO, UN Agencies focal points and UNCT | 3rd/4th quarter 2017 and 2019, December 2020, 2021 | Non Core (USAID/Norway) | 2,000 each |
| All SN (Impact area 1, 2, 3, 4, and OEEF) | Mid term-review, annual report, report to new Government and final report on the Cooperation Framework 2015-20 between UN Women and the Government of Colombia. Reports on the new cooperation framework with the Government of Colombia | UNW M&E focal point | Ministry of Foreign Affairs, Key institutional partners of UN Women in Colombia | Mid 2017, Feb 2018, July 2018, December 2018, December 2019, December 2020, 2021 | Non Core (USAID/Norway/FPI stats) | 2,000 each |
| All SN (Impact area 1, 2, 3, 4, and OEEF) | Quarterly monitoring of activities - Progress Reports RMS | UNW M&E focal point | Corporate – CO - Regional Office | Every quarter 2017-2021 | Non Core (USAID/Norway) | $10,000 per year |
| All SN (Impact area 1, 2, 3, 4, and OEEF) | Annual Report AWP | UNW M&E focal point | Corporate - CO - Regional Office | Every December 2017-2020 | Non Core (USAID/Norway) | $5,000 per year |
| Impact area 1, Outcomes 1.3 | Narrative and financial project reports to Donor (Project Women Count) | UNW M&E focal point / Programme Manager | Corporate - CO - Regional Office | 04/2021 and 11/2021 | Non-Core (Sweden) | 2,000 each |
| Impact area 3, Outcomes 3.1 and 3.2. Impact area 4, outcome 4.3 | Narrative and financial project reports to Donor | Project M&E focal point | Corporate - CO - Regional Office | 2017-19: Quarterly financial reports, monthly narrative updates, annual narrative and financial report (every February) | Non-Core (USAID GBV programme and USAID Humanitarian programmes) | $5,000 |
| Impact area 1, 2, 4, Outcomes 4.1 and 4.2. | Narrative and financial project reports to Donor | UNW M&E focal point / Programme Manager | Corporate - CO - Regional Office | 2/2019 and 6/2019, 2/2020, 2/2021, 2/2022 | Non-Core (Sweden new programme) | $5,000 |
| Impact area 4, Outcome 4.3 | Narrative and financial project reports to Donor | M&E focal point / National Programme Officer | Corporate - CO - Regional Office | 5/2018, 12/2018, 6/2019, 12/2019, 11/2020, 12/2020, 11/2021, 12/2021 | Non-Core (Norway) | $8,000 per year |
| Impact area 1, 2, 3, 4. | Other progress reports, Narrative and financial project reports to Donor on projects as per DAMS reporting commitments | UNW M&E focal point / Programme Manager | Corporate - CO - Regional Office | As per DAMS commitments | Non-Core (MPTF, PBF) | $5,000 |

Research Plan 2017-2021

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| RESEARCH |  |  |  |  |
| Knowledge products on women political participation and women economic empowerment at local level. (Case studies from Cauca and Meta) | UN WOMEN - USAID | 1/2017 - 6/2017 | Non-Core (USAID) | $ 40,000 |
| Knowledge products on Women participation in peace building, women and the construction of historical memory and reintegration | UN WOMEN – Government of Sweden | 1/2017 - 6/2017, 2018 | Non-Core (Sweden) | $40,000 |
| Implementation of activities scheduled in the national Knowledge Management Strategy | UN WOMEN | 1/2017 - 12/2017 1/2018 - 12/2018 1/2019 - 12/2019 1/2020 - 12/2020 2021 | Core and Non-Core | $10,000 per year |
| Knowledge products to promote women's leadership and participations in decision-making processes at local, municipal, regional and national level in Colombia | UN WOMEN | 6/2017 - 12/2017 1/2018 - 12/2018 1/2019 - 12/2019 1/2020 - 12/2020 2021 | Non-Core (USAID) | $15,000 per year |
| Knowledge products to contribute to eradicate all forms of violence against women and girls in Colombia | UN WOMEN | 6/2017 - 12/2017 1/2018 - 12/2018 1/2019 - 12/2019 1/2020 - 12/2020 2021 | Non-Core (USAID) | $15,000 per year |
| Knowledge products to promote women's participation and leadership in peace agreements’ implementation, reintegration, post-conflict and natural disasters, including KM activities and products led by the Technical Secretariat for competitive funding for civil society (WPHF, Norway) | UN WOMEN | 6/2017 - 12/2017 1/2018 - 12/2018 1/2019 - 12/2019 1/2020 - 12/2020 2021 | Non-Core (Sweden) | $20,000 per year |
| Women and men: gender gaps in colombia (gender profile national) y other knowledge products FPI Women Count gender profile Nariño, Cauca, Meta and Antioquia | UN Women with DANE, CPEM and Local governments | 11 - 12/2020 (Gender profile national, Nariño and Cauca) 05 - 10 – 11/2021 (Gender profile national, Meta and Antioquia) | Non-core (Sweden) FPI Women Count | 40,0000 |
| Care times: the data on inequality, FPI Women Count. | UN Women with DANE | 07/ 2020 | Non-core (Sweden) FPI Women Count | 20,000 |
| Ten-year analysis and trends of gender related killings of women and feminicides in Colombia, FPI Women Count. | UN Women | 06/2021 | Non-core (Sweden) FPI Women Count | 15,000 |
| Quantitative data collection: Quantitative endline and Tolerance to GBV study – USAID GBV programme COVID surveys | UN Women | 10/20 – 2/21 (Tolerance to GBV study) 10/20-1/21 (Covid survey) | Non-core USAID FPI Women Count | 130,000 |

Evaluation Plan 2017-2021

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Final Evaluation SWEDEN Project: Women’s citizenship for peace, justice and development | Y | UN WOMEN Impact 4 | Colombia Impact 4 | Colombia | Colombia | N | Government of Sweden | 11/17-4/18 | 16,000 Non-Core | Finalized | None |
| Mid term Evaluation USAID project: End GBV | Y | UN WOMEN Impact 1 | Colombia Impact 3 | Colombia | Colombia | N | USAID | 11/17-3/18 | 22,000 Non-Core | Finalized | None |
| Final Evaluation USAID project: End GBV | Y | UN WOMEN Impact 1 | Colombia Impact 3 | Colombia | Colombia | N | USAID | 02-21 to 05-21 | 25,000 Non-Core | Pending (draft tor) | None |
| Final Evaluation SN | Y | UN WOMEN SP Goal 1, 2, 3 and 4 | Colombia Entire SN | Colombia | Colombia | N | Main counterparts of the SN | 5-19 to 10-19 | 25,000 Core. | Finalized | None |
| Final internal review USAID project: Gender sensitive response to migration | Y | UN WOMEN SP 4 | Colombia Impact 3 and 4 | Colombia | Colombia | N | USAID | 09-20 to 12-20 | 10,000 Non-Core | Ongoing (internal final review to feed final report) | None |
| Mid-term evaluation safecities (Medellín and other city TBC) | N | UN WOMEN SP 3 | Colombia Impact 3 | Colombia | Colombia | N | AECID and local governments | 3-21 to 7-21 | 15,000 non-core TBM | Pending | Depending on funds availabilitY |
| Final Evaluation PBF GYPI project | Y | UN WOMEN SP 4 | Colombia and 4 | Colombia | Colombia | N | PBF GYPI | 09-20 to 12-20 | 15,000 Non-Core | Ongoing | None |
| Final evaluation PBF binational programme (joint with UNW Ecuador. Procurement process led by UNW Ecuador) | Y | UN WOMEN SP 4 | Colombia and 4 | Colombia | Colombia | Y | PBF, UNW, UNICEF, UNHCR | 12/20-2/21 | 5,000 non-core (UNW Col part) | Ongoing recruitment | None |
| Final evaluation of Women’s peacebuilders programme (before Thematic evaluation on women human rights defenders) | Y | UN WOMEN SP 4 | Colombia and 4 | Colombia | Colombia | N | Norway | 6-21 to 10/21 | 20,000 Non-core | Pending | None |
| Final evaluation of the new bilateral cooperation framework with the government of Colombia 2021-24 | Y | ALL framework/UNSDCF outcomes | All | Colombia | Colombia | N | MOFA, Main counterparts of the Framework | 2023/24 TBD | 30,000 core | Pending |  |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |
| UNDAF Evaluation | Y | ALL UNDAF AN SP Goal-Outcome | All UNDAF | RCO | Country | Y | SNU APC Ministry of Foreign Affairs | 2019 | 5,000 Core | Finalized |  |
| UNSDCF Final evaluation | Y | ALL UNSDCF outcomes | All UNSDCF | RCO | Country | Y | SNU APC Ministry of Foreign Affairs | 2023 | TBD | Pending |  |

Evaluation justification matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Final Evaluation SWEDEN Project: Women’s citizenship for peace, justice and development | The evaluation of “Women’s citizenship for peace, justice and development” was prioritized based of the tree follow criteria - Relevance. Peace Process between National Government and FARC-EP: The signature of a definitive peace agreement has never been so close. The programme has been developed with the purpose of guaranteeing women’s rights and gender equality in the implementation of: a) the Law that promotes Victims’ Rights within the frame of the existing National Policy for Gender Equality; b) possible peace agreements, including their popular ratification and implementation. - Significant investment. The programme considered a significant investment in relation to the overall office portfolio (4,588,514 USD, 2014-2016), It represents the 38.5% of the non-core available Budget of the AWP 2016. - Demands for accountability from stakeholders. The Embassy of Sweden in Colombia specifically requesting the evaluation in the agreement. | This final evaluation will be conducted at the end of an intervention’s life cycle. It will focus on the assessment of outcome -level results, and also capture lessons learned from the implementation of the intervention | To support the formulation of new programmatic activities and to generate accountability. |
| Mid Term Evaluation USAID project: End GBV | This evaluation was prioritized based of the tree follow criteria - Relevance. The programme contributes to eradicate all forms of violence against women and girls in Colombia, this subject is a key priority of the strategic plan. - Significant investment The programme considered a significant investment in relation to the overall office portfolio (total budget of the programme almost US$ 8 million). - Demands for accountability from stakeholders. USAID as the donor requires a final evaluation of the results is carried out in the project. | This mid term evaluation will be conducted at the end of the first phase of implementation. It will focus on the assessment of outcome -level results, and also capture lessons learned from the implementation of the intervention | To support the formulation of new programmatic activities and to generate accountability. |
| Final Evaluation USAID project: End GBV | This evaluation was prioritized based of the tree follow criteria - Relevance. The programme contributes to eradicate all forms of violence against women and girls in Colombia, this subject is a key priority of the strategic plan. - Significant investment. The programme considered a significant investment in relation to the overall office portfolio (total budget of the programme almost US$ 8 million). - Demands for accountability from stakeholders. USAID as the donor requires a final evaluation of the results is carried out in the project. | This final evaluation will be conducted at the end of an intervention’s life cycle. It will focus on the assessment of outcome -level results, and also capture lessons learned from the implementation of the intervention | To support the formulation of new programmatic activities and to generate accountability. |
| Final Evaluation SN | This evaluation was prioritized based of the tree follow criteria - Relevance. Information from this evaluation will strengthen our support to improve resources allocation for gender equality. The evaluation will also serve as accountability measure to evaluate the Cooperation Framework signed between UNW and the National Government. - Significant investment. The programme in Colombia considered a significant investment in relation to the portfolio of UN Women in the Region. - Demands for accountability from stakeholders. UN Women and the Colombian Government require a final evaluation of the results to be carried out at the end of implementation period. | Results and information gathered will allow us to evaluate the pertinence of our intervention. Also, the results of this evaluation will be an evaluation of an organization’s capacity to efficiently manage its assets for the achievements of results and its capacity for innovation and change. | Reorient our interventions at country level and to generate accountability. |

Please see Guidance on Decentralized Evaluations, link.

Please fill out a separate row for each evaluation.