MDA EVALUATION PLAN 2014-2017

| Evaluation name | Mandatory? (Y/N) | UNPF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Programme Budget | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |
| WIP, Final evaluation | Y | GLO SP 2.2.1 UNPF 2.1 | MDA AWP DR111, DR112 | MDA | MDA | Y, UNDP | n/a | Q4 2016 | US$2.9 M (1.9M UN Women part | US$40,000 CS | On going | To be agreed with partners that only final evaluation to be conducted and a mid-term review in 2015 |
| Country Portfolio Evaluation/ SN 2014-2017 | y | Strategic Plan | All outcomes | MDA | MDA | N | MLSFP, LPAs, CPAs, donors | Q4 2016 | US$20,0 th. (planned) | US$20 000 IB for evaluation US$20 000 CS | Procurement ongoing | The results expected in January 2017 |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |
| JILDP II evaluation | N | GLO SP211 GLO SP511 UNPF 2.1 | MDA AWP DR211 DR511 | MDA | MDA | Y (UNDP) | UNDP, CPAs & LPAs | Q3 2015 | US$0,5 M | US$ 10,000 (contribution from CS to UNDP) | closed | Joint UN Women/ UNDP |
| Labour Migration Program | N | GLO SP: 2.1.1 UNPF 2.1 | MDA AWP DR211 | MDA | MDA | N | BDR, MLSPF, MoEc, Migration Bureau, MoInt | Q3 2015 | US$0,5 M | US$ 0 CS | Ongoing | Data collection mission was in August 2016 |
| Regional Gender Responsive Budgeting | N | GLO SP 511 UNPF 2.4 | MDA AWP DR5111 | MDA | MDA/ALB/BiH | Y | MoF, MLSPF, ASEM | Q3 2016 | US$0,19 M | US$10,000 | Ongoing | Preliminary findings was presented to EMG. |