UPDATED ECUADOR’S MONITORING, EVALUATION AND RESEARCH PLAN 2015-2018

Monitoring and Research Plan 2015-2018

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Quarterly review of projects: project processes and advance; technical assistance process; consultant advance. | Local Governments: Azuay, Cuenca and Quito Technical Assistance to Central Government (National Assembly, Ministries of Social Inclusion; Ministry of Justice) Civil society organizations (organizations will be defined in competitive processes) | March 2015, 2016, 2017 June 2015, 2016, 2017 September 2016, 2017 November 2016, 2017 | Core | (included in staff duties) |
| Field visits and interviews | Local processes: Azuay, Cuenca | February 2018 May 2018 October 2018 | Core Non core AECID Non Core Ayuntamiento Madrid | (included in staff duties) 1.000 2.000 |
| Completion of Results Management System |  | January: 2015, 2016, 2017 and 2018 March: 2015, 2016, 2017 and 2018 June: 2015, 2016, 2017 and 2018 September: 2015, 2016, 2017 and 2018 November: 2015, 2016, 2017 and 2018 | Core | (included in staff duties) |
| Month end closure completion |  | The five first days of every month | Core | (included in staff duties) |
| Country office programme and operations quarterly report completion |  | Quarterly | Core | (included in staff duties) |
| UN Women Annual report |  | Annually | Core | (included in staff duties) |
| Mid-term Review of Ecuador’s Strategic Note | AWP Ecuador CO Partners | July – Sept 2017 | Core | 15.000 |
| RESEARCH |  |  |  |  |
| Study about Ecuadorian women’s conditions 1995-2014 |  | November 2014 – December 2015 | Core | 10.000 |

Evaluation Plan 2015-2018

| Evaluation name | Mandatory? (Y/N) | UNDAF Outcome/ UN Women SP Goal, Outcome | Country/ MCO/ RO AWP Output | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Key Stakeholders | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of the gender budget classifier | N | DRF 5 | Ecuador’s AWP 5.2 | Ecuador CO | Americas and Caribbean/Ecuador | Y Ministry of Finance | Sectorial Ministries | November 2015 – JanurayJanuary 2016 | 26.096 Core | Completed |  |
| Evaluation of the Safe Cities Programme | Y | DRF 3 | Ecuador’s AWP 3.1 | Ecuador CO | Americas and Caribbean/Ecuador | Y Municipality of Quito | Grassroots women’ s organizations Community leaders | Oct-Dec 2017 | 10.000 Non-core | Initiated |  |
| Evaluation of the Project on Economic Empowerment funded by CAF | Y | DRF 3 | Ecuador’s AWP 2.2. | Ecuador CO | Americas and Caribbean/Ecuador | Y Provincial Governemnt of Loja | Provincial Governemnt of Loja University of Cuenca | Nov – Dec 2017 | 15.000 | Initiated |  |

# Evaluation Justification Matrix

| List of selected evaluation | Criteria used for the selection | Potential evaluability | Intended use of evaluation findings |
| --- | --- | --- | --- |
| Evaluation of the gender budget classifier | Relevance: Information from this evaluation will strengthen our support to improve resources allocation for gender equality | The gender budget classifier has been used for 4 years. Information allows to identify gaps and issues to be improved. | Improve budget classifier’s items and methodology. Identify capacity building gaps to work with ministries. |
| Evaluation of the Safe Cities Programme | Relevance: This evaluation will allow us to see results achieved within the programme and identify good practices related to reducing violence against women in public spaces. | The Programme will end its implementation. Baseline collection was rigorous, then we have high quality information to assess targets achievements | Identify good practices on Safe Cities for women and girls to be replicated. |
| Evaluation of the Project on Economic Empowerment funded by CAF | The project includes a mandatory evaluation of the project to see the results achieved in impoving women’s income generation and also the UN Women model of intervention | The project has indicators that can be easily evaluated and the intervention was defined according a base line developed at the beginning of the project | Develop a model on economic empowerment for local governments |

Please fill out a separate row for each evaluation.