Evaluation Plan 2014-2017

| Title | Type | Goals | Relevant Country/AWP Outcome | Office to Manage the Evaluation | Region/ Country/ies | Joint Evaluation (Yes/No) | Key Stake holders | Planned Initiation Date | Planned End Date | Programme Budget(US$) | Planned Evaluation Budget | Status | Mgmt. Resp | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluations managed by the office |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation of the implementation of 2012-2013 strategic plan | Final Program Evaluation | - G1 - G2 - G3 - G4 - OEEF |  | UN Women/ Cameroon | WCARO/ Cameroon | No | Government, UN agencies | 1st october | 31st Nov. | 1 071 897 | 10 000 | Planned | No | The plan is no more in implementation stage |
| Evaluation of the joint project on Gender base Violence | Final Program Evaluation | - G1 |  | UN Women/ Cameroon | WCARO/ Cameroon | Yes | MINPROFF UNFPA, UNICEF, WHO, HCR, UNW, UNAIDS | July 2017 | Sept. 2017 | 9 394 403 | N/core 50,000 | Planned | No | 2014 is the first of the 4 years project duration |
| Evaluation of the joint project on women’s economic empowerment | Final project Evaluation | - G2 |  | UN Women/ Cameroon | WCARO/ Cameroon | Yes | MINCOMMERCE MINADER MINEPIA MINPROFF | July 2017 | Sept. 2017 | 18 802 500 | N/core 50,000 | Planned | No | 2014 is the first of the 4 years project duration |
| Evaluation of 2014-2017 strategic plan implementation | Final Evaluation | - G1 - G2 - G3 - G4 - OEEF |  | UN Women/ Cameroon | WCARO/ Cameroon | Yes | Ministries CTD CSO UNS | August 2017 | Oct 2017 | 25 167 159 | Core 50,000 | Planned | No | 2014 is the first of the 4 years project duration |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Joint H4+ Project evaluation | Final Evaluation | - G1 |  | UNICEF Cameroon | WCARO/ Cameroon | Yes/UNS | UN WOMEN WHO ONUSIDA UNFPA UNICEF BIRD | Oct. 2015 | Dec. 2015 | 609 000 | N/core 20,000 | Planned | No | 2014 is the first of the 2.5 years project duration |
| Evaluation of the inclusion of gender within UNDAF; score card | Final Evaluation | - G1 - G2 - G3 - G4 |  | UN Coordination | WCARO/ Cameroon | Yes NUS | Coordination, UNGTG | July 2016 | Oct 2016 | 685 776 784 | N/core 20,000 | Planned | No | 2017 will be the final year of UNDAF’s strategic plan implementation |