MONITORING, EVALUATION AND RESEARCH PLAN 2020-2024 
UN Women LIBERIA
NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real-life activities.

i. Monitoring and Research Plan 2020-2024

	Activity
	Partners and stakeholders
	Planned Dates (Month and year of start and end)
	Budget

	
	
	
	Source
	Amount

	MONITORING

	Coordinate and co-lead the Gender Thematic Group (GTG)
	UN Women, UN GTG
	Quarterly
	Staff time
	

	Draft and publish the UN Women Liberia annual reports
	UN Women Liberia
	annually - 2020, 2021, 2022, 2023, 2024
	Staff time
	

	Preparation of the Quarterly Monitoring Reports and Donor reports
	UN Women Liberia
	Quarterly
	Staff Time
	0

	Mid-term internal review of the AWP
	UN Women Liberia
	2020, 2021, 2022, 2023
	Core 
	50,000

	Conduct regular reviews of the work plan, e.g. weekly staff meetings, joint program & operations meetings and quarterly/bi-annual reviews, and to ensure implementation of follow up actions
	UN Women Liberia
	Each week/quarter
	Staff Time
	0

	Track spending, generate delivery reports and Monitor expenditure on a monthly basis and prepare delivery acceleration plans where necessary
	UN Women
	Quarterly
	Staff Time
	0

	On-field mission to project implementation sites
	UN Women
	Quarterly
	Project funds
	80,000

	UNCT joint on-field monitoring missions
	UNCT LIBERIA
	2020 -2024
	RCO funds
	20,000

	UN agency (UNCT) coordination meetings (Program Committee, M&E groups, etc.)
	UNCT LIBERIA
	Quarterly
	Core
	20,000

	Liberia Gender Profile
	UN Women Liberia
	2020
	Core
	$30,000

	WPEL Project Mid-term review 
	UN Women Regional Office
	January 2020
	Project Funds
	N/A

	RESEARCH

	Situation Analysis on Governance, leadership and Political Participation of Women
	UN Women Liberia
	2021
	Project funds
	$10,000

	 Situational Analysis  on Women Economic Empowerment 
	UN Women Liberia 
	2021
	Project funds
	$10,000

	EVAW : An Analysis of The Obstacles Impeding The Prevention of Sexual and Gender Based Violence in Liberia (2013 – 2018)
	UN Women Liberia, GoL, CSOs
	2020
	Project funds
	$10,000

	WEE (OEEF)
1. Pilot the ‘Women’s Empowerment in Agriculture Index’ (WEAI) for rural gender equality – October 2020
2. Research on the status of implementation of the National Social Protection Policy and Strategy, particularly for the impact on women – June 2021
3. Research on the status of women’s unpaid care work in Liberia – September 2022
4. Research on the status of Women’s Access to Finance: VSLAs and Orange Money – March 2020

	UN Women Liberia
	
1. October 2020
2. June 2021
3. September 2022
4.  March 2020
	
1. OEEF
2. SN Proj
3. JPRWEE
4. BfW
	
1. $10,000
2. $15,000
3. $10,000
4. $20,000

	Baseline study  of the Joint Project Sustaining Peace and Reconciliation through Strengthening Land Governance and Dispute Resolution Mechanisms

	UN Women Liberia
	 January 2020-March 2020
	LMPTF 
	USD 42,000

	Development of Liberia Gender Country Profile
	UN Women Liberia
	Second Quarter 2021
	TBM
	USD 100,000


ii. Evaluation Plan 2020-2024[footnoteRef:1] [1:  Please fill out a separate row for each evaluation.  ] 

	Evaluation name
	Mandatory?
(Y/N)
	UNSCDF Outcome/ UN Women SP Outcome and relevant SDGs[footnoteRef:2] [2:  Outcomes contributing to the SDGs as per the Strategic Plan ] 

	SN Output/Relevant flagship program
	Office in charge
	Region/ country
	Joint activity
(Y/ N, indicate partners)
	Planned Dates
(start-end)
	Budget (US$) / Sources of Funding
	Status (pending/ initiated/ ongoing/ completed)
	Remarks

	

	End-Term Evaluation of  Women Economic Empowerment WEE:
1. JPRWEE
2. Buy from women (BfW)
	Y
	UNSCDF 2020-2024 

	SN Output Cluster 3
	UN Women Liberia
	Liberia
	1. Y- JPRWEE is a joint  Evaluation
2. N
	1. JPRWEE (2021)
2. BfW 2022
	1. USD 50000.00
2. USD 25000.00
	Pending
	Bfw is UNW own initiative and will be managed by UN Women

	End-Term Evaluation of 2 programmes of  EVAWG:
1. SGBV Joint Programme
2. Spotlight Initiative
	Y
	UNSCDF 2020-2024
	SN Output Cluster 3
	UN Women Liberia
	Liberia
	Y
	1- Jan- 2020
2-To be decided by the spotlight initiative secretariate

	1- USD 67349.00
2- TBD be Spotlight initiative secretariate
	1- Ongoing 
2-Pending 

	The planning as started in November 2019, following donors approval of the proposal and budget of the end term evaluation of the programme. 

	End-Term Evaluation of Women Political Participation and Leadership  WPPL
	Y
	UNSDCF (2020-2024)
	SN Output Cluster 3
	UN Women Liberia
	Liberia
	Y
	2021-2022 WPPL

	It is from Non core available will be decided by the donor
	Pending (CO will start the preparation on Donor’s directive) 
	This  WPPL evaluation will be supported by the Donor (Govt of Canada) it is not funded under the SN 2020-24

	End-Term Evaluation of 3 projects under WPS:
A. PBF 
1-Advancing implementation of UNSCRs on WPS” through legislative reforms and civic Engagemnet.
B. LPMTF  
2-Sustaiing Peace and Reconcilation through strengthening land Governance and dispute resolution mechanisms.
3- Advanicing Reconcilation through legislative reforms and civic Engagemnet. 
	Y
	UNSDCF (2020-2024
	SN Output Cluster 3
	UN Women Liberia
	Liberia 
	Y (UNDP, OHCHR, WFP and UNFPA)
	1. Jul  2021
2. Jan 2023
3. Jul  2021

	These are the joint projects and these evaluations will be co funded by al the implementing agencies. 
	Pending 
	

	Mid-Term Evaluation of the EU/UN Spotlight Initiative
	Y
	UNDAF 2020-2024 
	SN Output Cluster 3
	UN Women Liberia
	Liberia
	Y
(to be done by spotlight initiative secretariate)
	June 2020

	USD 74,037.5
	Pending
	

	Liberia Country Portfolio Evaluation (SN 2020-2024)
	Y
	UN Women SP OEEF Output 3
	SN Output Cluster?
	UN Women Liberia
	Liberia
	N
	Prepatory work will be done in 
Jun – Dec 2022
While evaluation will be conducted in Jan- June 2023
	USD 75,000 (TBM)
	Pending
	

	Thematic Evaluation
	N
	UN Women SP OEEF 
	SN Output Cluster 3
	UN Women Liberia
	Liberia
	N
	2024
	[bookmark: _GoBack]USD 10,000 (TBM)
	Pending
	To be carried out on of one of the primary strategic/outcome areas of work that comprises one-third or more of the portfolio

	Evaluations in which the office participates

	Annual joint-review of the UNSCDF
	Y
	UNSCDF 2020-2024 
	SN Output Cluster 3
	UN Women/
liberia
	WCARO / liberia
	Y, 
UNCT;
Government counterparts
	2020 - 2024
	USD 10, 000, UNCT / RC funds
	Pending
	

	Gender Score Card Mid-Term review
	Y
	UNSCDF 2020-2024 
	SN Output Cluster 3
	UN Women/
Liberia
	WCARO / Liberia
	Y, UNDP;
Government counterparts
	2022
	USD 25, 000, UN Women Core funds
	Pending
	

	Final Evaluation of 2020 2024 UNSCDF
	Y
	UNSCDF 2020-2024
	SN Output cluster 3
	UN Women/
Liberia
	WCARO / Liberia
	Y,  
UNCT;
Government counterparts
	Jan. - June 2024

	 UNCT/RC funds
	Pending
	UNWLR will be involved as participatory member but not be taking lead at all.





