MONITORING, EVALUATION AND RESEARCH PLAN 2020-2024

UN Women LIBERIA

NOTE: Examples have been included below to illustrate how to complete each column; they are not meant to be accurate to real-life activities.

- Monitoring and Research Plan 2020-2024

| Activity | Partners and stakeholders | Planned Dates (Month and year of start and end) | Budget |  |
| --- | --- | --- | --- | --- |
|  |  |  | Source | Amount |
| MONITORING |  |  |  |  |
| Coordinate and co-lead the Gender Thematic Group (GTG) | UN Women, UN GTG | Quarterly | Staff time |  |
| Draft and publish the UN Women Liberia annual reports | UN Women Liberia | annually - 2020, 2021, 2022, 2023, 2024 | Staff time |  |
| Preparation of the Quarterly Monitoring Reports and Donor reports | UN Women Liberia | Quarterly | Staff Time | 0 |
| Mid-term internal review of the AWP | UN Women Liberia | 2020, 2021, 2022, 2023 | Core | 50,000 |
| Conduct regular reviews of the work plan, e.g. weekly staff meetings, joint program & operations meetings and quarterly/bi-annual reviews, and to ensure implementation of follow up actions | UN Women Liberia | Each week/quarter | Staff Time | 0 |
| Track spending, generate delivery reports and Monitor expenditure on a monthly basis and prepare delivery acceleration plans where necessary | UN Women | Quarterly | Staff Time | 0 |
| On-field mission to project implementation sites | UN Women | Quarterly | Project funds | 80,000 |
| UNCT joint on-field monitoring missions | UNCT LIBERIA | 2020 -2024 | RCO funds | 20,000 |
| UN agency (UNCT) coordination meetings (Program Committee, M&E groups, etc.) | UNCT LIBERIA | Quarterly | Core | 20,000 |
| Liberia Gender Profile | UN Women Liberia | 2020 | Core | $30,000 |
| WPEL Project Mid-term review | UN Women Regional Office | January 2020 | Project Funds | N/A |
| RESEARCH |  |  |  |  |
| Situation Analysis on Governance, leadership and Political Participation of Women | UN Women Liberia | 2021 | Project funds | $10,000 |
| Situational Analysis on Women Economic Empowerment | UN Women Liberia | 2021 | Project funds | $10,000 |
| EVAW : An Analysis of The Obstacles Impeding The Prevention of Sexual and Gender Based Violence in Liberia (2013 – 2018) | # UN Women Liberia, GoL, CSOs | 2020 | Project funds | $10,000 |
| WEE (OEEF) - Pilot the ‘Women’s Empowerment in Agriculture Index’ (WEAI) for rural gender equality – October 2020 - Research on the status of implementation of the National Social Protection Policy and Strategy, particularly for the impact on women – June 2021 - Research on the status of women’s unpaid care work in Liberia – September 2022 - Research on the status of Women’s Access to Finance: VSLAs and Orange Money – March 2020 | UN Women Liberia | - October 2020 - June 2021 - September 2022 - March 2020 | - OEEF - SN Proj - JPRWEE - BfW | - $10,000 - $15,000 - $10,000 - $20,000 |
| Baseline study of the Joint Project Sustaining Peace and Reconciliation through Strengthening Land Governance and Dispute Resolution Mechanisms | UN Women Liberia | January 2020-March 2020 | LMPTF | USD 42,000 |
| Development of Liberia Gender Country Profile | UN Women Liberia | Second Quarter 2021 | TBM | USD 100,000 |

- Evaluation Plan 2020-2024

| Evaluation name | Mandatory? (Y/N) | UNSCDF Outcome/ UN Women SP Outcome and relevant SDGs | SN Output/Relevant flagship program | Office in charge | Region/ country | Joint activity (Y/ N, indicate partners) | Planned Dates (start-end) | Budget (US$) / Sources of Funding | Status (pending/ initiated/ ongoing/ completed) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| End-Term Evaluation of Women Economic Empowerment WEE: - JPRWEE - Buy from women (BfW) | Y | UNSCDF 2020-2024 | SN Output Cluster 3 | UN Women Liberia | Liberia | - Y- JPRWEE is a joint Evaluation - N | - JPRWEE (2021) - BfW 2022 | - USD 50000.00 - USD 25000.00 | Pending | Bfw is UNW own initiative and will be managed by UN Women |
| End-Term Evaluation of 2 programmes of EVAWG: - SGBV Joint Programme - Spotlight Initiative | Y | UNSCDF 2020-2024 | SN Output Cluster 3 | UN Women Liberia | Liberia | Y | 1- Jan- 2020 2-To be decided by the spotlight initiative secretariate | 1- USD 67349.00 2- TBD be Spotlight initiative secretariate | 1- Ongoing 2-Pending | The planning as started in November 2019, following donors approval of the proposal and budget of the end term evaluation of the programme. |
| End-Term Evaluation of Women Political Participation and Leadership WPPL | Y | UNSDCF (2020-2024) | SN Output Cluster 3 | UN Women Liberia | Liberia | Y | 2021-2022 WPPL | It is from Non core available will be decided by the donor | Pending (CO will start the preparation on Donor’s directive) | This WPPL evaluation will be supported by the Donor (Govt of Canada) it is not funded under the SN 2020-24 |
| End-Term Evaluation of 3 projects under WPS: - PBF 1-Advancing implementation of UNSCRs on WPS” through legislative reforms and civic Engagemnet. - LPMTF 2-Sustaiing Peace and Reconcilation through strengthening land Governance and dispute resolution mechanisms. 3- Advanicing Reconcilation through legislative reforms and civic Engagemnet. | Y | UNSDCF (2020-2024 | SN Output Cluster 3 | UN Women Liberia | Liberia | Y (UNDP, OHCHR, WFP and UNFPA) | - Jul 2021 - Jan 2023 - Jul 2021 | These are the joint projects and these evaluations will be co funded by al the implementing agencies. | Pending |  |
| Mid-Term Evaluation of the EU/UN Spotlight Initiative | Y | UNDAF 2020-2024 | SN Output Cluster 3 | UN Women Liberia | Liberia | Y (to be done by spotlight initiative secretariate) | June 2020 | USD 74,037.5 | Pending |  |
| Liberia Country Portfolio Evaluation (SN 2020-2024) | Y | UN Women SP OEEF Output 3 | SN Output Cluster? | UN Women Liberia | Liberia | N | Prepatory work will be done in Jun – Dec 2022 While evaluation will be conducted in Jan- June 2023 | USD 75,000 (TBM) | Pending |  |
| Thematic Evaluation | N | UN Women SP OEEF | SN Output Cluster 3 | UN Women Liberia | Liberia | N | 2024 | USD 10,000 (TBM) | Pending | To be carried out on of one of the primary strategic/outcome areas of work that comprises one-third or more of the portfolio |
| Evaluations in which the office participates |  |  |  |  |  |  |  |  |  |  |
| Annual joint-review of the UNSCDF | Y | UNSCDF 2020-2024 | SN Output Cluster 3 | UN Women/ liberia | WCARO / liberia | Y, UNCT; Government counterparts | 2020 - 2024 | USD 10, 000, UNCT / RC funds | Pending |  |
| Gender Score Card Mid-Term review | Y | UNSCDF 2020-2024 | SN Output Cluster 3 | UN Women/ Liberia | WCARO / Liberia | Y, UNDP; Government counterparts | 2022 | USD 25, 000, UN Women Core funds | Pending |  |
| Final Evaluation of 2020 2024 UNSCDF | Y | UNSCDF 2020-2024 | SN Output cluster 3 | UN Women/ Liberia | WCARO / Liberia | Y, UNCT; Government counterparts | Jan. - June 2024 | UNCT/RC funds | Pending | UNWLR will be involved as participatory member but not be taking lead at all. |

Please fill out a separate row for each evaluation.

Outcomes contributing to the SDGs as per the Strategic Plan