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UN WOMEN SOUTH AFRICA MULTI-COUNTRY OFFICE

MONITORING, EVALUATION AND RESEARCH PLAN 2014-2017
	Activity 
	Partners and stakeholders 
	Planned Dates (Month and year of start and end)
	Budget

	
	
	
	Source
	Amount

	MONITORING

	Conduct quarterly monitoring visits to partners being supported under the Fund for Gender Equality, UN Trust Fund, and the Joint UNCT project support to KZN Province, South Africa, UNCT Botswana JP on Gender
	COWLHA, Grass root Soccer, SAFAIDS, AIDS Legal Network, Gender Links, Equality Now, Rural Women’s Movement, 
	Quarterly visits 
	Non-core
	US$30,000

	Undertake regular monitoring visits to the projects and field jointly with Gender Theme Group, RATESA and other forums
	Gender Theme Group, RATESA, Department of Women, Children and People with Disabilities (DWCPD), Hand-in-Hand
	Quarterly visits 
	Core
	US$20,000

	RESEARCH

	Production and dissemination of Experiences Sharing on Economic Empowerment Video (Coca-Cola Project)
	UN Women MCO Commissioned Video
	2013-2014
	Non-core
	$10,000

	Baseline study on ‘Women’s Economic Status and Opportunities’ in Lesotho 
	Ministry of Gender Equality and Women’s Empowerment, Department of Trade, and UNDP
	2014
	Core
	$20,000

	Experiences of Women in Mining Communities in Free State, South Africa
	Centre for Applied Legal Studies, University of Witts, South Africa
	2014
	Core
	$30,000

	Piloting study on social institutions and gender index indicators for South Africa
	OECD, DWCPD, Dept of Statistics, South Africa, UNDP and UN Women
	2014
	Core 
	$10,000 (cost –sharing)


	Evaluation name
	Mandatory?

(Y/N)
	UNDAF Outcome/ UN Women SP Goal, Outcome  
	Country/ MCO/ RO AWP Output
	Office in charge
	Region/ country
	Joint activity 
(Y/ N, indicate partners)
	Key Stakeholders
	Planned Dates 

(start-end)
	Budget (US$) / Sources of Funding
	Status (pending/ initiated/ ongoing/ completed)
	Remarks

	Evaluations managed by the office
	

	Evaluation of women empowerment projects in partnership with Coca-Cola (South Africa) 
	Y
	SCF/UNDAF Outcome 2
	AWP DRF 2
	UN Women MCO
	South Africa
	N
 
	Hand in Hand, Coca-Cola, DWCPD, DTI
	December 2014 (Mid-Term) and  Oct 2015 (end review)
	US$15000 (Coca-Coca, Non-Core)
	Not Started 
	


Evaluation Plan 2014-2017
	Evaluation name
	Mandatory?

(Y/N)
	UNDAF Outcome/ UN Women SP Goal, Outcome  
	Country/ MCO/ RO AWP Output
	Office in charge
	Region/ country
	Joint activity 
(Y/ N, indicate partners)
	Key Stakeholders
	Planned Dates 

(start-end)
	Budget (US$) / Sources of Funding
	Status (pending/ initiated/ ongoing/ completed)
	Remarks

	Evaluations in which the office participates
	

	Case Study to document what works in promotion of women leadership and highlight role and entry points for women leaders and gender champions to galvanize
	Y
	SCF/UNDAF Outcome 8
DRF 1
	CO AWP Output 1.3  
	UN Women Country Office

ZUBO
	South Africa
	N
	DWCPD, South Africa, Ministry of Gender, Namibia, Election Commission, South Africa and Namibia  
	April-July 2014
	US 30,000 (Core)
	Not Started
	

	End of Project Evaluation and Lessons Learned (WICBT Swaziland and Botswana Projects)
	Y
	UNDAF Outcome 2 (Swaziland) and Outcome 2 (Botswana)
	CO AWP DRF 2
	UN Women country Office


	South Africa
	Y 
With UNDP Swaziland
	Ministry of Trade, Commerce and Industry, UNDP Swaziland, Ministry of Home Affairs, Botswana, UNDP Botswana
	February-June  2014
	US 20,000 (Core) (Include consultancy, Travel, DSA)
	Not Started
	


